Report no. 103 – 19 December 2023



Murray–Darling Basin Plan: Implementation review 2023

Inquiry report

|  |
| --- |
| The Productivity Commission acknowledges the Traditional Owners of  Country throughout Australia and their continuing connection to land,  waters and community. We pay our respects to their Cultures, Country and Elders past and present.  The Productivity Commission  The Productivity Commission is the Australian Government’s independent research and advisory body on a range of economic, social and environmental issues affecting the welfare of Australians. Its role, expressed most simply, is to help governments make better policies, in the long term interest of the Australian community.  The Commission’s independence is underpinned by an Act of Parliament. Its processes and outputs are open to public scrutiny and are driven by concern for the wellbeing of the community as a whole.  Further information on the Productivity Commission can be obtained from the Commission’s website (www.pc.gov.au).  © Commonwealth of Australia 2023  CC-By logo  With the exception of the Commonwealth Coat of Arms and content supplied by third parties, this copyright work is licensed under a Creative Commons Attribution 4.0 International licence. In essence, you are free to copy, communicate and adapt the work, as long as you attribute the work to the Productivity Commission (but not in any way that suggests the Commission endorses you or your use) and abide by the other licence terms. The licence can be viewed at: https://creativecommons.org/licenses/by/4.0.  The terms under which the Coat of Arms can be used are detailed at: www.pmc.gov.au/government/commonwealth-coat-arms.  Wherever a third party holds copyright in this material the copyright remains with that party. Their permission may be required to use the material, please contact them directly.  ISSN 1447-1337 (online)  ISSN 1447-1329 (print) ISBN 978-1-74037-777-5 (online) ISBN 978-1-74037-776-8 (print)  An appropriate reference for this publication is:  Productivity Commission 2023, *Murray–Darling Basin Plan: Implementation review 2023*, Inquiry report no. 103, Canberra  Publication enquiries:  Phone 03 9653 2244 | Email [publications@pc.gov.au](mailto:publications@pc.gov.au) |

Transmittal letter

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Transmittal letterAustralian Government Productivity Commission logo  **Canberra Office** 4 National Circuit Barton ACT 2600  GPO Box 1428 Canberra City ACT 2601  Telephone 02 6240 3200  **Melbourne Office** Telephone 03 9653 2100  www.pc.gov.au  19 December 2023  The Hon Dr Jim Chalmers MP Treasurer Parliament House CANBERRA ACT 2600    Dear Treasurer  In accordance with section 11 of the *Productivity Commission Act 1998*, we have pleasure in submitting  to you the Commission’s inquiry report, *Murray-Darling Basin Plan: Implementation review 2023*.  Yours sincerely,   |  |  | | --- | --- | | **Signature** | **Signature** | | **Joanne Chong** Commissioner | **Christ Guest Associate Commissioner** | |

Terms of reference

I, Jim Chalmers, Treasurer, pursuant to Parts 2 and 3 of the *Productivity Commission Act 1998*, hereby request that the Productivity Commission (the Commission) undertake an inquiry into the effectiveness of the implementation of the Basin Plan 2012 (Cth) (Basin Plan) and water resource plans.

Background

The Basin Plan provides for the integrated management of water resources of the Murray‑Darling Basin in ways that optimise the objectives and outcomes in section 5.02 of the Basin Plan and promote the objects of the *Water Act 2007* (Cth) (Water Act).

Under section 87 of the Water Act, the Commission is required to undertake five‑yearly assessments of the effectiveness of the implementation of the Basin Plan and water resource plans. This inquiry is the second such assessment. The first assessment was completed on 19 December 2018. This subsequent 5-year assessment is due 19 December 2023.

Scope of the inquiry

In accordance with the provisions of Part 3 of the Water Act, the Commission is to report on the matter of the effectiveness of the implementation of the Basin Plan and water resource plans for the five-year period ending 19 December 2023.

In undertaking the inquiry, the Commission should assess the progress towards implementing the Basin Plan, including the:

* extent to which the Basin Plan is on track to be delivered within statutory timeframes,
* the likelihood and extent to which activities and arrangements currently in place will ensure that these provisions and timeframes will be met,
* the effectiveness of reforms to address previous Productivity Commission recommendations, including the Joint Basin government response to the Productivity Commission inquiry report: Murray–Darling Basin Plan: Five-year Assessment (2019), and
* the extent to which the current framework for implementing the Basin Plan, including the framework for monitoring, reporting and evaluation, is likely to be effective in supporting implementation of the Basin Plan.

In undertaking this assessment, the Commission should have regard to relevant agreements and reviews or audits that have recently been completed or are ongoing. Where possible, the Commission should avoid unnecessary duplication with recently completed or ongoing reviews, including those focused on compliance and enforcement, Basin Plan implementation, the Murray-Darling Basin water reform roadmap and national water reform.

The Commission should consider the impact of major droughts, floods, and the COVID-19 pandemic on the effectiveness of implementing the Basin Plan and water resource plans over the assessment period.

The Commission should also have regard to the differing responsibilities of the Basin states, the Department of Climate Change, Energy, the Environment and Water (DCCEEW), the Inspector-General of Water Compliance (IGWC), the Commonwealth Environmental Water Holder (CEWH), the Murray–Darling Basin Authority (MDBA), the Australian Competition and Consumer Commission (ACCC) and the Bureau of Meteorology (BOM).

The Commission should assess progress towards full Basin Plan and water resource plan implementation in the context of the differing timeframes applicable.

The Commission should make findings on progress to date and recommendations on any actions required to ensure full implementation of the Basin Plan and water resource plans.

The Commission should also consider and provide practical advice on the Basin Plan and water resource plans that could improve:

* the operation of the Basin Plan and water resource plans, particularly their ability to address future challenges including the impacts of climate change, their recognition of First Nations values, and their ability to efficiently support the maturation of environmental water management; and
* the efficiency and effectiveness of implementing the Basin Plan and water resource plans and contribute to the information available for the 2024 review of the Water Act and the 2026 review of the Basin Plan.

Given the breadth of the issues available for consideration, the Commission should consider reporting separately on:

* the effectiveness of the implementation of the Basin Plan and water resource plans over the five years since the previous assessment; and
* advice and recommendations on future actions and opportunities to simplify the framework of the Basin Plan to ensure effective achievement of its outcomes.

Process

In undertaking the inquiry, the Commission should undertake an appropriate public consultation process, including establishing a stakeholder working group in accordance with section 89 of the Water Act, inviting public submissions and releasing a draft report to the public.

The Commission should consult widely with relevant Australian Government, Basin state and territory government agencies, key interest groups and affected parties. These consultations should include, but not be limited to, parties with interests in agriculture, industry, the environment, First Nations people, local government, regional development, planning, emergency management and tourism. The Government has asked Basin jurisdictions to co‑operate with this inquiry, including by providing the Commission with the information it considers necessary in undertaking its inquiry.

The final report is to be provided to the Government by 19 December 2023.

**The Hon Jim Chalmers MP**  
Treasurer

[Received 2 May 2023]

Disclosure of interests

The Productivity Commission Act 1998 specifies that where Commissioners have or acquire interests, pecuniary or otherwise, that could conflict with the proper performance of their functions they must disclose those interests.

* Commissioner Joanne Chong holds an honorary position at the University of Technology Sydney.

Contents

Transmittal letter iii

Terms of reference iv

Overview 1

Key points 2

About the Murray–Darling Basin Plan and our task 3

A lot achieved, but there are still risks that key elements will not be delivered 7

A large water recovery task ahead – what should be done? 13

Recognising the values of First Nations people 17

Strengthening the Basin Plan 21

Basin governments must not waste extended timeframes 25

Findings and recommendations 27

1. About this inquiry 41

1.1 About the Murray–Darling Basin Plan 41

1.2 The Basin Plan – a significant reform 47

1.3 What we were asked to do and our approach 49

1.4 How we engaged 52

1.5 Structure of the report 53

2. Resetting the balance 55

2.1 Resetting the balance is core to Basin Plan implementation … 56

2.2 … but progress has been limited 60

2.3 Why has implementation slowed? 67

2.4 Where do we go from here? 81

3. Environmental water planning and management 101

3.1 About the Environmental Watering Plan 102

3.2 Held environmental water is being actively managed by environmental   
water holders 104

3.3 Looking back: 2019 to 2023 106

3.4 Effectiveness of environmental water planning and management 114

4. Water resource plans 133

4.1 Water resource plans are fundamental to implementing the Basin Plan 134

4.2 Making and assessing water resource plans 141

4.3 Compliance and reporting 147

5. The values of First Nations people 153

5.1 Some background 154

5.2 Assessing progress: 2019 to 2023 158

5.3 Strengthening the role of First Nations people in the Basin Plan 163

5.4 First Nations ownership of water in the Basin 172

6. Bringing new knowledge into the Basin Plan framework 175

6.1 The Basin Plan framework has an adaptive management approach 176

6.2 Processes for generating and using knowledge 186

7. Water quality and critical human water needs 193

7.1 Water quality 194

7.2 Critical human water needs 199

7.3 The northern Basin 201

8. Trading rules 207

8.1 Trading rules support water markets 208

8.2 Recent reviews of Basin water markets 210

8.3 Review of trading rules 211

9. Governance and engagement 217

9.1 An overview of arrangements 218

9.2 Accountability mechanisms under the Basin Plan 228

9.3 Information and transparency 233

9.4 Community engagement 241

Appendices

A. Public engagement 249

B. Public forums – what we heard 259

Abbreviations 271

References 275

Acknowledgments

The Commissioners would like to express their appreciation to the staff who worked on the review – Clare Sibly and Rosalie McLachlan, who led the review, Bronwyn Fisher, Catherine McCombe, Dominic Merrifield, George Steel, Jared Boorer, John Foster, Julian Parise, Krista Clift, Matthew Hyde, Michael Robinson, Michael Youren, Phil Heaphy, Sally Harvey, Sebastian Broadhurst, Simon Rohan-Jones and Uttam Khanal. Our thanks are also extended to Pragya Giri who provided administrative and project support.

The Commission would like to thank the members of the community and the organisations and government agencies who provided information for this Inquiry. We would particularly like to thank First Nations people and organisations who generously shared their stories and insights with the Commission.

Overview

|  |  |
| --- | --- |
| Key points | |
|  | The Murray–Darling Basin Plan (the Basin Plan) is a significant reform that aims to deliver a healthy, working Basin to benefit the environment, Basin communities, and current and future generations. Under the Plan, Basin governments agreed to recover 2,750 GL/y of water for the environment (~20% reduction in water for consumptive use) and an additional 450 GL/y. |
|  | Some progress has been made implementing the Basin Plan since 2018.  Water resource plans – which set out how much water can be taken from the system and how it is managed – are now all in place in Victoria, Queensland, South Australia and the ACT.  Environmental water management frameworks are also in operation, and water recovered for the environment – and partnerships to deliver this water – have improved river flows, connectivity, and ecosystem and biodiversity outcomes. |
|  | But the Basin Plan will not be fully implemented within the original timeframe or budget.  Key supply measures (infrastructure works and rule changes that offset water recovery) will not be delivered and projects to ease constraints on river operations are progressing slowly: less than half of the 605 GL/y supply measure offset has been achieved.  The program to recover an additional 450 GL/y of water via efficiency measures remains well short of its target (only 26 GL/y has been recovered). And 10 of 20 water resource plans in New South Wales, due in 2019, are still not in place. |
|  | Recent amendments to the Basin Plan and Water Act provide necessary timeframe extensions and allow for new supply measures and voluntary water purchases. Stronger reporting requirements are also included, as well as a greater emphasis on climate change and First Nations water interests. These are positive developments, but risks to full Basin Plan implementation remain. |
|  | The Australian Government – in partnership with Basin states – must ensure extended timeframes are used effectively to realise the objectives and outcomes of the Plan. A number of actions are needed:  Constraints‑easing measures are critical to achieving environmental outcomes from recovered water; they are complex projects and should be progressed separately to the remaining supply measures.  A significant water recovery task lies ahead. The Australian Government should – without delay – plan and implement a renewed water recovery approach, including voluntary water purchases. Purchases should be undertaken gradually, to avoid driving water market disruption and community adjustment pressures.  Future water recovery should occur alongside a commitment from Basin governments to assist communities, where warranted, to transition to a future with less available water. Adjustment assistance should build on the evidence about what programs work and the regional economic context.  Outstanding water resource plans in New South Wales pose a significant risk to Basin Plan implementation and must be developed and accredited as a matter of urgency. |
|  | Recognising First Nations values and delivering on First Nations interests requires Basin governments to improve how they partner and share decision‑making with First Nations people.  Building on recent reforms, Basin governments should publicly report on how water resource plans deliver on First Nations objectives and outcomes and strengthen the capacity of First Nations people to engage in Basin Plan activities. |

About the Murray–Darling Basin Plan and our task

### What is the Murray–Darling Basin Plan?

The Murray–Darling Basin Plan (the Basin Plan) was put in place in 2012 to deliver a healthy working Murray–Darling Basin – the largest river system in Australia. Established under the *Water Act 2007* (Cth), the Basin Plan was developed in response to increasing concerns about the overallocation of water in the Basin (it was put in place during the worst drought recorded, when inflows into the Murray River were at record lows) and a recognised need for a whole‑of‑Basin approach to manage the Basin’s water.

The Basin Plan sets the balance for water management – sharing available water between the environment, towns, irrigated agriculture and other industries, so the Basin’s rivers and groundwater can be sustainably managed. To do this, it sets out how much water can be taken from the Basin each year. This volume, or limit, known as the Sustainable Diversion Limit (SDL) is designed to leave enough water for the rivers, lakes and wetlands in the Basin to improve environmental health. There is an SDL for the Basin as a whole, made up of SDLs for individual valleys and shared targets for connected systems.

The SDLs are implemented through water resource plans developed by Basin states. Water resource plans set out how much water can be taken annually from each catchment, how much water is made available for the environment, requirements for surface and groundwater connectivity, and how water quality standards and critical human water needs will be met.

Meeting the SDLs requires the Australian Government to recover water entitlements from existing water users and provide these to the environment. This water recovery process is known as ‘Bridging the Gap’ (bridging the difference between the Baseline Diversion Limits and the SDLs) and can include voluntary water purchases and water‑use efficiency programs. In 2012, the Basin states (Victoria, New South Wales, South Australia, Queensland and the ACT) and the Australian Government agreed that 2,750 GL/y of surface water rights from across the Basin (about 20% less than the Baseline Diversion Limits) would be recovered for the environment by 30 June 2024.[[1]](#footnote-2)

To provide flexibility, the Basin Plan has an adjustment mechanism – the Sustainable Diversion Limit Adjustment Mechanism (SDLAM) – which can be used to change SDLs in the southern Basin. SDLAM incorporates ‘supply’ and ‘constraints‑easing’ projects and ‘efficiency measures’. Supply and constraints‑easing measures allow water recovery targets to be offset, and efficiency measures represent additional water recovery.

Basin states put forward a package of supply measures, which the Murray–Darling Basin Authority (MDBA) modelled in 2017 and determined could achieve equivalent or improved environmental outcomes with 605 GL/y less water. Amendments to the Basin Plan SDLs to reflect this – as well as a 70 GL/y reduction in the northern Basin water recovery target[[2]](#footnote-3) – were made in 2018, resulting in a new target of 2,075 GL/y (figure 1). These amendments effectively changed the ‘Bridging the Gap’ target to 2,680 GL/y – made up of a 2,075 GL/y water recovery target and the 605 GL/y offset expected via SDLAM.

The Basin Plan also allows for the recovery of 450 GL/y of water rights via efficiency measures for ‘enhanced environmental outcomes’. This is in addition to the 2,680 GL/y (figure 1).

Bridging the Gap water recovery, the SDL adjustment mechanism and the northern Basin toolkit measures are all essential to ‘resetting the balance’ of water uses in the Basin.

Figure 1 – Basin‑wide surface water recovery and SDLAM targets

This figure presents the different components of the 3,200 gigalitres per year of Basin-wide surface water recovery. This includes the original Bridging the Gap target of 2,750 Gigalitres per year, which is now reduced to 2,075 gigalitres per year. The rest of the 3,200 gigalitres is comprised of 605 gigalitres per year of offsets from supply measures, a 70 gigalitre per year reduction due to the Northern Basin Toolkit, and 450 gigalitres per year from efficiency measures. 

**a.** Bridging the Gap relies on 2,075 GL/y of surface water recovery and the supply measure offset.

The Australian Government is responsible for resetting the balance and administers water recovery programs to both bridge the gap and deliver the additional 450 GL/y. The MDBA is responsible for implementing the Basin Plan and monitoring and evaluating the outcomes.

Basin states are responsible for delivering the supply, constraints‑easing, and northern Basin toolkit measures. Supply and constraints measures are primarily funded by the Australian Government and overseen by a subcommittee of the Basin Officials Committee (BOC). BOC is the peak body of Basin government officials, with the chair a senior government official appointed by the Australian Government.

Under the Basin Plan, water recovery under Bridging the Gap and the water resource plans were to be completed by July 2019. All supply, constraints‑easing and efficiency measures were to be in place by 1 July 2024.

The Australian Government committed $5.95 billion to recover 2,750 GL/y under ‘Bridging the Gap’, $1.21 billion for supply measures, and $1.775 billion for efficiency measures and constraints‑easing projects through the Water for the Environment Special Account (WESA). Just over $2 billion committed to this part of the Basin Plan implementation remains unspent (table 1).

The Basin Plan operates alongside the Murray–Darling Basin Agreement – a water management and sharing agreement between Basin governments with roots back to 1914 – and state‑based water management arrangements.

Table 1 – Funding for resetting the balance as of 31 May 2023a

|  | Committed ($m, nominal) | Spent (incl. contracted) ($m, nominal) | Remaining ($m, nominal) |
| --- | --- | --- | --- |
| Bridging the Gap – Purchase | 2,832 | 2,832 | - |
| Bridging the Gap – Infrastructure | 3,120 | 2,978 | 142 |
| Supply measures (605 GL/y offset) | 1,212 | 485 | 727 |
| Efficiency measures (450 GL/y) | 1,575 | 384 | 1,191 |
| Constraints‑easing | 200 | 128 | 72 |
| Northern Basin toolkit | 180 | 144 | 36 |
| Total | **9,119** | **6,951** | **2,168** |

**a.** Data covers the period 2007 to 2023.

### What we were asked to do and our approach

Under the Water Act, the Commission is required to undertake five‑yearly assessments of the effectiveness of the implementation of the Basin Plan and water resource plans. This is the Commission’s second such assessment (the first assessment was undertaken in 2018).

Our terms of reference asked us to look at whether the Basin Plan was on track to be implemented on time, and where it was not, to advise on what needed to change. We approached the task by looking at:

* how the actions of governments were tracking against the timeframes set out in the Basin Plan
* whether the arrangements in place would deliver the objectives of the Basin Plan and enable its impacts and outcomes to be evaluated
* whether actions to implement the Basin Plan were effective and efficient
* whether changes were needed to ensure effective and efficient implementation of the Basin Plan going forward
* whether the governance arrangements were adequate.

We also considered how the Basin Plan could better adapt to a changing climate, better recognise the values of First Nations people and incorporate the best available science.

We did not revisit questions that fundamentally underpin the Plan, such as whether it was necessary to recover water for the environment, or questions that other agencies have been tasked and resourced to answer (such as how much water can sustainably be taken from the Basin).

We engaged widely on the Basin Plan, including with Australian Government agencies, state and territory basin governments, Murray–Darling Basin communities, and First Nations people, communities and organisations.

We held seventeen public forums across the Murray–Darling Basin (figure 2). Around 330 people attended the forums. We also held a First Nations roundtable.

Figure 2– The Commission held 17 public forums across the Murray–Darling Basin

June to August 2023

This figure shows the locations of the Commission’s public forums held from June to August 2023. They were held in St George, Goondiwindi, Moree, Dirranbandi, Bourke, Warren, Dubbo, Menindee, Renmark, Mildura, Goolwa, Hay, Griffith, Leeton, Deniliquin, Echuca and Shepparton.

### Some context

There is a lot of other monitoring and reporting on the Basin Plan. The MDBA reports on Basin Plan implementation progress in Basin Plan Report Cards and every five years undertakes a Basin Plan Evaluation (looking at what’s working, what’s not and where improvement is needed). The last Basin Plan Evaluation was undertaken in 2020.

There will also be a full review of the Basin Plan in 2026 and a review of the Water Act in 2027.

Many people in Basin communities are frustrated and fatigued by the recurrent reviews and consultation processes and slow progress on implementation. Communities are also concerned about the lack of coordination between the implementation of the Basin Plan and the operation of other Australian and state government mechanisms that affect its success. And while the Basin Plan includes mechanisms for First Nations people to provide input into the development and implementation of water management arrangements, we heard many concerns about how governments work, engage and partner with First Nations people on Basin Plan matters.

#### Recent reforms – a new agreement and the Restoring Our Rivers Act

This inquiry was conducted during a period of significant reform to the Water Act and Basin Plan. Notably, a new agreement was made between the Australian Government and most Basin states (not Victoria) and, shortly before this report was finalised, the *Water Amendment (Restoring Our Rivers) Act 2023* (Cth) was enacted.

The Restoring Our Rivers Act includes reforms to:

* extend the deadlines for meeting Basin Plan water recovery targets
* increase the range of measures that can be used to meet the 450 GL/y target and repeal the 1500 GL water purchase cap
* require the Australian Government Minister for Water to regularly publish water recovery progress reports
* allow the Australian Government Minister for Water to withdraw supply projects
* ensure climate change is considered in the 2026 review of the Basin Plan
* better recognise the cultural knowledge and practices of First Nations people and ensure Basin water management takes into account matters relevant to First Nations people, and
* improve the transparency and integrity of water markets.

Some of the recommendations made in the Commission’s interim report, and others we were considering, are no longer necessary, with the finalisation of the Restoring Our Rivers Act.

This report discusses important questions about implementation that remain relevant and will need to be addressed if the Basin Plan is to be delivered before the new deadlines.

A lot achieved, but there are still risks that key elements will not be delivered

There is some good news

While the Basin Plan, when first put in place, was heavily contested, it is now considered by many to be part of the landscape and central to securing a healthy and sustainable river system. For the most part, the conversation is no longer about whether or not there should be a Basin Plan, but rather whether there are better ways to deliver the Plan. In a recent address to the National Rural Press Club, the Chief Executive of the MDBA observed that:

… everyone shares a passion for the health of our rivers and importantly, no-one I have come across wants to do away with the Plan. Hand on heart, literally no-one has said … ‘throw it out’.

And many commented on what the Basin Plan has achieved to date. The National Irrigators’ Council, for example, said:

The Plan has been a vital tool in balancing the needs of our communities, our environment and our productive sector. It hasn’t always got it right, but it has achieved a great deal since its inception. Ensuring balance is needed so we can keep our rivers and communities healthy and thriving.

#### The 2,075 GL/y component of the ‘Bridging the Gap’ target is almost met

Most of the surface water needed to meet the 2,075 GL/y target has been recovered (figure 3) – just 46 GL/y (about 2%) remains outstanding. However, more than half the surface water was recovered before the Basin Plan was finalised in 2012.

Figure 3 – Surface water recovery and SDLAM progress, June 2023a

Surface water recovery and SDL adjustment mechanism progress, June 2023.
This figure shows progress in surface water recovery, as well as SDL adjustment mechanism progress, as at June 2023. 
Of the 2,075 gigalitres per year of ‘Bridging the Gap’, 2,029 gigalitres per year have been recovered with 46 Gigalitres per year remaining. 
Of the 650 gigalitres per year target from the SDL adjustment mechanism offset, 290 gigalitres per year has currently been offset, with a potential 315 gigalitre per year shortfall. 
Of the target of 450 gigalitres per year from efficiency measures, 26 gigalitres per year has been recovered, with 424 gigalitres per year remaining. 
There was also a 70 gigalitre per year reduction from the Northern Basin toolkit. 
All gigalitre per year recovery amounts are expressed as Long-Term average annual yields. 

**a.** The figure does not include nominal over‑recovery; the full volume recovered under ‘Bridging the Gap’ volume is reported at 2,107 GL/y. Shaded cells indicate target not yet achieved. Includes water under contract to be delivered. **b.**MDBA estimate of maximum supply measure shortfall.

For groundwater, 92% of water to meet the ‘Bridging the Gap’ target has been recovered. A further 3.2 GL/y of groundwater is yet to be recovered.

An open market tender to recover most of the outstanding balance of the 2,075 GL/y water recovery target received about 250 responses across the Basin (and for more than double the amount of water the tender called for). Offers have been accepted in the Condamine–Balonne in Queensland, and in the   
Barwon–Darling, NSW Border Rivers, Namoi, Lachlan and NSW Murray catchments in NSW.

Some, albeit limited, progress has also been made on other elements of resetting the balance since our review in 2018 (figure 3).

* There are five more supply measures operational (representing approximately 60–90 GL/y of water recovery offset). The 14 operational supply measures are estimated to be delivering about half (290 GL/y) of the 605 GL/y offset.
* On the 450 GL/y efficiency measures target, 12.2 GL/y was registered to the Commonwealth Environmental Water Holder (CEWH) at the end of June 2023 and another 13.8 GL/y was under contract.
* On the northern Basin toolkit measures, four environmental works projects have been approved for an ‘accelerated gateway model’. Three of these projects are currently completing onsite field surveys. Seven other projects are completing preliminary investigations and public consultation.

#### Significant progress made on environmental water management frameworks …

Significant progress has been made implementing the Environmental Watering Plan, which as the main instrument for achieving the best possible outcomes from the water available for the environment, is central to the Basin Plan.

The key components of the Environmental Management Framework, including the Basin‑Wide Environmental Watering Strategy, Long Term Environmental Watering Plans and annual environmental watering priorities, are now all in place. Pre‑requisite policy measures are implemented and a Northern Basin Environmental Watering Group (to coordinate the planning and delivery of water for the environment in the northern Basin) has been established.

The CEWH is well regarded in Basin communities. The CEWH has successfully engaged with local communities and built partnerships with irrigation infrastructure operators, including through its Local Engagement Officers. These partnerships and collaborations have been instrumental to the CEWH’s credibility and its success in facilitating the delivery of environmental outcomes. The Renmark Irrigation Trust, for example, spoke about a win/win arrangement.

The Trust’s partnership with the Commonwealth Environmental Water Holder, which aimed to bring Trust and Renmark Paringa Council owned floodplain land back to health, has … been a win/win arrangement; good for the riverine ecosystem, good for our business and local economy and good for our community. (sub. 24, p. 2)

#### … and benefits from water for the environment are evident

Providing and managing water for the environment is resulting in environmental benefits to the Basin, particularly at the local level. Environmental water has improved native vegetation and wetland conditions, the protection of rare and threatened biodiversity and the migration and breeding of native fish, frogs and waterbirds. Improved river flows and connectivity have helped water quality and environmental water holdings have been used to sustain targeted nurseries and ecosystems during dry periods, so that they can recover. And there are differences in outcomes between sites that are prioritised for environmental water and those that are not. The ACT Government provided the example of Blackfish.

In 2019, environmental flows between Bendora and Cotter Dams supported a large breeding event of the Blackfish that is highly significant following the population decline that resulted from the 2020 bushfires. Blackfish populations above Corin Dam, without environmental flows, have not recovered from the bushfires and remain at risk. (sub. 85, response to information request, p. 5)

The MDBA described environmental water planning and management as ‘a clear success and arrangements are world leading’, noting that the Basin Plan ‘has made a major contribution and water for the environment is now a secure and enduring element of river management’ (sub. 61, p. 17). Many participants commented on the benefits of water for the environment (box 1) and spoke about changing attitudes towards environmental watering since the Basin Plan commenced.

| Box 1 – The benefits of water for the environment: what participants said |
| --- |
| Commonwealth Environmental Water Holder  In extremely dry years (2017–20), Commonwealth environmental water played a pivotal role in breaking cease‑to‑flow events, maintaining flows to enable fish breeding and waterhole replenishment, as well as supporting core riparian and wetland habitat to promote a quick recovery of ecosystems once conditions improved. (sub. 69, p. 11)  The National Irrigators’ Council  Over 2100 gigalitres has been transferred to the Commonwealth Environmental Water holder (CEWH) and is being put to use. Over the last couple of years, the CEWH has delivered bird and fish breeding events throughout the Basin and that should be celebrated. … The CEWH needs to do more to celebrate and communicate its wins, so the public gets a real and true picture of progress. (sub. 62, p. 21)  The Victorian Government noted that at Barmah Forest, a Ramsar‑listed wetland, water for the environment has ‘improved overall health, protecting, and improving habitat and conditions for fish, waterbirds, frog and turtle species’. The site now supports 30% of the national population of the endangered Australasian Bittern, while turtle populations are recovering and are now considered ‘stable’. At the Ramsar‑listed Hattah Lakes, environmental watering combined with natural floods has resulted in a huge increase in waterbird breeding (sub. 74, p. 4). |
|  |

#### Water resource plans are in place in all Basin states, except New South Wales

Water resource plans are now all accredited and in operation in Victoria, Queensland, South Australia and the ACT.

While there were delays in making and assessing water resource plans across the Basin, in New South Wales things remain well behind schedule – just ten of its 20 water resource plans are accredited.

The absence of accredited water resource plans in New South Wales is a significant risk to the implementation of the Basin Plan – achieving the environmental and water quality outcomes of the Basin Plan relies on compliance with the SDLs and connectivity requirements, which are both set out in water resource plans. It is also not possible for the Inspector‑General for Water Compliance (IGWC) to assess New South Wales compliance with the long‑term annual SDLs without accredited water resource plans. This extends to Basin Plan requirements around water quality and critical human needs. At the River Reflections Conference in 2022, the IGWC commented that:

While NSW WRPs remain outstanding, full compliance with the Basin Plan cannot be achieved. … I can’t enforce the rules in the plans that don’t yet exist. …The single most important compliance matter in the Basin Plan is SDL compliance. … NSW’s level of accountability under the Basin Plan is not equal to that of other Basin states and the territory, each of who have accredited WRPs. (cited in sub. 75, p. 17)

But despite the importance of having all accredited water resource plans in place for delivering the Basin Plan, there are no significant consequences for New South Wales being so late with their water resource plans. There are step‑in provisions which allow the Australian Government Minister for Water to request the MDBA to develop water resource plans, but they have not been used.

#### And improvements have been made to governance and reporting arrangements

Since 2018, there have been some improvements to Basin Plan governance and reporting arrangements.

The IGWC was established in 2021 to provide oversight, monitoring, compliance and enforcement of the Basin Plan and parts of the Water Act.[[3]](#footnote-4) The establishment of the IGWC is generally considered to be an important positive change that has improved the effectiveness and accountability of compliance activities. The National Irrigators’ Council, for example, said ‘the tough cop on the beat helps build confidence in the system and its participants’ (sub. 62, p. 19).

The BOC adopted a new committee structure and transparency has increased. Basin governments have also improved how they engage, including by establishing more direct, local relationships. The MDBA, for example, undertook ‘listening tours’ and in 2021 achieved its 2019 goal of having one‑third of staff regionally based. However, notwithstanding efforts to improve engagement practices, concerns about the quality and value of Basin Plan engagement processes remain (sections 4 and 5).

Basin state agencies have also put in place several online water information portals since 2018. The Bureau of Meteorology now provides near real‑time water information by combining information from various state water agencies, dam operators, the MDBA and the CEWH. In 2020, the NSW Government also launched an online portal, WaterInsights, which has daily river reports, meteorology information and various graphs and maps designed to inform decisions around commercial water usage.

The usability and accessibility of some existing information sources have also improved.

### But resetting the balance remains far from complete

#### Even with more time, the 605 GL/y supply measure offset is unlikely to be achieved

Despite Basin governments having had six years to implement supply and constraints‑easing measures since proposing them in 2017, less than half of the 605 GL/y offset has been achieved (table 2). The MDBA estimated that, if reconciliation had taken place in June 2024 as originally planned, there would have been a shortfall of 190–315 GL/y, with the outcome likely to have been at the high end of this range. Seventeen of the 36 supply and constraints‑easing measures[[4]](#footnote-5) were not expected to be in operation by June 2024 (table 2).

Table 2 – Status of southern Basin supply and constraints projects

Progress as at July 2023

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project status | Total | Operational | Likely to be operable by June 2024 | Unlikely to be operable by June 2024 | Will not be operable by June 2024 |
| **Supply projects (excl. constraints)** | | | | | |
| NSW | 7 | 1 | 3 | 2 | 1 |
| VIC | 9 |  |  | 5 | 4 |
| SA | 4 | 4 |  |  |  |
| Shared | 11 | 9 | 2 |  |  |
| Total | 31 | 14 | 5 | 7 | 5 |
| Indicative expected offset (GL/y) | 523 | 278.1 | 73.7 | 40.6 | 130.6 |
|  |
| **Southern Basin constraints‑easing projects** | | | | | |
| NSW | 3 |  |  |  | 3 |
| VIC | 1 |  |  |  | 1 |
| SA | 1 |  | 1 |  |  |
| Shared | 1 |  |  |  | 1 |
| Total | 6 |  | 1 |  | 5 |
| Indicative expected offset (GL/y) | 82.4 |  | 20.6 |  | 61.8 |
|  |  |  |  |  |  |
| Project total | 37 | 14 | 6 | 7 | 10 |
| **Total indicative expected offset (GL/y)** | **605.4** | **278.1** | **94.3** | **40.6** | **192.4** |

The timeframe extensions under the Restoring Our Rivers Act mean reconciliation will occur at the end of 2026. While more time to deliver existing (and possibly new) supply projects is necessary, the 605 GL/y offset is still unlikely to be achieved in full. There are a number of reasons for this.

* Some key supply projects are not viable, including the Menindee Lakes project, which was initially estimated to contribute an offset of about 100 GL/y.
* Implementation costs are higher than when supply projects were first approved, and some supply projects may no longer represent value for money.
* Most projects to ease constraints are still at least 5–10 years from delivering outcomes.
* The likelihood that new supply projects will be proposed that represent value‑for‑money, will make a meaningful contribution to the offset, and be implemented by the end of 2026, is low.
* Accountability for implementing projects is weak – there are no real consequences for Basin states not delivering on supply projects.
* If the Victorian Government does not become a party to the new Basin Plan agreement, any additional offsets from Victorian‑led projects (once current funding agreements expire) will be negligible.

#### Remaining funding for supply and constraints‑easing will not be enough

A 2021 review of the WESA found that the estimated cost of the constraints and supply measures programs (largely drawing on the original 2016‑17 business cases) was around $145 million higher than the available funding. The actual costs of completing some projects are expected to be even higher than the business cases anticipated.

#### Earlier warnings about the significant risks did not result in change

The Commission’s 2018 assessment of Basin Plan implementation highlighted the need for changes to avoid the significant risk that supply and constraints‑easing measures would not be implemented as proposed. We recommended an independent advisory panel on supply projects to assess net benefits and the credibility of timeframes and milestones, and to recommend which projects should – and should not – be funded to proceed to implementation. We were also explicit about the requirement to ‘make good’ if a project failed – that is, that water would need to be recovered to make up any shortfall.

While the recommendation was agreed to in part, no independent panel was established, and there have been no apparent changes to funding approval processes by the Department of Climate Change, Energy, Environment and Water. And critically, no supply projects have been formally amended or withdrawn by the BOC, despite evidence that some projects are no longer viable.

Basin governments’ policies put in place over the last few years have also contributed to delayed water recovery projects. The Australian Government progressively reduced the scope of water recovery options (including ceasing open‑market water purchases and legislating a limit of 1,500 GL/y on water purchases towards Bridging the Gap). It also gave priority to slower, riskier and more expensive forms of water recovery. Such policy decisions reduced the incentive for Basin state governments to make progress on projects by undermining the credibility of any threat of additional water recovery.

A large water recovery task ahead – what should be done?

### Constraints‑easing measures should be separated from the supply measure package

Basin rivers are subject to a range of constraints that limit the flow rates that river operators can provide downstream. These constraints may be physical (such as flood‑prone infrastructure) or operational (river management rules designed to minimise flooding of private land).

There are potentially significant environmental and operational benefits from easing or removing constraints. Getting the most value out of environmental water relies on flow rates that allow rivers to connect to floodplains – easing constraints can enhance this connectivity by changing river operating rules. However, extensive negotiations with affected landholders are required, and these challenges were originally underestimated. Constraints projects will not be finalised by the end of 2026.

Including constraints as supply measures has restricted the ability of Basin governments to adjust these projects in response to community concerns over the proposed flow rates. These projects should be withdrawn from the supply package and pursued under a standalone program. With most constraints‑easing projects needing at least another 5–10 years to implement, the program requires a dedicated, collaborative focus from Basin governments to set it up for success.

Subject to making meaningful progress on existing projects, the Australian Government should assess the costs and benefits of further constraints easing and consider allocating additional funding for constraints easing.

### More transparency and accountability for supply measures is required

The limited progress made on the 2,680 GL/y target since 2018 means there is still a lot of work to do to complete ‘Bridging the Gap’. The feasibility, cost‑effectiveness and implementation progress of supply projects needs to be made much more transparent if meaningful progress is to be made before reconciliation.

#### Supply project funding should be contingent on compelling business cases

The deadline for supply and constraints‑easing projects has been extended to the end of 2026 and new supply measures can now be proposed. The Australian Government remains responsible for deciding whether it will fund supply projects, but there is little transparency and accountability about how these decisions are made. Before making these decisions, the Australian Government should rigorously assess:

* whether individual supply projects are likely to succeed – funding agreements should only be extended for projects that can realistically be delivered by 31 December 2026
* the cost‑effectiveness of supply projects relative to other forms of water recovery.

#### Unviable projects should be withdrawn

If necessary, the Australian Government should also exercise its new power to withdraw supply projects from the package. However, any decision to withdraw a supply project should only be made after consulting with the BOC (and in the first instance, there should be an opportunity for project proponents to adjust or re‑scope the project). The reasons for deciding to withdraw a project should be made public.

#### Progress reports should be comprehensive

The Australian Government Minister for Water is now required to table in Parliament annual reports about water recovery – with the first report due June 2024. These reports should cover all available information on project prospects, including:

* the status of projects
* funding arrangements, including the amounts spent to date
* the reasons for deciding to continue, amend or withdraw project funding, including evidence on the cost‑effectiveness of projects relative to other forms of water recovery
* the expected shortfall against the 605 GL/y water recovery offset (if any) and planned actions to make good.

### A renewed approach to water recovery is needed

#### Water purchases are necessary but must be carefully designed and staged

A substantial water recovery task lies ahead to deliver the 450 GL/y target by 2027. Even with more time for supply projects, it is unlikely the 605 GL/y supply measure offset will be met from these projects alone. At least some water will need to be purchased to meet the targets and the Australian Government should not wait until reconciliation to do so. Waiting will further delay Basin Plan implementation, risk increasing costs to taxpayers and prolong uncertainty for Basin communities.

Many inquiry participants argued for an immediate return to open tender water purchases as a way to recover water that delivers environmental outcomes more reliably and cost‑effectively than offset options. Lifeblood Alliance, for example, said:

Open tender, voluntary water purchases must be resumed as a key cost‑effective and transparent mechanism for meeting water recovery targets across the Basin. Reliance on infrastructure projects, both on and off farm, to recover water must be reduced, as these projects are high cost and low return in terms of environmental outcomes. (sub. 55, p. 2)

However, many others raised concerns about the socioeconomic impacts of previous water purchases and opposed further purchases. The Murray River Group of Councils, for example, said ‘buybacks damage communities’ (sub. 22, p. 11).

All options, including staged, voluntary water purchases, will need to be on the table for the Australian Government to reset the balance in a cost‑effective way. As earlier water recovery programs showed, purchasing water is the most cost‑effective way for governments to obtain water for the environment – the average cost[[5]](#footnote-6) of water recovery via purchases is currently $2,808/ML, compared to $8,126/ML for water recovery via gap‑bridging irrigation infrastructure (or almost three times more expensive per ML).

However, undertaking a large program of water recovery in a tight water market and short timeframe risks sharply raising prices and causing significant angst and adjustment pressure for Basin communities. Over the last three years, average annual entitlement trade in the southern Murray–Darling Basin has been between 90–100 GL/y. Purchasing the 424 GL/y needed to complete the 450 GL/y target by 2027 would significantly increase volumes of entitlement trade in the Basin.

The Australian Government should develop, without delay, a renewed water recovery program to manage these risks. Careful design and engagement with communities is required, including to manage risks to irrigation network viability.

The Commission sought views on the merits of establishing a corporate Commonwealth entity as an alternative delivery model for water recovery. While an entity operating at arms‑length from governments could offer several advantages over current institutional arrangements, it would take a number of years to establish and realise the benefits. Given the Australian Government expects the Basin Plan to be fully implemented by the end of 2027, a new water recovery entity is not currently warranted. If it becomes apparent that the extended water recovery timelines will not be met, the case for establishing such an entity could be reconsidered.

#### Adjustment assistance will be warranted in some cases

While structural adjustment in Basin communities has mainly been driven by broader economic and industry trends, water purchases have placed pressure on some communities. Smaller and more remote irrigation‑dependent communities have been affected by water purchases more than others (box 2).

A considered approach to design and staged implementation is vital. Nevertheless, some Basin communities may be adversely impacted by voluntary water purchases. Future water recovery should take place alongside a commitment from Basin governments to assist communities, where necessary and warranted, to transition to a future with less available water. Designing and implementing effective adjustment programs is difficult. Any future Basin adjustment program should include a robust evaluation framework and be based on the lessons learnt from past programs, and the regional economic context.

The renewed water recovery program should be coupled with a monitoring program to assess the broader community impacts of water recovery in the Basin and help target and design effective structural adjustment assistance. Involving affected community members and a range of other stakeholders through a shared, formal process in monitoring and assessing the socioeconomic impacts of water purchases, and the design of adjustment assistance programs, may be an effective way of giving this work credibility and legitimacy it would not otherwise have.

| Box 2 – Socioeconomic impacts of water purchases on Basin communities |
| --- |
| Water purchased by the Australian Government to meet commitments under the Basin Plan has had negative socio‑economic impacts on some Basin communities. However, at a Basin‑wide level, some aspects of economic performance have improved since the Basin Plan was put in place – for example, the gross value of irrigated agricultural production in the Basin increased by about 12% between 2013 and 2018, despite the volume of water used in irrigation declining by more than 16% over the same period.  People who sold water entitlements were compensated at market prices, with proceeds often funding on‑farm capital works, or market exits. Larger and more diverse regional centres in the Basin have largely adjusted to less water. However, there have been negative socio‑economic flow‑on effects in some small irrigation‑dependent communities, particularly following major irrigators selling large parcels of entitlements. Some Basin communities saw agricultural employment fall rapidly, without offsetting growth in other employment areas (the negative effects have been only slightly tempered by improvements to tourism resulting from improved ecological outcomes).  The size and speed of water purchases also appears to influence whether communities adapt relatively quickly (through other economic development and diversification) or experience more severe and lasting economic disruption. |
|  |

### Delivering the 450 GL/y target by 2027 will cost more than currently budgeted

The additional 450 GL/y cannot be delivered within the existing budget under the WESA.

Recent amendments to the Water Act and Basin Plan allow water purchases to contribute to the target. This is a positive step; it will improve the prospects of making progress toward the target and reduce the budgetary cost of recovering the 450 GL/y (compared to relying on ‘efficiency measures’).

However, with the price of water entitlements rising significantly in recent years, the cost of meeting the target will be substantial. The Australian Government has also said it will provide ‘significant transitional assistance’ where voluntary water purchases have flow‑on impacts on Basin communities. Given this, getting to 450 GL/y by 2027 is expected to require significant additional funding. The Australian Government has committed some additional funding, but the amount is not public.

The Commission previously raised concerns about the assumptions underpinning the 450 GL/y water recovery target, including the lack of any review point to assess the feasibility of the ‘enhanced environmental outcomes’ in schedule 5 of the Basin Plan and the value for money of the overall program. Some of the environmental benefits of this additional water are also contingent on the delivery of constraints‑easing projects – which are still 5–10 years from delivery.

Given these factors, and the potentially significant costs of purchasing large volumes of water quickly (discussed above), meeting the 450 GL/y target by the end of 2027 may not be feasible.

The 2026 Basin Plan review will consider the environmentally sustainable level of take, along with surface water and groundwater SDLs. This review is also an opportunity to assess how best to deliver the enhanced environmental outcomes that the 450 GL/y target is designed to meet.

Recognising the values of First Nations people

There are more than 100,000 First Nations people from more than 40 Nations living in the Murray–Darling Basin. First Nations people have deep connections to their land, waters and waterways and tens of thousands of years of knowledge about caring for water and river country.

However, since colonisation, First Nations people have been dispossessed of their lands and waters. This has fundamentally limited the opportunities for First Nations people to determine when, where and how they use water. First Nations people have also been excluded from the institutions that govern water resources. As the Victorian Government’s *Water is Life – Traditional Owner Access to Water Roadmap* put it, ‘Australia’s First Nations peoples have been treated as bystanders in the management, allocation, and ownership of water and water landscapes’. This has had significant implications for First Nations peoples’ economic, emotional, cultural and spiritual wellbeing.

As noted earlier, there are several mechanisms under the Basin Plan for First Nations people to provide input into the development and implementation of water management arrangements – including in the areas of water resource planning, environmental management and knowledge building. Some First Nations people said that while continuing with the Basin Plan is vital for First Nations people and culture, governments responsible for water management arrangements must do more to address the harm done to Country from lack of water. Other First Nations people said that they did not agree to or accept the Basin Plan and Murray Lower Darling Rivers Indigenous Nations (MLDRIN) said that the Plan ‘as a whole, and its individual provisions, largely override or ignore Basin Nations’ rights and obligations relating to waters and rivers’ (sub. 92, p. 3).

Basin state governments have improved how they work, engage and partner with First Nations people in the Murray–Darling Basin over the last five years. Some developments include:

* the *Murray–Darling Basin Indigenous River Rangers Program* (through the program, First Nations organisations improve waterway health and manage Country)
* the appointment of an Aboriginal member to the MDBA Board, fulfilling the legislated requirement for Indigenous representation
* the *National Cultural Flows Research Project* – a project supported by the MDBA and other Australian Government agencies to improve knowledge of cultural flows and ways of integrating cultural flows into Basin water management.

However, almost everyone with an interest in the Basin agrees that the Basin Plan needs to do more to recognise the values and deliver on the interests of First Nations people (box 3).

| Box 3 – Calls to do more: recognising the values and delivering on the interests of First Nations people |
| --- |
| Murray–Darling Basin Authority  The deep significance of First Nations' knowledge passed down over the generations is ever more pressing and more precious as our climate changes. We all need to work harder to provide a greater place for First Nations people in water management. (sub. 61, p. 7)  National Irrigators’ Council  … we are very supportive of further involvement of Indigenous Australians in managing the Basin, including but not limited to, addressing cultural flows. … NIC would welcome an enhanced First Nations engagement regime to further improve our connections with Indigenous peoples across the Basin. (sub. 62, p. 26)  National Parks Association of NSW  The independence and views of the numerous Aboriginal Nations with a connection to the Basin and its water should not be compromised. Water carries great cultural, spiritual, environmental, social and economic significance to these people … Despite the National Native Title Council (2014) stating it believed the Water Act was failing in its management objectives for Aboriginal people some ten years ago, not much has changed. (sub. 41, p. 6)  Wentworth Group of Concerned Scientists  … . the next Plan needs to address Aboriginal water rights and interests as a matter of urgency. More support is needed to build capacity of Indigenous land and water ranger programs to manage wetland Country. (sub. 81, p. 6)  River Lakes and Coorong Action Groups  We need to celebrate the wisdom of First Nations people in caring for the land and the water for millennia while it has only taken 235 years of settlement to destroy the system. We need to acknowledge the deep connection of First nations people to the land and to their totems and the intrinsic need to protect them. (sub. 15, p. 4)  MLDRIN  Solutions to the climate crisis must be informed by the knowledge and wisdom of cultures that have survived (and thrived) during significant changes to the climate over the past 60,000 years. … climate responses in the Plan must be genuinely co‑designed with Basin Nations. (sub. 92, p. 25) |
|  |

The policy landscape has also changed since the Basin Plan was introduced in 2012 (and since the Commission did the last review of the Basin Plan). Notably in 2020, all governments, along with the Coalition of Aboriginal and Torres Strait Islander Peak Organisations, signed the *National Agreement on Closing the Gap*. Under the Agreement, governments committed to work in genuine, formal partnerships with Aboriginal and Torres Strait Islander people for shared decision‑making (priority reform 1) and to transform government organisations, so they work better for Aboriginal and Torres Strait Islander people (priority reform 3).[[6]](#footnote-7)

Improving outcomes for First Nations people is also identified by the MDBA as one of the four priority themes for the 2026 Basin Plan Review.

### Meaningful, respectful and reciprocal engagement

Despite improvements in engagement made over the past five years, First Nations people – many who have invested a lot of time participating in the Basin Plan and reviews of it – shared their continuing frustration with engagement processes, which they say are often rushed and tokenistic.

A particular concern is the NSW Government’s approach to engagement on water resource plans. Water resource plans must be ‘developed having regard to the views of relevant Indigenous organisations … with respect to the objectives of Indigenous people and … the outcomes they desire’. In practice, we heard that while First Nations people were asked to provide feedback and input into plans, there was little evidence that the input was genuinely considered in decision‑making.

Meaningful engagement is crucial to building trust and working in partnership. It is not enough to recognise First Nations values in Basin Plan implementation. Transparent, accountable mechanisms by which First Nations people can inform and share decision‑making are important (they are also a key element of the priority reforms).

Recent reforms to the Water Act and Basin Plan require annual reporting about First Nations engagement activities. This is an important reform. Accountability would be further improved by requiring Basin governments to publicly report on the input and advice received from First Nations people and organisations on draft water resource plans, and how this advice is considered, actioned and reflected in finalised water resource plans.

The MDBA – in partnership with First Nations people – should develop a framework for monitoring and reporting on how governments engage with First Nations people on Basin Plan matters. This should be in place before the 2025 evaluation of the Basin Plan.

Empowering First Nations people to participate in the Basin Plan

There is a significant and growing pull on First Nation groups and individuals to participate in government processes about the Basin and broader water policy issues, with little capacity development (or funding) to support First Nations people to navigate complex water governance, policy and management arrangements.

Under the *National Agreement on Closing the Gap*, governments acknowledge that ‘adequate funding is needed to support Aboriginal and Torres Strait Islander parties to be partners with governments’. Government funding (and other supports) to First Nations people to participate in Basin Plan implementation and review activities is largely ad‑hoc. There would be value in Basin governments establishing a more structured and transparent process for providing support to First Nations people to participate in Basin Plan processes, including the development of water resource plans.

The MDBA and Basin governments are continuing to grapple with how to engage effectively with all First Nations people. Two groups – MLDRIN and the Northern Murray–Darling Basin Aboriginal Nations (NBAN) – were important in the earlier period of Basin Plan implementation (there are requirements in the Basin Plan for Basin governments to engage with MLDRIN and NBAN, and they have relied heavily on these organisations). However, the MDBA has ended its contract with NBAN. While MLDRIN has continued to actively engage in consultation processes and has made submissions to several reviews, some participants told the Commission that MLDRIN no longer has broad support by all First Nations. Many First Nations people said they felt under‑represented or forgotten in key processes.

First Nations bodies do not displace the need for other engagement mechanisms, but they can be an effective way for people to communicate concerns, advocate change, and respond to the ideas and proposals of others. Whether a new, non‑government representative body on Basin Plan matters should be established is a decision for First Nations people living in the Basin. As part of the upcoming Basin Plan Review, the MDBA – in partnership with First Nations people – should consider how best to work with First Nations people on Basin Plan implementation, given existing references to MLDRIN and NBAN.

### Progress on Aboriginal water ownership has been slow

Water ownership is important for realising First Nations people’s cultural, social, economic, spiritual and environmental aspirations. While First Nations people represent about 5% of the Basin population, they hold less than 1% of available Basin water holdings.

Many participants supported Aboriginal and Torres Strait Islander people holding water entitlements for cultural purposes, to support their economic and social participation in, and contribution to, regional communities. This aligns with the national framework for cultural flows (developed as part of the *National Cultural Flows Research Project*), which sets out a method for determining, delivering and assessing cultural flows.

The *Aboriginal Water Entitlements Program* commenced in 2018 with $40 million to support Aboriginal people in the Basin to purchase cultural and economic water entitlements. However, to date, not a single *Aboriginal Water Entitlements Program* dollar has been spent on purchasing water. As a number of participants pointed out, the $40 million will buy far less water today than in 2018, and the more than 40 First Nations in the Basin have missed out on cultural and economic benefits of water ownership. In November 2023, the Australian Government Minister for Environment and Water announced that funding for the *Aboriginal Water Entitlements Program* would be increased to $100 million.

The Department of Climate Change, Energy, the Environment and Water is in the process of consulting further with First Nations people on governance models to deliver the program (there has already been extensive engagement on this issue). The department plans to deliver the *Aboriginal Water Entitlements Program* by 2024 and has described the key program steps and timing as follows:

* develop purchasing principles and interim governance arrangements with Basin First Nations people for water entitlements in the Basin – July to November 2023
* convene a Basin‑wide First Nations Gathering (to present options for water entitlement portfolios and interim governance arrangements to Basin First Nation representatives) – November 2023
* implement the purchasing framework and commence the purchase phase of the *Aboriginal Water Entitlements Program* – January to June 2024.

### Partnerships for water delivery show promise

All Basin governments have work to do to demonstrate – and meet – their commitments under the *National Agreement for Closing the Gap*. That said, we heard about partnerships between Aboriginal and Torres Strait Islander people and governments that were working well, including to deliver environmental water in ways that also achieve cultural benefits. For example, the *Victorian Government’s Water is Life – Traditional Owner Access to Water Roadmap* sets out a pathway for how the Victorian Government intends to return water to Traditional Owners and increase their role in determining how environmental water is used for the purpose of healing Country.

There are opportunities for environmental watering to contribute to social or cultural outcomes (shared benefits) without compromising environmental outcomes. As one participant said:

There should be more partnership programs involving Aboriginal water managers and rangers, such as the Nimmie‑Caira project, which is training traditional owners in management of watered sites. (Dr Anne Jensen, sub. 39, p. 3)

The Basin‑Wide Environmental Watering Strategy is due to be updated by 2024. This is an opportunity for the MDBA – in partnership with First Nations people – to develop objectives and outcomes for shared benefits of environmental water use.

Recognising and valuing First Nations knowledges

The Basin Plan states that the ‘best available knowledge’ will be used in water resource management, which includes the local knowledge of First Nations people. As noted by a number of participants (box 3), there is scope for Basin governments to better draw on First Nations peoples’ knowledges and understanding of the river systems and natural resource management.

The success of formal partnership arrangements, such as the *Murray–Darling Basin Indigenous River Rangers Program* and the *First Nations Environmental Water Guidance Project*, should be built on to provide further opportunities for First Nations people to use their knowledge, cultural practices and connection to Country to contribute to managing and restoring waterway health in the Basin.

The Australian Government’s $20 million investment in the *Murray–Darling Water and Environment Research Program* is another key avenue to better understand First Nations’ values, and how water provides social, economic and cultural benefits to First Nations communities. It is important that Basin governments recognise that this knowledge is the cultural and intellectual property of First Nations people and respect relevant protocols and permissions around use of this knowledge.

Strengthening the Basin Plan

### Bringing new knowledge into the Basin Plan framework

The Water Act requires the Basin Plan to be developed ‘on the basis of the best available scientific knowledge and socio‑economic analysis’. Adaptive management is also a requirement of the Basin Plan. To this end, the Basin Plan requires various elements of the water management framework to be regularly reviewed or evaluated. Since the development of the Basin Plan, the relevant knowledge base has improved considerably, particularly in the areas of climate change and ecological water requirements.

A successful adaptive management approach to managing Murray–Darling Basin water resources requires generating new knowledge, reporting on that knowledge, and timely opportunities to update the water management framework to apply the knowledge. There is, however, evidence that not all aspects of the water management framework are adequately updated through the review processes to reflect the best available knowledge.

#### Climate change science should be further embedded in the Basin Plan

The Basin Plan was designed to rebalance the consumptive and environmental use of water and enable the Basin to better adapt to a changing climate, but this is an ongoing challenge. The Basin is expected to become hotter and drier, with more frequent and severe droughts and floods, and greater climate variability.

Adapting to climate challenges and increasing resilience is one of the MDBA’s six priority areas for the future, and climate change will be a focus of its 2026 Basin Plan Review. Following recent amendments to the Water Act, the MDBA is now required to consider and report on the management of climate change risks. A crucial part of this work will be considering the best available climate change projections and how they affect the Basin Plan, including the environmentally sustainable level of take.

The Basin Plan has objectives about ensuring water‑dependent ecosystems are resilient to climate change, but the related targets are not sufficiently specific, and this makes it difficult to assess progress against the objectives. More clarity is needed about how the climate change objectives are measured and assessed. The MDBA should set out how it evaluates whether these objectives are being met, including by setting out specific targets and indicators, and consider integrating this information into the Basin Plan.

#### Transparency and coordination of knowledge generation could be improved

Greater transparency around the use of new knowledge in decision making is important for trust and confidence in the Basin Plan. It can also make it easier for scientific claims to be verified and alternative or better information to be identified and shared. Transparency would be improved by making publicly available the data, modelling outputs and government‑commissioned research that is used to make decisions about water management in the Basin. This should include data, modelling and research used to reset the sustainable diversion limits in 2026.

Coordination of knowledge generation, and knowledge sharing among researchers and policy makers, could also improve the quality of Basin water management decisions and improve the efficiency of research investment. The lack of a dedicated role focused on overseeing and coordinating knowledge generation across the Basin is a gap in the Basin management framework.

### A risk‑based approach to amending water resource plans

Basin state governments play a key role in the Basin Plan by preparing and implementing catchment‑level water resource plans. The Basin Plan sets out what these plans must include, such as how much water can be taken from the system and how water will be managed during extreme events.

Making, assessing and accrediting water resource plans is a slow and complex process. There are 55 requirements in the Basin Plan that need to be met. The scale and complexity of the requirements are a key reason for some of the delays.

A number of Basin states said the requirements in the Basin Plan made for a very resource‑intensive process. The MDBA also noted that the number and complexity of the requirements has:

… led to highly complex WRPs that comprise multiple documents and incorporate a range of state instruments and strategies. This complexity, with cross‑referencing across numerous state instruments, strategies and plans means WRPs are prone to drafting errors and internal inconsistencies resulting in an invalid instrument which cannot be accredited. (sub. 61, response to information request, p. 2)

While water resource plans are designed to evolve and adapt as new information becomes available, Basin state governments may be reluctant to update their plans if the process is complex and slow. This could undermine the Basin Plan and inhibit adaptive water policy.

In its upcoming review of the Basin Plan, the MDBA should work with stakeholders to review the 55 requirements, some of which should be simplified, removed or made less prescriptive. The principle of subsidiarity should be a guiding consideration given that a core purpose of water resource plans is to implement SDLs and many other parts of the plans are largely the responsibility of state governments. The prospect of this change should not hold‑up the overdue NSW water resource plans, which for consistency with other states should meet the existing requirements.

Basin states should also be able to make a greater range of changes to water resource plans without the changes needing to be formally assessed by the MDBA. This would be for amendments that are uncontentious and clearly comply with the Basin Plan. The Water Act and regulations would need to be amended to enable these low‑risk changes to be fast‑tracked.

### Improvements to environmental water planning and management

Despite the positive outcomes and achievements from the use of environmental water, there is more to be achieved. Rivers are not regularly connecting to key wetlands on the floodplain, there are too many cease‑to‑flow events in the northern Basin and end‑of‑system flow targets are not consistently being met. Arresting and reversing long‑term declines in native fish and waterbird populations also requires sustained effort.

The focus for environmental management should now be on simplifying and embedding current best practice approaches into the Environmental Management Framework.

* The Basin‑Wide Environmental Watering Strategy – which sets out the environmental outcomes expected in key areas – needs to be more relevant and effective (including, for example, providing clear guidance, under all water availability scenarios, on the priority for achieving flow connectivity at the system scale relative to watering within a Water Resource Plan Area).
* Basin annual environmental watering priorities are general in nature, do not change significantly on an annual basis, and provide limited value in prioritising environmental water use. The 2026 review of the Basin Plan should assess the value of these priorities and whether requirements for annual priorities should be amended or removed.
* First Nations peoples’ objectives and outcomes for providing shared benefits from environmental water use should be included in the Basin‑Wide Environmental Watering Strategy and long‑term watering plans.
* Long‑term watering plans should include actions to integrate the management of environmental water with natural resource management.

### Water quality and critical human water needs

There remain long‑standing concerns about water quality and critical human water needs in the Lower Darling. We heard that towns like Walgett, Wilcannia and Bourke show that the arrangements for meeting these needs in the northern Basin are not working. The Dharriwaa Elders Group told us that ‘river foods, drinking water and water to swim in and enjoy have been taken from Walgett’ and ‘warrambuls, lakes and creeks and waterholes are regularly dry’. And that:

Critical human needs must be more clearly defined and given a high priority in water management – otherwise rivers could be understood as only existing for irrigation, water trading and other industrial purposes. We urge the Productivity Commission to ensure that critical human needs are prioritised by the Basin Plan, not only in the context of ‘extreme events’. (sub. 86, p. 6)

The NSW Government has a number of programs to address these problems, but water resource plans and water quality plans remain outstanding. Managing water quality and critical human water needs in the Lower Darling is largely the responsibility of the NSW Government. However, given that connectivity between Queensland and New South Wales is critical to outcomes, the Basin Plan has a role to play.

The upcoming Basin Plan review should identify options for securing good quality water and meeting critical human water needs in these regions. For example, the review should consider whether the ‘three‑tier’ arrangements that apply in the southern Basin might be adapted and applied to the northern Basin. Extractions in New South Wales and Queensland could also be reviewed to identify opportunities to better manage critical human water needs, with any changes given effect through amending water resource plans.

Water quality targets across the Basin will also need to be reviewed to reflect updated national guidelines and to ensure they are set at the right scale.

### Governance and institutional arrangements

Accountability mechanisms, which are central to Basin Plan implementation, need to be strengthened.

Regular reports to the Australian Parliament by the Minster for Water that identify which supply projects will receive Commonwealth funding and why (discussed earlier) will go a long way to bolstering accountability.

The rationale for tasking the IGWC with oversight of some, but not all, intergovernmental agreements is not clear. The Australian Government Minister for Water should prescribe by regulation additional intergovernmental agreements over which the IGWC should have oversight. The rationale for including or excluding agreements in the IGWC’s remit should be made public.

The activities and decisions of the BOC should also be made more transparent (including publishing decisions and the reasons for those decisions) and there is a case for an independent chair.

And while very few participants wanted more engagement with governments on the implementation of the Basin Plan, there was a lot of support for more meaningful (and in many cases, local) engagement. More joined‑up engagement efforts could reduce costs for participants and governments and allow for a more holistic consideration of some issues. A strengthened role for the Basin Community Committee in BOC decision making processes – such as a standing item at BOC meetings for the Basin Community Committee to provide advice on key issues and decisions from a community perspective – would allow communities to be part of decisions affecting them.

Basin Plan governance arrangements are complex, in part due to the number of laws, plans, agreements, policies and other instruments that govern Basin water management. The Murray–Darling Basin Agreement (a long‑standing agreement between the Australian Government and Basin states for sharing water in the southern Basin and for operating the regulated River Murray system) operates in parallel with the Basin Plan, but there are overlaps and conflicts. A review could help establish how the two instruments best work together.

### Monitoring, evaluation, and reporting

Effective reporting, monitoring and evaluation is critical to the successful implementation of the Basin Plan. While there is lots of reporting and monitoring – the 2020 evaluation by the MDBA found more than 100 outputs from monitoring and research programs – it is not necessarily providing the right information (and in fact the MDBA found that despite all the available information, it did not have what it needed to undertake the evaluation).

A more strategic approach to monitoring and reporting is needed. Ahead of the 2026 review of the Basin Plan, the MDBA should conduct a ‘stocktake’ of the Basin‑related monitoring information currently being collected (both by governments and other parties). This would allow for important information gaps to be identified. It could also reveal areas of low‑value reporting, duplication and overlap in reporting efforts, or areas where responsibility is unclear. The outcomes of this stocktake should inform the development of a new monitoring strategy.

One avenue for this work is the Basin Condition Monitoring Program, which the MDBA is developing to operate alongside other long‑term monitoring programs and other focused monitoring programs.

The MDBA is currently planning for the 2025 evaluation of the Basin Plan. This is an opportunity to assess the effectiveness of the Basin Plan, including the extent to which the objectives and outcomes of the Plan have been achieved. With the extension of timeframes, an evaluation in 2025 is a chance to identify what should be done differently over the remainder of the implementation period.

Trading rules

There has been considerable work in recent years on the framework governing water markets in the Basin, including significant reforms in the Restoring Our Rivers Act. However, the trading rules in the Basin Plan have not been thoroughly reviewed since they were made and it is unclear whether they are operating effectively, particularly in removing unnecessary trade restrictions.

The Australian Competition and Consumer Commission, which is responsible for providing advice to the MDBA about the trading rules, should be asked to conduct a comprehensive review of the rules in time for its findings to inform the MDBA’s upcoming review of the Basin Plan.

Basin governments must not waste extended timeframes

The Basin Plan is a significant, long‑term environmental reform. It has been described as ‘one of Australia’s most ambitious and complex reforms’. And while there is considerable support for the Basin Plan – it is considered central to securing a healthy and sustainable river system – and real progress has been made – it has fallen well behind schedule and was not going to be delivered within the original timeframe or budget. Delivery delays also reduce the environmental outcomes of the Basin Plan and Basin communities continue to face uncertainty.

The recent amendments to the Basin Plan and Water Act provide necessary timeframe extensions and more flexibility and accountability, but do not address all the factors that have contributed to the lack of progress across the range of projects. Escalating costs, across both water recovery and the supply projects, also means resetting the balance will cost taxpayers considerably more than originally expected.

All Basin governments need to support implementation progress for a healthy, working Basin to be sustained.

Key to protecting public investment in the Basin Plan, achieving environmental outcomes and providing Basin communities with greater clarity about their futures, is for the Australian Government to be more accountable for its funding decisions on the supply, constraints‑easing and toolkits projects during the next phase of implementation.

Given the large water recovery task ahead, the Australian Government needs to start working on a dedicated water recovery program. Undertaking voluntary purchases in a well‑prepared, staged way is necessary to help minimise market disruption and negative socio‑economic impacts on Basin communities. Future water recovery should occur alongside a commitment from Basin governments to assist communities, where warranted, to transition to a future with less available water. Adjustment assistance should build on the evidence about what programs work and complement existing regional development strategies.

Outstanding water resource plans must be a priority for the NSW Government. Crucially, all Basin governments must materially improve how they work, partner and share decision‑making with First Nations people, not only on water resource plans, but a range of other Basin Plan matters. Changes are also needed to improve how the Basin Plan adapts over time, including to new knowledge, climate change and contemporary views of Basin communities and the wider Australian community.

Findings and recommendations

### Chapter 2. Resetting the balance

|  | Finding 2.1  Resetting the balance has slowed because of weak governance in a changing water market |
| --- | --- |
| Resetting the balance in the Basin has slowed since 2018 and will not be completed by the original deadline of 30 June 2024. Limited progress has been made toward environmental water recovery targets, including towards the additional 450 GL/y. This is largely because of government policy decisions, alongside rapid growth in water entitlement prices.  Key supply projects will not be completed by the original deadline. Accountability for implementing the supply projects is weak, and Commonwealth funding arrangements have failed to drive effective project implementation by Basin state governments. Key projects are unviable, but Basin governments are not transparent about the need to rescope or withdraw these projects, or the implications of failing to deliver projects on time.  These delays have substantially increased the financial costs of meeting Basin Plan water recovery targets, prolonged the uncertainty Basin communities face, and reduced the potential environmental outcomes of the investment in the Plan. | |
|  | |

|  | Finding 2.2  Program design has not suited the complexity of constraints‑easing projects |
| --- | --- |
| Constraints‑easing projects have progressed slowly, with detailed property‑level modelling and extensive landholder engagement needed to identify and manage the impacts of higher flow rates. Including constraints in the supply measure package has led to a focus on maximising the water recovery offset, rather than the environmental and operational benefits of easing constraints. | |
|  | |

|  | Finding 2.3  Slow progress on the northern Basin toolkit reflects unclear accountability for delivering program outcomes |
| --- | --- |
| Delays implementing the northern Basin toolkit measures are a result of inadequate accountability for delivery, as well as a lack of oversight and review of the measures. Public information about project progress has been sparse, and there is no framework in place to monitor the environmental merits of these projects as they progress. | |
|  | |

|  | Finding 2.4  Full delivery of the 605 GL/y supply measure offset by December 2026 is uncertain |
| --- | --- |
| Full delivery of the 605 GL/y supply measure offset by December 2026 is at risk because:   * key projects, including the Menindee Lakes project, will not be delivered as designed * constraints‑easing projects cannot be completed in full by December 2026 (which may also limit the offset achieved by other supply measures) * there are unlikely to be enough new supply projects that are implementable by December 2026, represent value for money and can make a substantial contribution to the water recovery offset.   There is a strong possibility of a significant water recovery shortfall in the southern Basin. | |
|  | |

|  | Finding 2.5  The costs of achieving the enhanced environmental outcomes (schedule 5 of the Basin Plan) through water recovery have risen substantially |
| --- | --- |
| The budget available under the Water for the Environment Special Account to recover the 450 GL/y will not be adequate to achieve the target, even with water purchases.  The 2026 Basin Plan review is an opportunity to assess how to cost‑effectively deliver the enhanced environmental outcomes that the 450 GL/y target is designed to meet. | |
|  | |

|  | Recommendation 2.1  The Australian Government should cease funding unviable supply measures |
| --- | --- |
| The Australian Government should cease funding any supply measure that is unlikely to deliver on its planned outcomes or is found not to be cost‑effective.  Before this decision is made, the Australian Government Minister for Water should seek the advice of the Basin Officials Committee. The advice should be provided within three months of the request, and could include a proposal to rescope the project and amend the notification to the Murray–Darling Basin Authority.  If funding is ceased, the measure should be withdrawn under s 7.12(6) of the Basin Plan. | |
|  | |

|  | Recommendation 2.2  Australian Government funding decisions should be publicly reported |
| --- | --- |
| The Australian Government Minister for Water should ensure that reports prepared under s. 85AB of the *Water Act 2007* (Cth) include:   * the northern Basin toolkit measures * statements on which supply, constraints‑easing and toolkit measure projects remain feasible and represent value for money, and which ones will no longer be funded * an update on any expected shortfall against the supply measure offset, and planned actions to make good. | |
|  | |

|  | Recommendation 2.3  Reset and extend implementation of constraints‑easing projects |
| --- | --- |
| Basin governments should remove southern Basin constraints‑easing projects from the supply measure package.  The Basin Plan requires the Murray–Darling Basin Authority to develop a constraints‑easing implementation roadmap. This roadmap should include:   * pathways to incremental improvements in flow rates in each river, including evidence on the benefits of gradual increases in flow rates * a process to provide procedural fairness to affected landholders * a sequence for constraints‑easing projects.   Subject to making meaningful progress on incremental constraints easing, the Australian Government should assess the costs alongside the environmental and operational outcomes of further constraints easing, and consider allocating additional Water for the Environment Special Account funding towards constraints easing. | |
|  | |

|  | Finding 2.6  Adjustment assistance should draw on local strengths and be closely monitored for effectiveness |
| --- | --- |
| Basin Plan implementation has taken place during a period of socioeconomic change in the Murray–Darling Basin. Reduced water availability under the Basin Plan has had relatively small impacts on aggregate socioeconomic outcomes in the Basin, compared to other drivers of change – including climate variability and reduced on‑farm labour. However, water purchases have contributed to adjustment pressures in some Basin communities, especially smaller and more remote irrigation‑dependent communities.  Adjustment assistance can help communities better adapt to structural change, but designing a program that generates demonstrable and lasting economic benefits is not easy. Evaluation of adjustment assistance is not generally done well, but the available evidence suggests assistance is typically more effective where it leverages the competitive strengths of the local community and is well‑integrated with prevailing regional development strategies and frameworks. Ongoing monitoring and adaptation of adjustment programs is crucial for success. | |
|  | |

|  | Recommendation 2.4  Develop a renewed approach to water recovery |
| --- | --- |
| Given the substantial water recovery task, the Australian Government should develop and implement – without delay – a renewed approach to water recovery.  This approach should consider all water recovery options, including voluntary water purchases. Any purchasing should be undertaken gradually, to avoid driving water market disruption and community adjustment pressures. Water purchases should also be coordinated with irrigation network rationalisation where necessary to avoid impacts on irrigation network viability.  The Australian Government should update and publish its water recovery strategy to clarify how this renewed water recovery program will proceed. The strategy should outline:   * the sequencing of different water recovery targets (both the 450 GL/y and any expected 605 GL/y shortfall), based on the progress of supply and constraints measure implementation * how different water recovery options will be used, based on the availability of projects, their cost‑effectiveness and likely socioeconomic impact * when and how community adjustment programs will be implemented, based on socioeconomic monitoring * requirements for monitoring, evaluation, reporting and improvement on adjustment program design. | |
|  | |

|  | Finding 2.7  Effective institutional arrangements are central to efficient water recovery |
| --- | --- |
| A corporate Commonwealth water recovery entity operating at arms lengths from governments could offer several advantages over current institutional arrangements for effective and efficient water recovery. Characteristics of an effective dedicated water recovery entity would include:   * Independence: the ability to depoliticise project administration and decision making. * Collaboration: the ability to work on the ground with proponents and streamline project development. * Trust and credibility: having a clear mandate and the flexibility to engage expertise as needed would provide greater clarity and confidence to Basin communities.   However, there is not enough time to establish and realise the benefits of a new corporate water recovery entity within the amended Basin Plan timeframes. If it becomes apparent that the amended water recovery timeframes will not be met, the case for establishing such an entity could be reconsidered. | |
|  | |

### Chapter 3. Environmental water planning and management

|  | Finding 3.1  Identifying key Basin environmental assets and priority management actions in the Basin‑Wide Environmental Watering Strategy |
| --- | --- |
| In 2025, the Murray–Darling Basin Authority is expected to publish a Basin‑wide conservation prioritisation framework to identify places of high conservation value and prioritise management actions to conserve their critical assets, values and functions. The development of this framework and its inclusion in the Basin‑Wide Environmental Watering Strategy has the potential to provide greater direction to, and accountability for, the Commonwealth Environmental Water Holder’s decision making on environmental watering. | |
|  | |

|  | Recommendation 3.1  Improving the effectiveness of the Basin‑Wide Environmental Watering Strategy |
| --- | --- |
| The Murray–Darling Basin Authority’s next update to the Basin‑Wide Environmental Watering Strategy should include:   * an objective that environmental watering should seek to contribute to social or cultural environmental outcomes (where compatible with environmental outcomes) * First Nations peoples’ objectives and outcomes, under all water availability scenarios, for shared benefits from environmental water use (where compatible with environmental objectives) at the Basin‑wide scale * clear guidance, under all water availability scenarios, on the priority for achieving flow connectivity at the system scale relative to watering within a water resource plan area * risks to achieving environmental objectives, in a changing and more variable climate. | |
|  | |

|  | Recommendation 3.2  The adaptive management of long‑term watering plans |
| --- | --- |
| In the next iterations of long‑term watering plans, Basin state governments should include:   * First Nations peoples’ objectives and outcomes under all water availability scenarios for shared benefits from environmental water use (where compatible with environmental objectives) for each water resource plan area * planning and management actions to integrate the management of environmental water with natural resource management (such as habitat restoration or weed and pest control). | |
|  | |

|  | Recommendation 3.3  Basin annual environmental watering priorities require review |
| --- | --- |
| As part of the 2026 review of the Basin Plan, the Murray–Darling Basin Authority should assess the value of Basin annual environmental watering priorities and whether the Basin Plan requirements for these annual priorities should be amended or removed. | |
|  | |

|  | Recommendation 3.4  Delivering shared benefits from the use of environmental water |
| --- | --- |
| First Nations peoples’ objectives and outcomes for providing shared benefits from environmental water use for inclusion in the Basin‑Wide Environmental Watering Strategy and long‑term watering plans should be developed by First Nations people through genuine, resourced partnerships with the Murray–Darling Basin Authority (for the Basin‑Wide Environmental Watering Strategy) and Basin state governments (for long‑term watering plans), consistent with commitments made by all governments under the National Agreement on Closing the Gap. | |
|  | |

### Chapter 4. Water resource plans

|  | Finding 4.1  Incentives to complete water resource plans on time are weak |
| --- | --- |
| The Basin Plan does not adequately incentivise Basin states to complete their water resource plans within the legislated timeframes, and Basin state governments face no significant consequences for failing to do so. | |
|  | |

|  | Finding 4.2  Without water resource plans, the Murray–Darling Basin Plan cannot be fully implemented |
| --- | --- |
| Half of the water resource plans for New South Wales remain outstanding more than 10 years after the Basin Plan was put in place and almost four years after an already extended deadline. Without all water resource plans in place across the Basin, the Murray–Darling Basin Plan cannot be fully implemented or properly enforced. With 10 of 20 plans outstanding, there is a greater risk of over extraction in New South Wales compared to other Basin states. | |
|  | |

|  | Finding 4.3  Preparing and assessing water resource plans is unnecessarily difficult |
| --- | --- |
| The process of preparing and assessing water resource plans is onerous and time‑consuming. This is in part because the requirements in the Basin Plan are unnecessarily complex and prescriptive. | |
|  | |

|  | Recommendation 4.1  Simplify requirements for water resource plans |
| --- | --- |
| In its 2026 Basin Plan Review, the Murray–Darling Basin Authority should consider how the requirements for water resource plans could be simplified and whether some requirements should be removed or made less prescriptive and more focused on outcomes. The principle of subsidiarity should be a guiding consideration in this review, given many of the arrangements included in the plans are largely the responsibility of state and territory governments, with the implementation of sustainable diversion limits being a core purpose of water resource plans. | |
|  | |

|  | Recommendation 4.2  A risk‑based approach to amending water resource plans |
| --- | --- |
| The *Water Act 2007* (Cth) should be amended to allow the accreditation of amendments to water resource plans to be fast‑tracked, where those amendments are low‑risk and clearly comply with the Basin Plan. | |

|  | Recommendation 4.3  Revise annual water resource plan compliance reporting |
| --- | --- |
| The Murray–Darling Basin Authority, in consultation with the Inspector‑General of Water Compliance and Basin states, should revise the annual water resource plan compliance reporting template to ensure it:   * does not duplicate information collected elsewhere * reflects the water resource plan compliance framework * helps assess whether water resource plans are delivering on the objectives and outcomes of the Basin Plan, including as part of the 2025 evaluation. | |

### Chapter 5. The values of First Nations people

|  | **Recommendation 5.1**  **Strengthen the roles of First Nations people in the Basin Plan** |
| --- | --- |
| In line with the priority reforms committed to under the National Agreement on Closing the Gap, Basin states should:   * publish the input and advice received from First Nations people and organisations on draft water resource plans * publicly report on how the advice is considered, actioned and reflected in finalised and amended water resource plans.   In addition, the Murray–Darling Basin Authority should:   * in partnership with First Nations people, develop a framework for monitoring and reporting on how Basin governments engage with First Nations people on Basin Plan matters. This should be in place before the 2025 evaluation of the Basin Plan * in partnership with First Nations people, consider how best to work with First Nations people on Basin Plan implementation, given existing references in the Plan to Murray Lower Darling Rivers Indigenous Nations (MLDRIN) and the Northern Murray–Darling Basin Aboriginal Nations (NBAN).   Basin states should provide the Secretary of the Australian Government Department of Water with information about First Nations engagement on Basin Plan water management matters, for the purpose of the Secretary’s annual reports on First Nations engagement.  All Basin governments should:   * actively pursue opportunities to work in formal partnership with First Nations people on the implementation of, and shared decision‑making about, the Basin Plan and provide funding and capacity strengthening support to these partnerships * work in partnership to develop, then make public, their First Nations engagement intentions early, including for the upcoming 2025 Basin Plan Evaluation and 2026 Basin Plan Review. | |
|  | |

|  | Finding 5.1  Limited progress made on the Aboriginal Water Entitlements Program |
| --- | --- |
| The Australian Government has made little progress on the Aboriginal Water Entitlements Program since the program was announced in 2018. Given the increase in water entitlement prices over that period, the $40 million original program budget will buy less water today than it would have in 2018. | |
|  | |

### Chapter 6. Bringing new knowledge into the Basin Plan framework

|  | Recommendation 6.1  Climate projections and the Basin Plan |
| --- | --- |
| In its 2026 review of the Basin Plan, the Murray–Darling Basin Authority should consider and report on:   * how climate change has impacted, and is projected to impact, the Basin’s water resources, and * how climate change science has informed any proposed amendments to the Basin Plan, including to the environmentally sustainable level of take. | |
|  | |

|  | Recommendation 6.2  Specific measures or targets for evaluating climate change resilience |
| --- | --- |
| The Murray–Darling Basin Authority should set out how it evaluates whether water‑dependent ecosystems are resilient to climate change, including by specifying which targets are relevant to climate change resilience and how progress against these targets is monitored. When reviewing the Basin Plan in 2026, the Murray–Darling Basin Authority should also consider whether some of this information should be integrated into the Basin Plan. | |
|  | |

|  | Recommendation 6.3  Publishing material used for decisions |
| --- | --- |
| Government agencies should publish, including in regular scheduled reports, the data, modelling outputs and government‑commissioned research that informs their decisions about water management in the Basin. This should include any decisions related to resetting sustainable diversion limits. | |
|  | |

|  | Recommendation 6.4  Strategic coordination of knowledge generation and sharing activities |
| --- | --- |
| The Australian Government should establish a role for overseeing and coordinating water‑related knowledge generation and knowledge sharing across the Murray–Darling Basin. | |
|  | |

Chapter 7. Water quality and critical human water needs

|  | Finding 7.1  Poor water quality and critical human water needs in the northern Basin |
| --- | --- |
| Some communities in the northern Basin live with a precarious supply of safe drinking water. The current arrangements in the Basin Plan, even if implemented, will not ensure these needs are met. | |
|  | |

|  |  |
| --- | --- |
|  | Recommendation 7.1  The Basin Plan should play a greater role in improving water quality and securing critical human water needs in the northern Basin |
| Improving water quality and meeting critical human water needs in the northern Basin should be a key priority for the 2026 Basin Plan Review. Noting the connectivity of water systems in the northern Basin, the review should consider:   * how the Basin Plan can contribute to improving water quality and securing critical human water needs in the northern Basin * whether arrangements for the southern Basin can be adapted for the northern Basin * whether changes should be made to other instruments and agreements, including the Murray–Darling Basin Agreement and state water sharing plans. | |

### Chapter 8. Trading rules

|  | Recommendation 8.1  A comprehensive review of trading rules in the Basin Plan |
| --- | --- |
| The Murray–Darling Basin Authority (MDBA) should ask the Australian Competition and Consumer Commission (ACCC) to conduct a comprehensive review of the Basin Plan trading rules. The review should consider, among other things, how unnecessary trade restrictions should be identified and removed.  The *Water Act 2007* (Cth) should be amended to enable the ACCC to provide advice to the MDBA about the trading rules on its own initiative. The ACCC should notify the MDBA before preparing any such advice. | |
|  | |

### Chapter 9. Governance and engagement

|  | Recommendation 9.1  Extending oversight of intergovernmental funding agreements relevant to Basin Plan implementation |
| --- | --- |
| The Australian Government Minister for Water should prescribe by regulation additional intergovernmental funding agreements that the Inspector‑General of Water Compliance (IGWC) should oversee.  The Australian Government Department of Climate Change, Energy, the Environment and Water should consult with Basin state governments, the IGWC and other interested parties to determine which new and existing agreements should be prescribed and make public the rationale for including or excluding each agreement in the IGWC’s remit. | |
|  | |

|  | **Finding 9.1**  **Information about Basin Plan funding, processes and outcomes can be difficult to access** |
| --- | --- |
| Information about Murray–Darling Basin water management is fragmented and difficult to navigate. This can cause confusion about which agency to go to for information and reported information can differ across agencies. Communities can find it difficult to understand and engage with water policy and practice. Inconsistencies in information can undermine public confidence and trust in Basin institutions and instruments. | |

|  | **Recommendation 9.2**  **Improving the transparency of the Basin Officials Committee** |
| --- | --- |
| The Basin Officials Committee (BOC) should be more transparent. The BOC should publish:   * meeting agendas, communiqués and information on meeting outcomes * BOC decisions and the reasons for those decisions * formal directions to the BOC from the Ministerial Council * information on the BOC’s strategic priorities, stakeholder engagement activities, governance practices and sub‑committees.   The *Water Act 2007* (Cth) should be amended to enable the appointment of an independent Chair to the BOC. | |

|  | **Finding 9.2**  **Engagement by government agencies on the Basin Plan is not well coordinated** |
| --- | --- |
| There are many Australian Government and Basin state agencies that engage with the community on the Murray–Darling Basin Plan. These engagement processes are generally not well coordinated, which can frustrate participants. More joined‑up engagement efforts could reduce costs for participants and governments and allow for a more holistic consideration of issues. | |

|  | **Finding 9.3**  **Well defined local outreach can be an effective engagement approach** |
| --- | --- |
| Local, place‑based engagement mechanisms can be an effective way of ensuring community views are sought, responded to, and considered by decision‑makers. A permanent local presence in communities can help foster community understanding of water policy processes and build relationships and trust. The Commonwealth Environmental Water Holder Local Engagement Officer model provides a good template for effective local engagement. | |

|  |  |
| --- | --- |
|  | Recommendation 9.3  Strengthening the community voice in Basin decision‑making |
| The Basin Community Committee should have a standing agenda item at Basin Officials Committee meetings to provide input and advice on matters from a community perspective. The Basin Officials Committee should publicly report on how this input and advice has been considered and has influenced decision‑making. | |

# About this inquiry

The Murray–Darling Basin Plan (the Basin Plan) was put in place in 2012 to improve and protect the health of the Murray–Darling Basin (the Basin) to benefit the environment, Basin communities and industries, and future generations. To allow Basin governments and communities to manage the changes needed for a healthy working Basin, the Basin Plan is being implemented over a transition period.

This inquiry is a review of the implementation of the Basin Plan.

The Productivity Commission is required, under the *Water Act 2007* (Cth), to assess the effectiveness of the implementation of the Basin Plan and water resource plans every five years. This function was included in the Water Actto ensure there is a regular independent review, which the Minister at the time noted ‘is necessary to ensure continuing public confidence in the implementation of the Basin Plan’ (Assistant Minister for Social Services 2014).

This inquiry is the Commission’s second assessment. The first was conducted in 2018.

## About the Murray–Darling Basin Plan

### About the Murray–Darling Basin

The Basin is a system of interconnected rivers and lakes in Australia’s south‑east. The River Murray and the Darling‑Baaka River are the two main rivers in the Basin.

The Basin covers over 1 million square kilometres, including large areas of New South Wales, all of the ACT and parts of Victoria, Queensland and South Australia (figure 1.1). It has two key connected areas – the northern Basin and the southern connected system. Water in the northern Basin runs into the Darling‑Baaka River and water in the southern Basin runs into the River Murray.

The Basin provides water to more than 2.3 million people and supports 7,300 irrigated agriculture businesses (MDBA 2020p). It is also home to 16 internationally significant wetlands, 35 endangered species and 120 different species of waterbirds (MDBA 2023r). And it is an area of cultural significance to Aboriginal and Torres Strait Islander people[[7]](#footnote-8) – it is home to more than 100,000 First Nations people from over 40 different First Nations.

Figure 1.1 – The Murray–Darling Basin



### What is the Murray–Darling Basin Plan?

The Basin Plan is an Australian Government instrument that gives effect to agreements between Basin state governments[[8]](#footnote-9) and the Australian Government about how to reset the balance between the use of water for the environment, irrigation and communities to improve the health and sustainability of the river system.

The Basin Plan was developed in response to increasing concerns about over‑allocation of water in the Basin and the health of the river system and followed decades of Basin governments seeking to establish arrangements to share and jointly manage the Murray–Darling river system (box 1.1, figure 1.2). The Murray–Darling Basin Authority (MDBA) said:

The introduction of the Basin Plan was recognition that change was needed to past attempts to share the water, and that a whole‑of‑Basin approach was required to manage the Basin’s water resources in the national interest, including to meet Australia’s international obligations. (sub. 61, p. 1)

| Box 1.1 – The long road to the Basin Plan |
| --- |
| In 1914, after four failed attempts by New South Wales, Victoria and South Australia to agree on how to share and jointly manage the river, the three states and the Australian Government signed the River Murray Waters Agreement (RMWA).  The RMWA set out states’ share of the water, a governance structure and an extensive capital works program to regulate the river. The RMWA was settled under the pressure of a drought, funding by the Australian Government (that filled the gap between what the states were prepared to pay for capital works and their estimated costs), and the Australian Government mediating negotiations. Under the RMWA, all decisions required unanimity. As autonomous entities, the states were committed to retaining their independence and would only join in co‑operative action when each of them benefited.  The period up to the completion in 1979 of the last regulating structure – the Dartmouth Dam – were the building years, where the capital works program agreed in 1914 was rolled out. This work occurred in the context of water take being well within the volume available, when water quality and riverine environmental health were neither significantly impacted nor well understood, and when social values embraced the extraction of water for irrigation. The RMWA yielded the economic benefits of storing and regulating water for irrigation in the three states and was a vehicle for economic development.  From the 1970s on, as water allocations began to push against the limits of availability, the consequent environmental stress became evident and of increasing concern. Addressing water quality entailed costs, by way of constraints on state prerogative, limits on irrigation water take and capital works projects like salt interception schemes, which yielded benefits outside the jurisdiction. The requirement for unanimity meant it was difficult to agree on the actions needed to address water quality.  In 1987 the RMWA was broadened to cover the entire Murray–Darling river system, and became the Murray–Darling Basin Agreement (MDB Agreement). In time, Queensland and the ACT became signatories. However, governance, roles and powers under the new MDB Agreement did not change to address the environmental challenges.  On the eve of Australia Day in 2007, during the worst ever recorded drought, the then Prime Minister John Howard proposed that the Australian Government take over water management in the Basin.  … the old way of managing the Murray–Darling Basin has reached its use‑by date. The tyranny of incrementalism and the lowest common denominator must end. I will therefore be writing to all relevant State and Territory Leaders requesting that they refer to the Commonwealth their powers of water management over the Murray–Darling Basin. (Howard 2007)  The proposal required a referral of Constitutional powers from the states to the Australian Government, which did not occur. With bipartisan Parliamentary support, the Australian Government proceeded with the Water Act (that relied on its own powers) which enabled the Australian Government, in conjunction with the Basin states, to manage the Basin’s water resources in the national interest. The MDB Agreement remained in place and states retained water management powers. The Water Act established the Murray Darling Basin Authority, a statutory agency with a Basin‑wide remit (sitting over the roles and responsibilities that states had exercised for over 100 years).  Source: Guest (2016). |
|  |

Figure 1.2 – Key developments in the history of the Basin Plan

This figure shows key developments in the history of the Basin Plan.
1914: the signing of the first water sharing agreement (the River Murray Waters Agreement) between NSW, Vic and SA
1917: formation of the River Murray Commission (RMC)
1987: The Murray Darling Basin Agreement is signed, establishing the Murray Darling Basin Commission (replaces the RMC).
1997: The beginning of the Millenium drought, the longest recorded drought in Australia’s history.
2004: The National Water Initiative is approved by COAG, which commits all Australian governments to improve how water resources are managed.
2007: Water Act (2007) is introduces, which established the Murray Darling Basin Authority and creates the Basin Plan.
2012: The Basin Plan becomes law.


Source: Based on Inspector‑General of Water Compliance, sub. 75, p. 2.

Signed into legislation in 2012 under the Water Act, the Basin Plan sets out how much surface water and groundwater can be taken from the Basin each year for irrigation, town and industry. This volume, or limit, known as the Sustainable Diversion Limit (SDL) is designed to leave enough water for the rivers, lakes and wetlands in the Basin. There is an SDL for the Basin as a whole, made up of SDLs for individual valleys and catchments.

Water resource plans are central to how these SDLs are met. Developed by Basin states, catchment‑level water resource plans are the legal mechanism which set out how much water can be taken annually from each catchment, how much water will be made available for the environment and how water quality standards and critical human water needs will be met.

Meeting the SDLs requires the Australian Government to recover water entitlements from existing water entitlement holders. This process is known as ‘Bridging the Gap’ (bridging the difference between the Baseline Diversion Limits and the SDLs). In 2012, the Basin states and the Australian Government agreed that 2,750 GL/y of water from across the Basin would be recovered for the environment by 30 June 2024.

To provide flexibility, the Basin Plan has an adjustment mechanism – the Sustainable Diversion Limit Adjustment Mechanism (SDLAM) – which can be used to change SDLs in the southern Basin. The adjustment mechanisms are ‘supply’ and ‘constraints‑easing’ projects and ‘efficiency measures’ (that modernise water delivery infrastructure for consumptive users and are effectively additional water recovery, chapter 2).

Basin states put forward a package of supply measures, which the MDBA modelled in 2017 and determined they could achieve equivalent or improved environmental outcomes with 605 GL/y less water. Amendments to the Basin Plan SDLs to reflect this – as well as a 70 GL/y reduction in the northern Basin water recovery target[[9]](#footnote-10) – were made in 2018, resulting in a new target of 2,075 GL/y. These amendments effectively changed the ‘Bridging the Gap’ target to 2,680 GL/y – made up of a 2,075 GL/y water recovery target and the 605 GL/y offset expected via the SDL adjustment mechanism.

The Basin Plan also provides for the recovery of an additional 450 GL/y of water rights via efficiency measures to pursue enhanced environmental outcomes. These efficiency measures are additional to the 2,680 GL/y.

Bridging the Gap water recovery, the SDL adjustment mechanism and the northern Basin toolkit measures are all essential to ‘resetting the balance’ of water uses in the Basin (chapter 2).

The Australian Government is responsible for resetting the balance. Basin states are responsible for delivering supply, constraints and northern Basin toolkit projects. All elements of resetting the balance were to be completed by 1 July 2024 (figure 1.3). However the date was amended in November 2023 (discussed below).

The Basin Plan also required new management arrangements, including water resource plans and a framework for the management of environmental water, to commence by 1 July 2019 (figure 1.3). The water resource plans need to be assessed by the MDBA and accredited by the Australian Minister for Water.

Figure 1.3 – Elements of the Basin Plan and original timings

Elements of the Basin Plan and timings.
To July 2019: water recovery to bridge the gap between the Baseline Diversion Limit and the new Sustainable Diversion Limit (SDL).
To July 2024: adjustment to the new SDLs; supply projects; efficiency projects; constraints easing projects; and toolkit measures (no deadline).
Resetting the balance to be completed 30 June 2024.
New management arrangements to commence 1 July 2019.
Environmental water management; Water Resource Plans, water trading rules; water quality, critical human water needs; compliance with the Plan and SDLs; and monitoring and evaluating the Plan.
Review of the Plan in 2026

The MDBA has two distinct roles. Under the Murray–Darling Basin Agreement, the MDBA is responsible for operating the dams, locks and weirs that regulate the River Murray and managing joint natural resource programs on behalf of the states and the Australian Government. Under the Water Act, the MDBA is responsible developing the whole of Basin Plan, including assessing water resource plans, periodically reviewing the Basin Plan, and monitoring and evaluating outcomes. The Australian Government funds the Basin Plan, and the MDBA is accountable to the Minister for Water (governance arrangements are discussed in chapter 9).

Responsibility for water resource management in the Basin Plan is with the Basin states.

### Recent amendments to the Water Act and Basin Plan

It has been apparent for some time that the Basin Plan will not be implemented in full by 30 June 2024. The Australian Government publicly acknowledged this in July 2023 (Plibersek 2023a). And in late August, the Minister for Water announced ‘a new agreement of Murray–Darling Basin ministers to deliver the Basin Plan in full’ (DCCEEW 2023b). The Victorian Government was not party to the agreement.

The agreement:

* allows more time – until 31 December 2026 – for the delivery of existing supply and constraints projects (and northern Basin initiatives), and – until 31 December 2027 – for the 450 GL/y target (the last date contracts can be entered into)
* allows Basin states to bring forward *new* supply projects (provided they can be delivered by 31 December 2026)
* allows for a range of water recovery options – including voluntary water purchases – to be used to meet the 450 GL target
* aims to minimise the socio‑economic impacts on communities and will provide for community adjustment assistance for the impacts of water purchases toward the 450 GL for enhanced environmental outcomes.

The agreement requires amendments to the Water Actand the Basin Plan. The *Water Amendment (Restoring Our Rivers)* *Act* *2023* (the Act) was passed by Parliament in November 2023.

Among other things, the Act:

* extends the deadlines for meeting Basin Plan water recovery targets
* increases the range of measures that can be used to meet the 450 GL/y target and repeal the 1500 GL water purchase cap
* requires the Australian Government Minister for Water to regularly publish water recovery progress reports
* allows the Australian Government Minister for Water to withdraw supply projects
* ensures climate change is considered in the 2026 review of the Basin Plan
* better recognises the cultural knowledge and practices of First Nations people and ensure Basin water management takes into account matters relevant to First Nations people
* improves the transparency and integrity of water markets
* delays the Water Act review until 2027.

Figure 1.4 – Amended timeline for the Basin Plan

Amended timeline for the Basin Plan.
Resetting the balance to be completed 31 December 2026.
Supply projects, constraints easing projects and toolkit measures now to 2026. 
Efficiency projects now to 2027.
Review of the Plan in 2026 and review of the Water Act in 2027

## The Basin Plan – a significant reform

The Basin Plan is a significant, long‑term environmental reform (box 1.1). It has been described as world‑leading and as ‘one of Australia’s most ambitious and complex reforms’ (MDBA 2020c, p. viii). The Chair of the MDBA, for example, said:

All governments decided to act in the national interest. Together, we embarked on a bipartisan water reform journey not seen anywhere else in the world. The significance of that statement cannot be underestimated. (MDBA 2020c, p. iii)

And one expert told the MDBA’s annual River Reflections conference this year that the Basin Plan was a beacon for other nations on how integrated water management at the Basin scale can work.

I’m particularly impressed by the balance achieved between community and industry needs and the protection of water for the environment in Australia. That commitment is enviable … In the Colorado River Basin we desperately need a whole system model like the Murray–Darling Basin Plan. One that looks at the trade‑offs among end‑users and costs of environmental degradation with an eye to a more sustainable future for our grandchildren. (MDBA 2023g)

### Many support the Basin Plan

The ambition of the Basin Plan is shared by many people across Basin communities (box 1.2). The Basin Plan is now considered by many to be part of the landscape and central to securing a healthy and sustainable river system. For the most part, the conversation is no longer about whether or not there should be a Basin Plan, but rather how to deliver the Plan and its intended outcomes. In a recent address to the National Rural Press Club, the Chief Executive of the MDBA, said:

… everyone shares a passion for the health of our rivers and importantly, no‑one I have come across wants to do away with the Plan. Hand on heart, literally no‑one has said … ‘throw it out’. I struggle to think of anywhere else in the world where such an extraordinary political agreement has been achieved. (McConville 2022)

Several inquiry participants also argued that with climate change, delivering the Basin Plan is more important than ever.

| Box 1.2 – Support for the Basin Plan: what participants said … |
| --- |
| Department of Climate Change, Energy, the Environment and Water  In the face of an increasingly harsh climate and greater demand for water, delivering the Basin Plan in full is more important than ever. (sub. 77, p. 28)  Latji Latji Mumthelang First Peoples  We are fully behind the Basin Plan being delivered, including the provision for First Nations water, which is yet to be delivered properly. (sub. 78, p. 1)  NSW Government  The NSW Government agreed to implement the Basin Plan in 2014 and NSW supports implementation of the Basin Plan in full. (sub. 43, p. 1)  Murray River Group of Councils said it supports:  … the balanced implementation of the Murray Darling Basin Plan, to sustain the long‑term viability of our regional economy and the wellbeing of our communities and to deliver the environmental outcomes that will protect and preserve our region’s ecosystems. (sub. 22, p. 1)  Central Irrigation Trust  Collectively we must look for all opportunities to deliver the outcomes of the Plan without the irrigated agriculture sector being disproportionately impacted. It is imperative that all levels of Government look beyond the numbers in the plan, and work together to deliver the agreed outcomes in alternative and innovative ways. (sub. 33, p. 3) |
|  |

The Inspector‑General of Water Compliance undertakes a community sentiment survey which asks respondents questions about awareness of and support for the Basin Plan. The survey found that most survey participants were aware of the Basin Plan (but not the details) and of those who were aware of the Basin Plan’s details, around half were largely supportive of it (46% of community member respondents and 48% of water licence holders, sub. 75, p. 6).

More than 80 per cent of survey respondents who were aware of the details of the Basin Plan agreed that it was important for the survival of the Basin and its communities and 40% agreed that the Plan ensures water is available for future use (figure 1.5).However, a low proportion of participants felt positive about the management of water in the Basin – 6% of community member respondents, 8% of First Nations people and 19% of water licence holder respondents.

Figure 1.5 – Community perceptions of the Basin Plan

% who agree of those who were aware of details of the Plan

Community perceptions of the Basin Plan. 
Of those who were aware of details of the Plan:
85% agreed it was important for the survival of the Basin and its communities; 83% agreed it was important for the development and growth of communities in the Basin; 51% agreed it encourages more efficient use of water in the Basin; 40% agreed it ensures that water is available for future use; and 23% agreed it achieved an appropriate balance between economic, environmental and social needs in the Basin.


Source: IGWC (sub. 75, p. 6).

Many also commented on what the Basin Plan had achieved to date. The National Irrigators’ Council, for example, said:

The Plan has been a vital tool in balancing the needs of our communities, our environment and our productive sector. It hasn’t always got it right, but it has achieved a great deal since its inception. Ensuring balance is needed so we can keep our rivers and communities healthy and thriving.[[10]](#footnote-11)

But while there is support for the objectives of the Basin Plan, some participants observed that the focus is on volumes of water and less on the outcomes the Plan is trying to achieve. For example, the National Farmers’ Federation said:

… to achieve water recovery targets and meet supply and efficiency measures, a shift towards outcomes‑based targets rather than volume‑based targets is crucial. By focusing on outcomes, such as maintaining ecological health and supporting viable farming communities, we can ensure a more balanced approach that considers the social and economic impacts of water management decisions. (sub. 46, p. 2).

And some First Nations people participating in this inquiry said while continuing with the Basin Plan was vital, governments responsible for water management arrangements should do more to address the harm done to Country from lack of water. Other First Nations people said that they had not agreed to, and did not accept the Basin Plan (chapter 5).

## What we were asked to do and our approach

The Commission was asked to look at whether the Basin Plan was on track to be implemented on time, and where it was not on track, what needed to change. This included advising and recommending future actions and opportunities to simplify the framework of the Basin Plan to ensure efficient and effective achievement of its outcomes. The Commission was also asked to:

* assess the effectiveness of reforms to address previous Productivity Commission recommendations
* consider the impact of major droughts, floods, and the COVID‑19 pandemic on the effectiveness of implementing the Basin Plan and water resource plans
* provide practical advice on how the Basin Plan and water resource plans could better address the impacts of climate change and recognition of First Nations values and their ability to support environmental water management.

We assessed the individual elements of the Basin Plan (such as water resource plans and supply measures) as well as broader governance and institutional arrangements and looked at:

* whether the arrangements in place were likely to deliver the objectives of the Basin Plan and enable its impacts and outcomes to be evaluated
* whether actions to implement the Basin Plan were effective and efficient (box 1.3)
* how the actions of governments were tracking against the timeframes set out in the Basin Plan
* whether changes were needed to ensure effective and efficient implementation of the Basin Plan
* whether the right governance arrangements were in place.

| Box 1.3 – Efficiency and effectiveness |
| --- |
| Efficiency and effectiveness are terms used in both the Basin Plan and the terms of reference for this inquiry.  Economic efficiency and water efficiency  Economic efficiency refers to how well a society is making use of the resources available to it. Policies and programs can improve efficiency and the material wellbeing of the community.  In the context of water, an increase in technical efficiency refers to getting greater output from a given volume of water. ‘Efficiency measures’ in the Basin Plan aim to save water through improvements in water‑use efficiency, such as through investment in infrastructure.  Effectiveness  An effective policy is one that achieves what it was intended to achieve. For example, in the context of the Basin Plan, a ‘healthy working basin’ or ‘implementing SDLAM measures’.  A related concept is ‘cost effectiveness’, which can be useful where an outcome has been agreed, and the question is how to achieve the outcome at lowest cost. If an option is economically efficient, it must also be the most cost effective. But the converse is not always true – cost effective policies and programs need not be economically efficient. |
|  |

The Commission also considered how the operation of the Basin Plan could better adapt to a changing climate, recognise the values of First Nations people and incorporate the best available science.

We did not revisit questions that underpin the Plan, such as whether it is necessary to recover water for the environment, nor questions that other agencies have been (or will be) tasked and resourced to answer, such as how much water can sustainably be taken from the Basin.

There is a lot of other monitoring and reporting on the Basin Plan. The MDBA provides regular updates on progress of implementation of the Basin Plan and every five years it also undertakes a Basin Plan Evaluation (looking at what’s working, what’s not and where improvement is needed). Other recent reviews include an assessment of the social and economic conditions in the Basin, work by the Inspector‑General of Water Compliance and the Australian Competition and Consumer Commission, the South Australian Murray–Darling Basin Royal Commission and independent assessments of the fish deaths in the lower Darling.

There will be a full review of the Basin Plan in 2026 and a review of the Water Act in 2027.

### A community‑wide perspective

The Commission adopted a community‑wide perspective to assessing the implementation of the Basin Plan (a requirement under the *Productivity Commission Act 1998* (Cth)). This involved taking into account the costs of the Basin Plan in light of the benefits and the impacts on the lives of people, regions and industries affected by the Plan and Australians more generally.

This approach is consistent with the Basin Plan. A healthy, working Basin requires long‑term sustainable management of water and other resources to underpin the range of community uses and values. Resetting the balance requires considering the environmental benefits across the Basin and the socioeconomic impacts on industries and regional communities of a permanent reduction in water available for irrigation.

The Australian Government has committed at least $13 billion to implement the Basin Plan (more funds have been committed, but the amount is not public). The basis for spending this amount of taxpayers’ money on implementing the Plan, like that of any public spending, is that the benefits exceed the costs across the economy. Basin communities and the wider community also want assurance that value for money has been achieved in the pursuit of environmental outcomes and sustainable consumptive uses of water. Critical to the community’s trust and confidence in the Basin Plan are the governance arrangements holding Basin governments to account for implementation, expenditure and outcomes. The Inspector‑General for Water Compliance, noting the importance for the wider community of linking government expenditure to outcomes, said:

Underpinning the management of Basin water resources is the money spent on, or committed to, achieving Basin Plan outcomes. If the public cannot see for themselves where the money for Basin reform has gone, and what outcomes have been achieved, trust in the management of Basin water resources will erode. (sub. 75, p. 7)

Basin governments also need to demonstrate that the funds spent on the Basin Plan are dollars well spent from tax revenues for which there are many competing uses.

### Principles of good governance

To assess whether the right governance arrangements are in place, we looked at how well the institutional and governance arrangements aligned with principles for good governance. The principles include:

* **clarity around roles and responsibilities**, with responsibility given to institutions that can best achieve the outcomes. Each institution’s purpose and objective should be clear, and they should have the powers, functions and capability to fulfil their responsibility
* **management of conflicting functions**, for example, separating regulatory, service delivery and policy‑making into separate institutions
* **transparent decision making and clear accountability for decisions and actions**; the costs and benefits of decisions should also be clearly articulated and there should be an effective framework for monitoring, reporting and assessing implementation
* **effective processes for collaboration on implementation**, with all parties having a genuine commitment to shared goals and co‑operative working arrangements (as a joint responsibility of Basin governments, the Basin Plan requires collaboration to implement it). Arrangements for collaboration should be clearly documented, while shared risks should be identified and managed, and potential overlaps and gaps should be identified and addressed
* **effective processes for meaningful community engagement**, including giving parties genuine opportunities to influence decisions, providing parties the information, analysis and time to support their deliberations so they can meaningfully contribute, and communicating decisions to parties in an open, transparent and accessible way.

## How we engaged

We engaged widely on this inquiry, including with Australian Government agencies, state and territory and local governments, individuals and organisations, including Aboriginal and Torres Strait Islander people and organisations.

* In May 2023, the Commission released a Call for Submissions paper with key questions on the various components of the Basin Plan. We received 103 submissions and 19 brief comments in response to the Call for Submissions paper.
* We held public forums in 17 locations across the Basin from June to August 2023 (figure 1.6). 330 people attended these forums.
* In October 2023, the Commission released an interim report with interim recommendations and information requests. We received 42 submissions and 6 brief comments in response to the interim report.
* A stakeholder working group (in accordance with the requirements of the Water Act) was established to provide a forum for the exchange of information and views on issues relevant to the inquiry.
* In November 2023, the Commission held a roundtable with First Nations participants.

Details of the individuals and organisations who participated in this inquiry are provided in appendix A. Appendix B reports what we heard at the public forums. First Nations participants’ comments made at the roundtable are in chapter 5.

Our assessment was also informed by detailed responses to information requests submitted to Australian and state and territory government departments and agencies with responsibility for implementing the Basin Plan. Responses to the information requests are published as attachments to their respective submissions to this inquiry (except where the material was provided to the Commission on a confidential basis). The Commission is grateful for the assistance received from these agencies throughout the inquiry, which included providing data and helpful responses to questions about existing arrangements.

The Commission is mindful of the heavy engagement burden experienced by many in the community. The Commission thanks all inquiry participants for meeting with Commissioners and staff, making submissions, attending public forums and the roundtable, and providing information to inform the inquiry.

Figure 1.6 – The Commission’s public forums

June to August 2023

This figure shows the locations of the Commission’s public forums held from June to August 2023. They were held in St George, Goondiwindi, Moree, Dirranbandi, Bourke, Warren, Dubbo, Menindee, Renmark, Mildura, Goolwa, Hay, Griffith, Leeton, Deniliquin, Echuca and Shepparton.

## Structure of the report

The rest of this report is set out as follows:

* chapter 2 – resetting the balance
* chapter 3 – environmental water planning and management
* chapter 4 – water resource plans
* chapter 5 – the values of First Nations people
* chapter 6 – bringing new knowledge into the Basin Plan framework
* chapter 7 – water quality and critical human water needs
* chapter 8 – water trading rules
* chapter 9 – governance and engagement.

Appendix A outlines the engagement processes undertaken for this inquiry and appendix B sets out what we heard when we engaged with communities across the Basin.

# Resetting the balance

|  |  |
| --- | --- |
| Key points | |
|  | Resetting the balance of water uses in the Basin is core to implementing the Basin Plan and delivering its outcomes. It requires governments to implement, in full, water recovery, the sustainable diversion limit (SDL) adjustment mechanism, constraints‑easing projects, and the northern Basin toolkit. |
|  | For most elements of resetting the balance, inadequate progress has been made since 2018 to meet the 2024 deadline. Limited progress has been made on most constraints‑easing projects, and some supply projects are no longer viable. The program to recover an additional 450 GL/y remains well short of its target.  Southern Basin states have not delivered projects as agreed, and the Australian Government has not held them to account. Over time, Basin governments have also progressively reduced the scope of water recovery options available, and given greater priority to slower and more expensive forms of water recovery.  Delays in resetting the balance mean the Basin Plan will be more expensive to complete, limiting the environmental outcomes that can be achieved with the allocated funds. The failure of Basin governments to deliver imposes costs on the environment, Basin communities, and the broader Australian community. |
|  | Recent amendments to the Basin Plan and *Water Act 2007* (Cth) provide necessary additional time for supply measures, constraints‑easing and the 450 GL/y. New supply measures can now be proposed, and the 450 GL/y – which the Minister must now ‘take all reasonable steps’ to deliver – can now be met through voluntary purchases. |
|  | Whether these amendments are enough to finalise resetting the balance, in full, remains to be seen. Victoria has not agreed to the proposed pathway, and the risk of a shortfall against the 605 GL/y supply measure offset remains high.  Low water market liquidity means that finalising both the 450 GL/y and any shortfall on the 605 GL/y by 2027 may contribute to significant disruption for both market participants and Basin communities. The Australian Government’s renewed approach to water recovery should ensure voluntary purchases are staged gradually over time. It must meet its commitment to fund community adjustment assistance where warranted.  Additional reporting required under amendments to the Water Act will rightly put greater scrutiny on Australian Government decision making. These reports should also clarify the status of project funding arrangements. |
|  | Constraints‑easing projects remain important to environmental improvement, beyond their potential water recovery offset. Easing constraints requires renewed focus, separate to the supply measure package, and substantially more time. |

The Basin Plan resets the balance between water for the environment and water for other uses: towns, households, irrigation and other industries. This balance is established through sustainable diversion limits (SDLs) on water take. Moving to the SDLs requires governments to recover water access rights from consumptive users and make them available for environmental use.

This chapter assesses how effectively governments have rebalanced water use in the Basin since December 2018, and makes recommendations to progress the outcomes of the Plan.

## Resetting the balance is core to Basin Plan implementation …

### What needs to be done to reset the balance?

Resetting the balance has three interconnected components.

1. **‘Bridging the Gap’** byrecovering water entitlements for environmental use to meet the SDL in each valley. Water recovery can include voluntary water purchases and water‑use efficiency programs.
2. The **SDL adjustment mechanism** in the southern Basin. It comprises of:
   1. **Supply measures**: works, measures and rule changes that deliver ‘environmentally equivalent’ outcomes to environmental water recovery, with less water.
   2. **Efficiency measures**: 450 gigalitres (GL) a year[[11]](#footnote-12) of additional water recovery through projects that improve water‑use efficiency with neutral or improved socioeconomic outcomes.
   3. **Constraints‑easing measures**: Projects to ease river operating constraints in the Basin; constraints may be physical (such as flood‑prone infrastructure) or operational (river management rules designed to minimise flooding). Most constraints projects are also notified as supply measures.[[12]](#footnote-13)
3. **The northern Basin toolkit**: a $180 million package of six measures, including constraints‑easing, environmental water protection and complementary measures, that aim to improve the ecological health of the northern Basin.

Further detail on each of these components is provided in box 2.1.

| Box 2.1 – Components of resetting the balance |
| --- |
| Bridging the gap to the sustainable diversion limits (SDLs)  ‘Bridging the Gap’ refers to programs that reallocate water rights from consumptive uses (including towns, households and industry) to the environment. These targets are defined as the difference between the baseline diversion limits (BDLs; set at 2009 levels of development) and the SDLs defined in the Basin Plan. The 2012 Basin wide surface water target was 2,750 GL/y (in long‑term annual average terms). This is a reduction of about 20% from the overall BDL (MDBA 2023d).  Bridging the Gap has included programs to directly purchase water entitlements through open and limited tenders, infrastructure projects, and other state‑led programs. Recovered water entitlements are managed by the Commonwealth Environmental Water Holder to achieve environmental outcomes.  SDL Adjustment Mechanism: Supply measures  Supply measures refer to a range of works, measures and rule changes that seek to provide equivalent environmental outcomes to water recovery. These allow SDLs to be increased and water recovery targets to be reduced or offset. Some projects aim to provide localised environmental benefits, while others are more complex and have system‑wide impacts.  A package of 36 supply measures was agreed to by Basin state governments. In 2017, the Murray–Darling Basin Authority (MDBA) modelled the environmental equivalence of the package, and assessed that it could offset 605 GL/y of water recovery in the southern Basin. The Basin Plan was amended to reflect this lower water recovery target, subject to the MDBA conducting a ‘reconciliation’ process that compares the modelled water savings of all completed projects against the original modelling.  SDL Adjustment Mechanism: Constraints‑easing measures  Constraints refer to rules limiting the flow rates of regulated rivers to protect infrastructure and avoid flooding of private land. Constraints‑easing measures are projects that aim to raise those allowable flow rates, so rivers can reconnect with floodplains more often. Five constraints projects are notified as supply measures (and contribute to the water recovery offset), and one is part of the northern Basin toolkit.  SDL Adjustment Mechanism: Efficiency measures  Efficiency measures are a water recovery program that aims to recover an additional 450 GL/y with ‘neutral or improved socioeconomic outcomes’. These allow SDLs to be reduced alongside improved water‑use efficiency for consumptive users. Under the Plan, neutral or improved socioeconomic outcomes are met when an individual voluntarily participates in a water efficiency project (s. 7.17). The Ministerial Council later agreed to a set of 13 additional criteria to assess the socioeconomic impacts of these projects, including that projects do not negatively impact on social and environmental outcomes. The 450 GL/y is intended to pursue the ‘enhanced’ environmental outcomes defined in schedule 5 of the Basin Plan. One of these outcomes explicitly relies on easing constraints.  The northern Basin toolkit  The 2016 Northern Basin Review recommended a 70 GL/y reduction in water recovery targets for the northern Basin, provided the Australian, Queensland and New South Wales governments committed to implementing six ‘toolkit measures’ designed to improve water management (MDBA 2016a, p. 2). These measures included a suite of works projects, constraints‑easing measures and improved environmental water management. The Plan was amended in 2018 to reflect this water recovery reduction. |
|  |

The Basin Plan SDLs led to a Basin‑wide surface water environmental water recovery target of 2,750 GL/y, and a 38.45 GL/y groundwater target. These targets are made up of catchment‑specific local targets and shared targets for connected surface water systems. The surface water targets were altered in 2018 by the SDL Adjustment Mechanism and Northern Basin Review, resulting in a new Bridging the Gap target of 2,075 GL/y (assuming the full 605 GL/y offset under the SDL Adjustment Mechanism; figure 2.1).

Figure 2.1 – Basin‑Wide Surface water recovery and SDL adjustment targets

This figure presents the different components of the 3,200 gigalitres per year of Basin-wide surface water recovery. This includes the original Bridging the Gap target of 2,750 Gigalitres per year, which is now reduced to 2,075 gigalitres per year. The rest of the 3,200 gigalitres is comprised of 605 gigalitres per year of offsets from supply measures, a 70 gigalitre per year reduction due to the Northern Basin Toolkit, and 450 gigalitres per year from efficiency measures. 

**a.** Bridging the Gap relies on 2,075 GL/y of surface water recovery and the supply measure offset.

Note: All volumes are reported in long‑term average annual yield. These targets are affected by the 5% limits of change in the SDL adjustment mechanism (Basin Plan, s. 7.19), which is 543 GL/y. A 605 GL/y supply measure offset requires 62 GL/y of efficiency measures to be recovered; otherwise, the overall offset is reduced to avoid breaching the 5% limit, and the Bridging the Gap target is increased.

Source: DCCEEW (2023i).

The Australian Government is primarily responsible for resetting the balance[[13]](#footnote-14) and administers water recovery programs to both bridge the gap and deliver the additional 450 GL/y. The Australian Government committed $5.95 billion to recover 2,750 GL/y under ‘Bridging the Gap’ and $1.21 billion for supply measures. $1.775 billion is committed to efficiency measures and constraints‑easing projects through the Water for the Environment Special Account (WESA) (DCCEEW, sub. 77, response to information request, p. 6; table 2.1).

Basin states are primarily responsible for delivering the supply and constraints‑easing measures, funded by the Australian Government and overseen by a subcommittee of the Basin Officials Committee (BOC). The locations of constraints‑easing projects across the southern Basin are shown in figure 2.2. The New South Wales and Queensland governments are responsible for delivering works under the northern Basin toolkit measures, while the Australian Government is responsible for some measures, and other measures are delivered jointly by the three governments.

Under the 2012 Basin Plan, all supply, constraints‑easing and efficiency measures were to be notified to the MDBA by 31 December 2023, and all elements of resetting the balance were to be completed by 1 July 2024. Under the 2013 *Intergovernmental Agreement on Implementing Water Reform in the Murray Darling Basin* (2013 IGA), the northern Basin toolkit was also due to be completed by 30 June 2024.

Table 2.1 – Funding for resetting the balance as of 31 May 2023

|  | Committed ($m, nominal) | Spent (incl. contracted) ($m, nominal) | Remaining ($m, nominal) |
| --- | --- | --- | --- |
| Bridging the Gap – Purchase | 2,832 | 2,832 | ‑ |
| Bridging the Gap – Infrastructure | 3,120 | 2,978 | 142 |
| Supply measures (605 GL/y offset) | 1,212 | 485 | 727 |
| Efficiency measures (450 GL/y) | 1,575 | 384 | 1,191 |
| Constraints‑easing | 200 | 128 | 72 |
| Northern Basin toolkit | 180 | 144 | 36 |
| Total | **9,119** | **6,951** | **2,168** |

Note: Data covers the period 2007 to 2023.

Source: DCCEEW, sub. 77, response to information request, pp. 6–7.

Figure 2.2 – Map of southern Basin constraints‑easing measures and estimated costs

**Figure 2.2 shows the locations of constraints easing projects across the southern Basin, and their projected status’ by June 2024. It also states their expected costs, and whether they were nominated as part of the supply measure package. 
River Murray in South Australia constraints easing measure is likely to be operable by June 2024, and is expected to cost between 38 to 55 million dollars. The River Murray in South Australia constraints easing project was nominated as a supply measure.
The Lower Darling constraints easing measure, which was nominated as part of the Menindee lakes supply measure, will not be operable by June 2024 and costs were not published. 
The Murrumbidgee constraints easing measure will not be operable by June 2024 and is expected to cost between 113 to 164 million dollars. The Murrumbidgee constraints easing project was nominated as a supply measure.
The Hume to Yarrawonga constraints easing measure will not be operable and is expected to cost between 26 to 34 million dollars. The Hume to Yarrawonga constraints easing project was nominated as a supply measure.
The Yarrawonga to Wakool Junction constraints easing measure will not be operable by 2024, and is expected to cost between 262 to 306 million dollars. The Yarrawonga to wakool Junction constraints easing project was nominated as a supply measure. 
The Goulburn constraints easing measure will not be operable and is expected to cost 71 million dollars. The Goulburn constraints easing project was nominated as a constraints easing project only.
**

**a.** Lower Darling nominated as part of Menindee Lakes Project.

Note: Cost estimate for River Murray in SA project released as part of Senate Motion No. 685 for production of documents (22 March 2018), p. 662 (p. 5 of document 68).

Sources: (DPI (NSW) 2016; MDBA 2023o, 2023a, p. 15; NSW DPIE 2016; Victorian DELWP 2016b, 2016a).

On 22 August 2023, the Australian Government announced an agreement with all Basin states (except Victoria) to extend timeframes for the supply measures, northern Basin toolkit measures and a package of ‘no regrets’ constraints projects to 31 December 2026, and the 450 GL/y program to 31 December 2027 (DCCEEW 2023b). The Australian Government will also allow Basin states to propose new supply measure projects until July 2025.

On 30 November 2023, both houses of the Australian Parliament passed the *Water Amendment (Restoring Our Rivers) Act 2023* (Cth), which amends the *Water Act 2007* (Cth) and Basin Plan to give effect to parts of the August 2023 agreement, including additional time to deliver projects. The amendments also require the Australian Government Minister for Water to take ‘all reasonable steps’ to recover the additional 450 GL/y, and place reporting obligations on the Australian Government.

## … but progress has been limited

### Some progress since 2018

Since the Productivity Commission’s 2018 review of the Basin Plan, some elements of resetting the balance have progressed, but substantial gaps remain (figure 2.3). The Commission assessed progress towards the Basin Plan deadlines as they stood prior to the November passage of the Restoring Our Rivers Bill; the implications of the Bill are discussed in section 2.4.

Figure 2.3 – Surface water recovery and SDL adjustment mechanism progress, June 2023a

Surface water recovery and SDL adjustment mechanism progress, June 2023.
This figure shows progress in surface water recovery, as well as SDL adjustment mechanism progress, as at June 2023. 
Of the 2,075 gigalitres per year of ‘Bridging the Gap’, 2,029 gigalitres per year have been recovered with 46 Gigalitres per year remaining. 
Of the 650 gigalitres per year target from the SDL adjustment mechanism offset, 290 gigalitres per year has currently been offset, with a potential 315 gigalitre per year shortfall. 
Of the target of 450 gigalitres per year from efficiency measures, 26 gigalitres per year has been recovered, with 424 gigalitres per year remaining. 
There was also a 70 gigalitre per year reduction from the Northern Basin toolkit. 
All gigalitre per year recovery amounts are expressed as Long-Term average annual yields. 

**a.** Figure does not include nominal over‑recovery; full volume recovered under Bridging the Gap volume is reported at 2,107 GL/y. Shaded cells indicate target not yet achieved. Includes water under contract to be delivered. **b.** Based on MDBA estimate of maximum supply measure shortfall.

Sources: (DCCEEW 2023i; MDBA 2023m).

#### Incremental progress towards supply and constraints‑easing measures

Of the 36 notified supply measures, an additional five measures (representing a water recovery offset of approximately 60‑90 GL/y (MDBA 2020b, p. 28)) are now operational.[[14]](#footnote-15) The 14 operational supply measures (table 2.2, figure 2.4) are delivering about half of the 605 GL/y offset (MDBA 2023n). A further five measures, representing an offset of approximately 74 GL/y, are likely to be operational by mid‑2024.

Table 2.2 – Status of southern Basin supply and constraints projects

Progress as of July 2023

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Supply projects  (excl. constraints)** | | **Southern Basin constraints‑easing projects** | | **Combined** | |
|  | **Number of projects** | **Indicative expected offset (GL/y)** | **Number of projects** | **Indicative expected offset (GL/y)** | **Number of projects** | **Indicative expected offset (GL/y)** |
| **Operational** | 14 | 278.1 | 0 | 0 | **14** | **278.1** |
| **Likely to be operational by 2024** | 5 | 73.7 | 1 | 20.6 | **6** | **94.3** |
| **Unlikely to be operational by 2024** | 7 | 40.6 | 0 | 0 | **7** | **40.6** |
| **Will not be operational by 2024** | 5 | 130.6 | 5 | 61.8 | **10** | **192.4** |
| **Total** | **31** | **523** | **6** | **82.4** | **37** | **605.4** |

Sources: Commission estimates based on Indec (2021b, pp. 30–66) and MDBA (2023m, pp. 38–41).   
Note: Total includes the New Goulburn constraints measure, which was not nominated as a supply measure. Menindee Lakes Project counted as both a supply and constraint project as it includes Lower Darling constraints key focus area. Total excludes Improved Regulation of the River Murray supply measure (not progressed).  
Indicative expected offsets are based on Indec estimates of individual project offset volumes, allocated based on the MDBA’s 2023 update of project progress. The actual modelled offset will depend on interactions between the actual measures that are in place at time of reconciliation.

**Figure 2.4 – Status of supply and constraints projects by state**

Progress as of July 2023

This figure shows the status of supply and constraints projects in South Australia, New South Wales and Victoria, as well as shared projects, as assessed by the MDBA in 2023.
In South Australia, four projects are operational and one is likely to be operational by June 2024. 
In NSW, one project is operational, with three likely to be completed by June 2024. Two projects are unlikely to be completed by June 2024, and four projects will not be operational by that time. 
In Victoria, five projects are unlikely to be operational, and a further five will not be operational by June 2024. 
Of the shared projects, nine are now operational. A further two projects are likely to be operational, and one will not be operational by June 2024.

Source: MDBA (2023m, pp. 38–41).

However, other supply measure projects have not progressed at the rate needed to meet the original deadline. The MDBA stated that some key projects, including the Menindee Lakes project, are ‘not viable’ and cannot be implemented as notified, even with more time (MDBA 2023c, p. 5). However, the MDBA also reported that no projects have yet been formally withdrawn.

Constraints‑easing measures have also progressed slowly across the southern Basin and an independent review of the overall supply measure program noted the risk in constraint project timelines. MDBA advice, provided to the Australian Minster for Water in July 2023, also stated that four of the five southern Basin constraints projects will not be operable by 2024 (Indec 2021a; MDBA 2023c, p. 4). The MDBA estimated in 2022 that several constraints measures were at least 5‑10 years away from delivering outcomes (MDBA 2022n, p. 2).

Basin governments have also adjusted their constraints programs.

* The New South Wales Government has rescoped the Menindee Lakes and the Yanco Creek supply projects into the Better Baaka and Better Bidgee projects, respectively, and repackaged the three constraints projects into the Reconnecting River Country program (NSW Government, sub. 43, p. 5). However, these changes have not been formally notified to the MDBA as amendments to the notified package of supply measures.
* The Victorian Government has reset the implementation of the Victorian Constraints Measures Program, with the new Goulburn constraints measure operating in a ‘consultative manner to ensure community input based on solid technical information’ (Goulburn‑Broken CMA, in Victorian Government, sub. 74, p. 23).

Had reconciliation taken place in early 2024, there would have been a substantial shortfall in the supply measure offset. The MDBA estimated the shortfall at 190‑315 GL/y, with the outcome likely to be at the high end of this range (MDBA 2023m). The extension of timeframes under the Restoring Our Rivers Act means reconciliation will now occur in late 2026.

#### Bridging the Gap to 2,075 GL/y is nearly complete

46 GL/y of surface water remains to be recovered (as of 18 September 2023) (DCCEEW 2023i). This is about 2% of the 2,075 GL/y target under Bridging the Gap – although this outcome does not account for the potential supply measure shortfall, which would re‑open an obligation for the Australian Government to bridge the gap in the southern Basin.[[15]](#footnote-16) A 190‑315 GL/y shortfall would be equivalent to an additional 9%–15% over the existing 2,075 GL/y target.

Very little progress has been made on finalising the surface water component of Bridging the Gap since the 2018 assessment (figure 2.5). Prior to March 2022, the Australian Government had prioritised limited tender strategic purchases, with two such purchases made since 2018 to recover 4.6 GL/y in the Murrumbidgee and Lower Darling (DCCEEW 2023h).

Figure 2.5 – Total gap‑bridging water recovery by method

This figure shows progress in recovering water from 2007 to 2023. Most water purchasing took place prior to 2013. About two thirds of overall water recovery has occurred by purchase, with the remainder through infrastructure projects. 
In 2018, the Bridging the Gap target was reduced from 2,750 gigalitres a year to 2,075 gigalitres a year. Very little progress has occurred since 2018, and the target is not yet met.

Source: DCCEEW, sub. 77, attachment 2.  
Note: All volumes are reported in long‑term average annual yield. In 2018, the Basin Plan was amended to reduce the water recovery target following the operation of the SDL adjustment mechanism and the Northern Basin Review.

As of September 2023, the remaining surface water gap is larger than was reported in 2018. This is because of changes to ‘cap factors’, as part of the NSW water resource planning process, which led to a 39.7 GL/y reduction in the NSW Murray recovery volume (DCCEEW, sub. 77, response to information request, p. 15). A water recovery target also re‑emerged in the ACT in 2019 because previously‑recovered entitlements were considered ‘invalid’ due to their location (ACT Government, sub. 85, response to information request, p. 7).

On 23 March 2023, the Australian Government commenced an open market tender to purchase water entitlements in the surface and groundwater systems with an outstanding gap, excluding the ACT (DCCEEW 2023f). The tender is being undertaken subject to the 2023 Strategic Water Purchasing Framework (DCCEEW 2023g). On 31 October 2023, the Australian Government Minister for Water announced that 250 responses to the tender had been received, offering more than double the required water, and that the Government had commenced making offers (Plibersek 2023c).

In the ACT, the Australian Government is negotiating directly with the ACT Government to recover 4.9 GL/y (DCCEEW 2023d, ACT Government, sub. 85, response to information request p. 7). This is because a significant share of ACT water entitlements is owned by the urban water provider and, in the ACT Government’s view, the ‘conditions of the water efficiency program were not conducive to urban water projects’, necessitating a direct negotiation with the Australian Government.

For groundwater, tender processes undertaken between 2015 and 2017 recovered 2.7 GL/y of the 38.45 GL/y groundwater target. More recent tenders undertaken by the Australian Government during 2018‑19 recovered a further 32.1 GL/y. This progress – coupled with the Queensland Government undertaking 0.5 GL/y of compulsory groundwater licence reductions in 2019‑20 – has delivered an additional 32.6 GL/y toward the target (DCCEEW, sub. 77, attachment 2). 3.2 GL/y of groundwater, located in the Queensland Upper Condamine Alluvium, remains to be recovered (DCCEEW 2023e).

#### Very little progress made on the 450 GL/y

Little has been achieved toward the 450 GL/y efficiency measures target. At the end of September 2023, just 12.2 GL/y was registered to the Commonwealth Environmental Water Holder (CEWH) and another 13.8 GL/y was under contract (DCCEEW 2023i). The two statutory reviews of the WESA confirmed that the 450 GL/y would not be delivered within existing budgets or timeframes (WESA Review 2020, 2021). The second review in 2021 anticipated that only 60 GL/y could be recovered by 2024 because of the lack of support from Basin state governments and limitations in the design of the Off‑Farm Efficiency Program (OFEP) (WESA Review 2021, p. 27).

Most of the funding available under the OFEP is for State‑led projects, with projects currently being implemented across five irrigation infrastructure networks expected to deliver 23.4 GL/y towards the target (DCCEEW 2023d).

#### Some steps towards implementing the northern Basin toolkit measures

Progress across the northern Basin toolkit package is mixed. After seven years, there are improvements to the coordination of environmental water and event‑based watering mechanisms (NBPC 2023). Finalising other elements relies on accreditation of NSW water resource plans (discussed in chapter 4) and completion of Bridging the Gap water recovery in the northern Basin under the ongoing tender process.

However, project implementation is still at a very early stage for the Gwydir constraints project and environmental works measures (table 2.3). Four environmental works projects have since been approved for an ‘accelerated gateway model’, with the Australian Government assigning $90 million of the $180 million committed towards these projects to speed up implementation (MDBA 2023i). This model is designed to undertake both the pre‑construction and construction stages ‘concurrently’ to enable implementation by 30 June 2024 (DCCEEW, sub. 77, response to information request, p. 21).

Table 2.3 – Works projects in the northern Basin toolkit

| Project | State | Status | On track for 2024? | Accelerated funding? |
| --- | --- | --- | --- | --- |
| **Projects addressing system constraints in the Gwydir catchment** | | | | |
| Gingham Watercourse | NSW | Business case completed | No | No |
| Lower Gwydir Watercourse | NSW | Business case completed | No | No |
| Lower Mehi River | NSW | Business case complete | No | No |
| Environmental works projects to promote fish movement and habitat including fishway construction | | | | |
| Fish for the Future: Reconnecting the Northern Basin project | NSW | Implementation partially underway | Partially | Yes |
| Scoping Initiative: Macquarie Marshes enhanced watering project | NSW | Implementation partially underway | Partially | Yes |
| Fish for the Future: Fish‑friendly Water Extraction project | NSW | Implementation partially underway | Yes | Yes |
| Fish‑friendly Water Extraction: Condamine‑Balonne and Border Rivers project | QLD | Gateway assessment underway, installation underway | Yes | Yes |
| Enhance the Flexibility and Capability for Distributing and Managing Low Flows through the Lower Balonne River System Bifurcation Weirs project | QLD | Business case submitted for assessment | No | No |
| Reconnecting Catchments: Condamine‑Balonne project (Jack Taylor and Beardmore dams) | QLD | Business case submitted for assessment | No | No |
| Improving Within‑Catchment Fish Resilience – Lower Balonne project (Culgoa) | QLD | Business case submitted for assessment | No | No |

Sources: MDBA (2023k), NBPC (2023).

#### Limited action, despite earlier warnings and recommendations

The Commission’s 2018 assessment of Basin Plan implementation highlighted that changes were necessary to avoid the significant risk that supply and constraints‑easing measures would not be implemented as proposed. Because there was no credible process to rescope or abandon measures that could not be delivered, or where the anticipated net benefits of measures had significantly declined, we recommended the Australian Government change its processes for reviewing and funding supply measures, and consider extending deadlines (PC 2018, pp. 135–141). The intent was to give worthwhile measures the best chance of success, and reduce the costs of resetting the balance by avoiding water recovery in cases where supply measures were more cost‑effective than purchasing water (PC 2018, p. 139).

We also drew attention to the escalating cost of the 450 GL/y efficiency measures program and the need to re‑assess the parameters of that program, as well as recommending improved oversight of the northern Basin toolkit measures.

Basin governments accepted most of the recommendations at the time, with only one rejected outright. Other recommendations, including the recommendation to extend deadlines, were marked as requiring further consideration (Joint Basin Governments 2019). Governments agreed that the delivery of some supply and constraints projects by 2024 would be ‘challenging’, with deadlines to be revisited on a case‑by‑case basis (Joint Basin Governments 2019, pp. 22–23).

Limited apparent progress was made on key elements of the Commission’s advice for resetting the balance. In particular, the opaque operation of the ‘gateway’ process for funding the supply, constraints and toolkit measures remains a concern: the recommended gateway was intended to ensure the Australian Government carefully assessed supply projects for their feasibility and cost‑effectiveness and, if states failed to make reasonable progress through the design phase, projects could be removed.

We were also explicit that the requirement to ‘make good’ if a project failed – that is, the obligation to recover water to make up the shortfall – should remain in place.

However, some projects have remained in limbo, even though the MDBA has explicitly stated that they are not viable as notified (MDBA 2023c, p. 5). The process under the Basin Plan to amend or withdraw a measure has not been used – despite the existing requirement to amend notifications ‘as soon as practicable’ once the details of a project have changed[[16]](#footnote-17) – and there is no clarity on the consequences of removing a project from the package. The MDBA has also not published any updated modelling of the expected environmental outcomes of 450 GL/y of additional environmental water with the notified supply measure package or other changes to River Murray operating conditions since 2012.

In 2018, oversight of the toolkit was to be undertaken by the Northern Basin Commissioner, with that function transferred to the Interim Inspector‑General of Murray–Darling Basin Water Resources (BOC 2023a, p. 7). The Inspector‑General of Water Compliance (IGWC), established in 2021, was intended to ‘replace, and assume the independent assurance functions of’ the interim Inspector‑General.[[17]](#footnote-18) This indicates that independent assurance of the northern Basin toolkit would have also transferred to the IGWC. However, the IGWC has not undertaken any dedicated reporting on the northern Basin toolkit (IGWC, pers. comm, 31 July 2023).

#### Delays will increase costs and reduce the benefits of delivering the Basin Plan

It has been apparent for some time that resetting the balance would not be complete by 30 June 2024. Although the nominal gap‑bridging target (2,075 GL/y) is largely on track to being achieved by 2024, the expected supply measure shortfall means the SDLs will not be in effect, as envisioned, by that time.[[18]](#footnote-19) Following the August 2023 agreement, the Australian Parliament has amended the Basin Plan and Water Act to extend deadlines to 2026 for supply and toolkit measures, and to 2027 for the additional 450 GL/y. (Section 2.4 discusses these amendments in more detail.)

The failure of all Basin governments to achieve water recovery targets by the original deadlines, across most elements of resetting the balance, means the cost of delivering the Basin Plan will be considerably higher than first estimated. There have been significant increases in water entitlement prices and construction costs over the last fifteen years: construction costs have doubled in nominal terms (figure 2.6), while in 2022‑23, an index of southern Basin water entitlement prices sat at about three times its 2012 value (Aither 2023a, p. 10). Taxpayers will bear the costs of delivering Basin Plan targets in this higher‑cost environment.

Figure 2.6 – Construction cost price index, 2007 to 2022a

This figure plots the Annualised construction cost index over time, as a percentage change since 2007. This cost index grew by around 10 percent by 2010. It then grew to over 20% by 2013, where it roughly stayed at until 2016. After this, it increased steeply to around 40% by 2019, and rose to around 55% by 2022. 

**a.** ABS quarterly Producer Price Index for ‘Other heavy and civil engineering construction Australia’, converted to annual average.

Source: ABS 6427.0 Producer Price Indexes, Australia, June 2023.

The second WESA review put the cost of recovering the full 450 GL/y, within current legislative constraints, at between $3.4 and $10.8 billion (WESA Review 2021, p. 31). It also confirmed a likely funding deficit across the available funding sources for supply and constraints‑easing projects (WESA Review 2021, p. 39). As the South Australian Murray Irrigators put it:

Kicking the can down the road and not addressing the core issues has led to … a more expensive exercise than it otherwise would have been if the issue had been confronted and funded head on. This is not the fault of the public, or the well‑intended taxpayer. This is the fault of governments and bureaucracies trying to generate political mileage and avoid expensive responsibilities. (sub. 96, p. 8)

Delays in meeting water recovery targets in full means that there has been less water available to deliver Basin environmental outcomes in the meantime. Slow progress on constraints‑easing has also limited the benefits of the existing held environmental water portfolio. While there is not enough evidence to conclude whether Basin environmental outcomes are measurably poorer because of the delays in meeting these targets, a new Sustainable Rivers Audit, currently being planned by the MDBA (sub. 126, p. 2), should help answer this question.

## Why has implementation slowed?

### Basin governments’ policies have delayed water recovery projects …

Slow progress recovering water entitlements, under both Bridging the Gap and the 450 GL/y, reflects policy decisions – including stricter criteria on ways to recover the 450 GL/y – as well as changes in Basin water markets that have increased the cost and complexity of water recovery programs.

Over time, the Australian Government has progressively reduced the scope of water recovery options available and given greater priority to slower and more expensive forms of water recovery. Many of these changes were made in response to community concerns about water recovery and its perceived effects on some regional communities. Goulburn‑Murray Water, for example, said:

Many of the wider communities experienced adverse socioeconomic impacts where water was bought. Economic activity reduced, there were less jobs, outward migration, reduced access to services and, ultimately, a fraying of the social fabric of these communities. Recognising this failing, governments responded by limiting the total volume of water that could be bought-back, and introduced strengthened socioeconomic tests, including for on-farm investment in return for transfer of water to the funder. (sub. 74, p. 9)

Shortcomings in how Basin governments have engaged with communities during Plan implementation have also contributed to community opposition. Effective engagement, which ensures community members feel heard and can see how their input has been taken into account by decision‑makers, can help reduce community frustration (chapter 9).

#### Australian Government policy on Bridging the Gap

For Bridging the Gap, the Australian Government made a number of policy changes.

* In 2013, while committing to Bridge the Gap, the Australian Government also stated its intent that ‘no water entitlements will be eroded or compulsorily acquired’ under the Plan.[[19]](#footnote-20) This ruled out the use of compensated reductions in entitlement reliability, or other administrative options to reduce allocations.
* In 2014, the Australian Government ceased open‑market water purchases and prioritised infrastructure programs (Birmingham 2014). In 2015, the government legislated a limit of 1,500 GL/y on all water purchases towards Bridging the Gap.[[20]](#footnote-21) (This cap was repealed by the *Restoring Our Rivers Act 2023*.)
* In 2020, the Australian Government ruled out additional open tender purchases (DCCEEW, sub. 77, p. 7).

The decision to cease open tenders led to the use of limited tenders through direct negotiation, which is a slower way to recover large volumes of water. The amounts paid for some water entitlements between 2016 and 2019, alongside weak transparency on the reasons for those amounts, contributed to community concerns that culminated in a 2020 performance audit by the Australian National Audit Office (ANAO 2020). The Department adjusted its processes in response to the ANAO audit to develop frameworks for value for money, probity and monitoring, evaluation, reporting and improvement, and an update to its conflict of interest management policy (DCCEEW, sub. 77, response to information request, pp. 17–18). There have been just two limited tender purchases since 2019 (DCCEEW, sub. 77, attachment 2).

#### MDB Ministerial Council decisions affected delivery of the 450 GL/y

Recovering water through efficiency measures towards the 450 GL/y target requires those projects to meet a test of ‘neutral or improved socioeconomic outcomes’ in the Basin Plan. This test is met where a water holder willingly participates in an on‑farm or off‑farm water use efficiency project, or if a project is proposed by a Basin state government.[[21]](#footnote-22)

However, the additional socioeconomic criteria, agreed to by the MDB Ministerial Council December 2018, are restrictive. For example, the need to ‘not directly increase the price of water’ (DCCEEW 2021b, p. 2) is difficult to verify and comply with. Some inquiry participants supported the criteria,[[22]](#footnote-23) but others said they can block a large number of potentially worthwhile projects. Beasley (sub. 47, p. 13) referred to them as ‘absurd’, and Goulburn Valley Environment Group (sub. 28, p. 2) said the criteria cause ‘landholders to miss out [on] opportunities to rationalise irrigation systems and [deny] communities opportunities to transition to a drying environment’. The Australian Government agreed to cease on‑farm water recovery programs towards the 450 GL/y in Victoria and New South Wales (ABC 2021), prioritising off‑farm projects instead.

The Australian Government has opened and closed new programs towards the 450 GL/y multiple times. According to the second WESA Review:

* the South Australian pilot of the Commonwealth On‑Farm Further Irrigation Efficiency (COFFIE) program opened in September 2016 and closed in October 2018
* the Murray–Darling Basin Water Infrastructure Program opened in July 2018 and closed in December 2018
* the Water Efficiency Program opened in July 2019 and closed in March 2021
* the OFEP opened in October 2021 and remains operational, albeit closed to new projects unless proposed by a state government (WESA Review 2021, pp. 15–18).

Reviews of the WESA concluded that the current program design significantly limited the number of projects that can be proposed. As of December 2021, the panel estimated that the program was only likely to deliver up to 60 GL/y by the expected expiry of the WESA in June 2024 (WESA Review 2020, p. 19, 2021, p. 25). Work undertaken for the review indicated that up to 675 GL/y of additional efficiency measures may be technically feasible – but this includes on‑farm efficiency projects (which are not included under current program design) as well as urban and industrial projects, stock and domestic efficiency works, and off‑farm projects. The assessment of technical efficiency did not consider the cost of these works (MJA 2021, p. 46).

### … while water market and other developments have changed the operating context

Southern Basin water markets have changed markedly since the Plan commenced, and this has substantially altered the opportunities – and cost – to recover water for the environment. The ACCC observed that, since 2012:

… there have been significant changes to the volume and location of trade, the participants in the market, Basin State trade administration practices, the evolution of environmental watering arrangements and the impacts of changing climate patterns. (sub. 26, p. 5)

Over this period the cost of recovering water – through purchase and infrastructure projects – has increased substantially. In 2022‑23, the Aither water entitlement price index sat at about three times its 2012 value, having grown at an average rate of 15% a year since 2015‑16 (Aither 2023a, p. 10). This affects the value for money assessment for water purchases and other projects, and is in part why the original budget for recovering the 450 GL/y will not be adequate to meet that target (WESA Review 2020, p. 17, 2021, p. 21).

The costs of water use efficiency projects have also increased. Substantial past investments in water efficiency means there are fewer cost‑effective water use efficiency gains to be made – even before considering higher construction costs (figure 2.6). The current suite of off‑farm projects under the OFEP are contracted to recover 23.4 GL/y at a cost of almost $347 m (DCCEEW 2023d), representing an average cost, in LTAAY terms, of $14,800 per megalitre (ML). Table 2.4 outlines the average costs of infrastructure modernisation programs over time in the Murrumbidgee Irrigation network, by means of example.

Table 2.4 – Outcomes of off‑farm water recovery programs in the Murrumbidgee Irrigation area

|  | Year | Cost (2022 $m) | Recovery (ML LTAAY) | Average cost  ($/ML LTAAY) |
| --- | --- | --- | --- | --- |
| PIIOP round 1 | 2009 | 68.17 | 5,700 | 11,959 |
| PIIOP round 2 | 2011 | 221.80 | 36,960 | 6,001 |
| PIIOP round 3 | 2015 | 144.53 | 13,663 | 10,578 |
| OFEP | 2022 | 126.48 | 5,472 | 23,114 |
| Total |  | **560.97** | **61,795** | **9,078** |

**PIIOP:** Private Irrigation Infrastructure Operators Program in New South Wales. **OFEP:** Off‑Farm Efficiency Program. **LTAAY:** Long‑term Average Annual Yield.

Sources: DCCEEW (2022c, 2023d). Deflated to 2022 dollars using ABS *Consumer Price Index, June quarter 2023* Series A2325846C, converted from quarterly to financial year.

However, expectations about future water entitlement price growth also affects the willingness of entitlement holders to participate in water recovery infrastructure projects. For example, on‑farm infrastructure projects are less appealing to entitlement holders if the market value of water entitlements is expected to increase: they are being asked to trade an appreciating asset (a water entitlement) for a depreciating one (on‑farm water infrastructure) (MJA 2021, p. 30). Greater water‑use efficiency can also introduce additional operating costs, including higher energy use from pumping systems compared to gravity‑fed systems (Croke, sub. 12, p. 10). Jeremy Cass observed that:

Smaller growers used the [infrastructure grant] money to convert from flood irrigation to drip irrigation and other efficiencies in the spirit that the scheme was intended, most of these growers would now tell you that had they known what the future would hold they would not have gone down this path due to the rising cost of power to move the water that was once free with gravity. (sub. 20, p. 1)

Holding water entitlements can be a more financially‑prudent decision for farmers. The Department’s evaluation of the COFFIE pilot program demonstrates this: a survey of program participants found that, in spite of how generous the scheme was, 40% would not participate in a future program (43% said they would). Some cited a lack of viable projects on their properties, but others said the subsequent increase in water prices means they would prefer to keep the water (Cutting et al. 2022, pp. 38–39). Analysis undertaken for the second WESA review also suggested that a range of economic, climatic and socio‑political factors affect participation in water use efficiency measures (MJA 2021, pp. 30–41).

### Poor accountability for under‑delivery on supply measures

It has been evident for some time that the full suite of supply measure projects will not be delivered by June 2024. Some projects are years away from being operational, let alone capable of demonstrating ‘environmental equivalence’ to environmental water recovery, and other projects are not viable. There are a few reasons for this under‑delivery.

* The initial project selection process appears not to have adequately considered the delivery risks of complex projects.
* The Australian Government’s funding ‘gateway’ process (which outlines how projects progress to receive funding) lacks transparency, and there are no consequences for Basin governments failing to adjust the overall program – including in response to independent reviews.
* The ‘threat’ of water recovery was ineffective in incentivising Basin states to progress projects, and discouraged the amendment or withdrawal of projects.
* More recently, finalising some projects has been delayed because of flooding and the COVID–19 pandemic, which limited the ability of governments to engage with regional communities and start construction.

Box 2.2 outlines the experience with the Victorian Murray Floodplain Restoration projects, from assessment through to their current status, to highlight how some of these factors played out.

#### Project selection did not adequately consider complexity or delivery risk

The 2017 supply measure package included projects that have since turned out to be either unfeasible or extremely costly. This was, in part, because the initial assessment process underestimated the complexity of some projects, and community engagement may not have been adequate.

In assessing projects for its 2017 determination of the water recovery offset, the MDBA assessed the project business cases for whether they had a risk management strategy in place to assess project delivery risks (MDBA 2016b, p. 24). Basin governments were responsible for developing a joint program to manage implementation risks.

Prior to the MDBA’s determination, Basin state governments were required to complete feasibility studies and business cases for each individual supply project. These feasibility studies and business cases were then used by the BOC to notify the MDBA of the full suite of proposed measures. Projects were assessed in three phases: feasibility (phase 1), a business case (phase 2) and demonstration of in‑principle funding arrangements (phase 3) (MDBA 2017b, p. 5). Through each of these phases, governments had to demonstrate that the projects were technically feasible and cost‑effective, were likely to deliver outcomes, and the risks were manageable (MDBA 2017b, p. 9).

Although the business cases included risk assessments, these tended to focus on the risk of adverse environmental outcomes due to project construction and operation, rather than delivery risk. For example, the risk assessment within the Belsar-Yungera project business case only outlined risks to water quality or damage to floodplain ecosystems around the sites (Victorian DEPI 2015a, pp. 44–49), with the subsequent risk management strategy also focusing on these potential impacts (2015a, p. 51).

Limited community engagement in this process may have contributed to project delivery risks not being identified during the initial determination. Many community members said they were dissatisfied with the level of transparency and consultation during the original determination process (PC 2018, p. 128), with inadequate information provided on benefits, costs and impacts of the proposed supply measures. The MDBA’s determination report also provided limited transparency on decision‑making: it did not provide detailed assessments of individual projects, instead outlining the benefits of projects at a high‑level (MDBA 2017d, pp. 36–44). Little consultation was required in this process: the MDBA was only required to consult as part of estimating the water recovery offset, although Basin states had to provide details of engagement as part their project proposals (2017b, p. 10).

| Box 2.2 – Victorian Murray Floodplain Restoration Projects |
| --- |
| The Victorian Murray Floodplain Restoration Projects (VMFRPs) refer to nine supply measures included in the 2017 determination. The VMFRPs aim to improve environmental outcomes for high‑value floodplains along the Victorian side of the River Murray by constructing infrastructure (such as regulators, pumps, and containment banks) to allow for water to move onto the floodplain more often. Some projects also include other environmentally‑beneficial infrastructure, such as fishways.  A list of the projects and their most recent updated status is shown in the table below.   | Project | Status (June 2023) | Capital costs to  June 2023 (2014 dollars) | Implementation costs to June 2023 (2014 dollars) | | --- | --- | --- | --- | | Lindsay Island (Stage 2) floodplain management project | Paused | $63,262,361 | $72,831,526 | | Wallpolla Island floodplain management project | Paused | $49,427,395 | $59,523,808 | | Guttrum and Benwell State forests floodplain environmental works project | Paused | $28,449,309 | Not available | | Gunbower national park floodplain management project | Paused | $12,838,185 | Not available | | Hattah Lakes North floodplain management project | Not operable; unlikely to be in place by 2024 | $5,586,623 | $8,811,408 | | Belsar–Yungera floodplain management project | Not operable; unlikely to be in place by 2024 | $47,177,817 | $55,632,428 | | Burra Creek floodplain management proposal | Not operable; unlikely to be in place by 2024 | $7,787,033 | $12,138,362 | | Vinifera floodplain management project | Not operable; unlikely to be in place by 2024 | $5,332,891 | $9,122,148 | | Nyah floodplain management project | Not operable; unlikely to be in place by 2024 | $7,055,019 | $10,942,589 | | **Total** |  | **$226,916,633** | **$229,002,269a** |   a. Implementation costs for Guttrum and Benwell, and Gunbower projects were not available. All figures are adjusted for inflation and presented in net present value terms in 2014 dollars, as in the original business cases.  In April 2023, the Victorian Government announced a pause to four VMFRP projects, and stated that:  Due to time and cost impacts from these challenges, the VMFRP was required to refocus its work program in March 2023 as it did not have Australian Government commitment for a time extension or further funding. This was to mitigate any State financial risk and stem any perceptions of being disingenuous in undertaking cultural heritage surveys with no intent to construct. Negotiations with the Australian Government continue, for further funding and time. (sub. 74, response to information request, p. 22)  Pausing the VMFRP projects has impacted cultural heritage work which would have otherwise been undertaken as part of the project. Latji Latji Mumthelang First Peoples explained that:  [W]hen the Victoria Government halted the VMFRP in 2023, we couldn’t get this burial site ‘heritage listed’ because the cancellation meant that the required Cultural Heritage Management Plan could not be completed (even though it was only a month shy of being finished). The consequence of this is that we cannot get government funding to undertake other requirements to achieve heritage listing of this site and secure its future. (sub. 78, p. 2)  Given that project costs estimated in business cases were calculated using 2014 present value amounts, increases to project costs are expected. The 2019 Stage 1 funding agreement between the Australian and Victorian governments stated that project construction was estimated to cost more than $300 million (Andrews 2019). This figure represented a 19.4% increase (in constant dollar terms) of the $226.9 million estimated in the initial capital costs.**b**  MDBA reported in June 2023 that all projects are in the planning phases (MDBA 2023m, pp. 24–28), and it is not clear if that funding agreement is able to cover development costs for all projects.  **What are the next steps?**  In their submission to this inquiry, the Victorian Government stated that the ‘cost to complete Stage 1 activities is being finalised to enable Victoria to progress planning and approvals for all nine sites; and enable further negotiations to go to construction’ (sub. 74, response to information request, p. 22). This suggests that the funding arrangement made in 2019 was not enough to cover all project costs.  The Victorian Government has not made any further announcements on whether works will restart in the near future. However, Victoria’s absence from the August 2023 agreement on Basin Plan implementation indicates that project funding may not continue beyond June 2024. |
| **b.** The initial capital costs of $226.9 million is equal to about $251.2 million in June 2019, when adjusted using the ABS producer price index for ‘other heavy and civil engineering construction’.  Sources: (MDBA 2023m, pp. 24–28; Victorian DEPI 2014a, p. 82, 2014b, p. 113, 2015d, p. 111, 2015g, pp. 96–97, 2015c, p. 92, 2015a, p. 92, 2015b, p. 80, 2015f, p. 84, 2015e, p. 86). |
|  |

Inquiry participants also said that the initial consultation process did not adequately draw on local knowledge. Coleambally Irrigation Cooperative argued for both a ‘bottom up’ and ‘top down’ approach to identifying opportunities to develop the supply projects, and noted that:

Many of the SDLAM projects proposed by government had no community ownership and were never built in partnership with communities or with those impacted. It should be no surprise that several large, complex projects, such as constraints relaxation projects and Menindee Lakes reconfiguration, have no prospect of being achieved in the timeframes set, if at all, due to the lack of community consultation and resultant ownership. (sub. 21, p. 3)

Murray Regional Strategy Group (sub. 27, p. 2) also raised concerns with the ‘top down’ approach, which made communities ‘resentful and angry’. They likewise noted the ‘bureaucratic lens’ through which programs were designed and planned meant they were ‘not planned with practical knowledge, experience and understanding of locals’. As one participant put it:

Frustration with the MDBA approach has been reported in community consultation meetings, submission and despite appeals for a more flexible and adaptive approach that can incorporate new information or ideas, the rigidity of the MDBA’s approach does not permit these sort of concepts. (Louise Burge, sub. 98, p. 7)

Shortcomings in the consultation process undermined community support for key projects. With specific reference to the Menindee project, the Pastoralists Association of West Darling said consultation was poor and at times misled the community (sub. 42, pp. 2–3). They also claimed that information provided in stakeholder meetings was ‘extremely limited’, with ‘no costings, no water savings outcomes and no operational rules’ outlined.

#### Transparency on project delivery has been inadequate

Public information on the scope and progress of supply projects has been relatively limited. Only limited detail has been provided on how close projects are to delivery, and how or why changes are made between updates. And business cases and other information released at the start of the program did not always outline why projects were chosen or warranted ongoing funding. The regular reporting of delivery delays – again, with limited detail – reduces the impact of these statements, and gives no guidance on how this reporting contributes to program‑level adjustments.

In 2019, the MDBA commenced annual assurance reporting on the supply measures. Following the 2021 *SDLAM Reconciliation Framework*, the MDBA changed their focus from updating on project delivery progress to reporting on whether operational projects were likely to deliver the expected environmental outcomes (MDBA 2021f, p. 11, 2022n, p. 9). Given that few projects were operational at the time (and a period of operation is needed to judge environmental outcomes) only four projects were assessed in 2021 and nine in 2022 (MDBA 2021f, p. 11, 2022n, p. 10).

Publicly reporting on project delivery is important. However, given poor progress on supply measures has been highlighted in multiple MDBA assurance reports and independent reviews – but not led to any real change to the program – this poor progress has effectively been normalised, with the impact of each new report diminished.

##### Basin governments have failed to take up opportunities to reset the program

Basin governments are jointly responsible for delivering the supply measure package through the BOC, and it remains unclear where responsibility lies for inadequate project delivery, or for adjusting the overall approach to implementation. Multiple reviews have recommended program‑level changes to supply measure implementation, but it is unclear what (if any) changes have been made in response, or how responsibility for adjusting the program is shared between the MDB Ministerial Council, the Australian Government and the BOC.

In 2021, Indec undertook a detailed assessment of the supply projects and the risk of non‑delivery. The review made eight recommendations, including a ‘reset’ of the supply projects (including constraints projects), and an options assessment of what could ‘be practically implemented, by when’ (2021b, p. 2). Both the Ministerial Council and the BOC outlined responses to these recommendations, with the Ministerial Council agreeing in April 2021 to rescope the Menindee and Yanco Creek projects. In September 2021, the BOC released a response to the other five recommendations. Four of the five recommendations in the report were agreed with, including the need for a mechanism to allow changes in project scope. However, the committee stated that the final recommendation – advocating for independent third‑party verification and reporting on project progress – was not considered necessary at time of response, and warranted further consideration.

Although the BOC has commenced quarterly dashboard reporting (in line with recommendations four and six), it is unclear whether the recommendation to review stage 2 funding approval processes (recommendation five) has been implemented, and no re‑scoped projects have yet been notified to the MDBA.

##### Can project delays be attributed to COVID–19 and flooding in the Basin?

While accepting that projects were behind schedule, Basin state governments highlighted issues with supply chains, reduced labour availability, flooding events and lockdowns during the COVID–19 pandemic as reasons for slow progress and increasing costs.

* The NSW Government stated that delays in project commencement and funding were compounded by widespread bushfires, drought and floods, and the pandemic which disrupted project consultation and delivery (sub. 43, p. 5).
* The Victorian Government said ‘record floods, supply chain issues and the COVID–19 pandemic’ contributed to project delays (sub. 74, p. 1).

These factors are likely to have delayed the completion of some projects that were in the pre‑construction phase in New South Wales and Victoria. However, other key projects were already behind schedule at the time of the Commission’s previous assessment, prior to flooding or the COVID–19 pandemic. The MDBA’s 2019 assurance report also concluded that some projects were ‘extremely complex, with risks and policy matters to be worked through and resolved for the significant program benefits to be realised’ (MDBA 2019b, p. 6). And while the MDBA acknowledged these broader factors (MDBA 2023m, p. 1), it did not attribute overall delays in the program to the impacts of flooding or the pandemic.

#### The Australian Government does not hold Basin states to account

As project funders, the Australian Government should be holding Basin state governments to account for project delivery. But while funding agreements were conditional on Basin states achieving development milestones, there are projects that are still in the design and approval stages.

The independent gateway review of projects that the Commission recommended in 2018 (discussed earlier) was designed to ensure there was an opportunity to assess whether a project remained a good use of public funds prior to confirming final funding – as well as providing an avenue to abandon projects that were no longer worthwhile (PC 2018, p. 139).

The Australian Government and Basin state governments finalised funding schedules at the end of February 2019. The agreed schedule was a two‑stage funding approach, with some implementation milestones required before agreements could be reached on the second stage of funding. While this mirrors the recommended gateway process, it lacks the recommended independent review panel.

##### Funding agreements created delays, but not accountability

The late agreement of funding arrangements limited the time to deliver those projects that did not already have other funding and could not otherwise commence planning. As the MDBA said, the ‘funding delay has compressed the timeline for implementation, which may pose a risk for the full delivery of some of the more complex and detailed projects’ (MDBA 2019b, p. 11).

The 2021 Indec review also identified funding approvals as a major risk for most projects, with delays impacting project continuity and schedules as well as credibility with stakeholders. Indec recommended a staged release of stage 2 funding to allow for an adaptive design model that ‘better aligns with the reality of delivery challenges’, and that this could be delegated to below a ministerial level (2021b, p. 2).

Basin state governments also highlighted funding delays in their submissions to this inquiry. The Victorian Government said funding negotiations (among other factors) had impacted delivery timelines for projects and negotiations with the Australian Government for funding were ongoing (sub. 74, response to information request, p. 21). The NSW Government also referenced delays to project commencement and funding, noting that inefficiencies in program management arrangements and delays in negotiating amendments to funding arrangements had led to challenges (sub. 43, p. 5).

Ongoing delays in finalising funding agreements could further reduce the incentive for Basin state governments from fully committing to project delivery, and impact on Plan implementation. Chapter 9 discusses the need to draft intergovernmental agreements in ways that provide the right incentives for delivery.

#### The policy intent to make up any shortfall through water recovery did not motivate Basin governments to deliver projects

If the supply measures fail to achieve the full 605 GL/y offset, Basin governments are meant to ‘make good’ on any shortfalls against the Bridging the Gap target through additional water recovery. With water recovery through purchases unpopular in many Basin communities (ABC News 2023; Minister for Lands and Water NSW 2022), this was seen to provide an incentive for Basin state governments to prioritise delivering the projects and avoiding any water recovery shortfall.

But this incentive has not worked well enough to motivate progress. In part, this is because governments have not made clear how ‘making good’ will take place, including how any shortfall will be recovered following reconciliation. And as discussed earlier, Australian Government policy decisions to amend the Water Act and limit total surface water purchases has undermined the credibility of any threat. In the views of some participants, this model did not provide a sufficiently strong incentive for Basin state governments to implement projects; rather, it created a situation where Basin communities bore the risk of governments failing to deliver (Committee for Greater Shepparton, sub. 80, p. 10). The Central Irrigation Trust, for example, said:

A learning from the current model is that the current governance and accountability framework has not proven sufficient to hold state governments accountable for the delivery of what they signed up for. For irrigation communities who have done what has been asked of them, the lack of action, particularly from NSW, is creating an unjust scenario where buybacks are considered a viable fix. (sub. 33, p. 2)

The threat of water recovery could also have provided an incentive for governments to avoid being upfront about the infeasibility of certain projects and the need to withdraw or rescope them (as this would have effectively confirmed a shortfall in the full 605 GL/y offset). And the risk of a reduced offset may have encouraged Basin state governments to avoid making changes to projects or delivery processes, even when change could have increased the likelihood of successfully delivering projects.

#### Ultimately, Basin governments faced few consequences for under‑delivery

Overall, weak and muddled accountability for delivering the supply measure projects between Basin governments allowed them to avoid and deflect criticism for slow implementation. Planning and delivery are inadequate at both project and program scales, and the inflexibility of the determination process has hampered any ability to revise projects. The BOC is ultimately responsible for formally rescoping and withdrawing projects, but this has not taken place.

Unless these underlying governance issues are addressed, extending timeframes for the supply measures will not substantially improve the prospects of full delivery.

|  | Finding 2.1  Resetting the balance has slowed because of weak governance in a changing water market |
| --- | --- |
| Resetting the balance in the Basin has slowed since 2018 and will not be completed by the original deadline of 30 June 2024. Limited progress has been made toward environmental water recovery targets, including towards the additional 450 GL/y. This is largely because of government policy decisions, alongside rapid growth in water entitlement prices.  Key supply projects will not be completed by the original deadline. Accountability for implementing the supply projects is weak, and Commonwealth funding arrangements have failed to drive effective project implementation by Basin state governments. Key projects are unviable, but Basin governments are not transparent about the need to rescope or withdraw these projects, or the implications of failing to deliver projects on time.  These delays have substantially increased the financial costs of meeting Basin Plan water recovery targets, prolonged the uncertainty Basin communities face, and reduced the potential environmental outcomes of the investment in the Plan. | |
|  | |

### Constraints‑easing projects were hampered by unrealistic expectations

The sluggishness of constraints‑easing reflects both the poor accountability and inflexibility of the supply measure package (discussed above), and the difficulty of scoping and progressing these highly complex and long‑term projects.

#### Initial costs and timeline estimates were significantly understated

The initial estimates for the costs and timelines for constraints‑easing were optimistic.

Originally, $200 million was committed to easing constraints through the WESA, but the anticipated costs of the projects have increased significantly since then. Business cases developed as part of the supply measure package led to an updated cost estimate of between $510‑630 million for southern Basin constraints‑easing projects by 2016 (figure 2.2). And there is a risk that estimated costs will continue to increase: in 2021, Indec noted that, based on one of the few funded sub‑projects (the NSW Mid‑Murray Anabranches Project), costs had roughly doubled from the 2016 cost estimates (Indec 2021a, pp. 23–24).

Slow progress calls into question whether the estimated timelines were realistic, as previous implementation reviews by the Commission and others noted (Indec 2021a, p. 5, 2021b, p. 18; MDBA 2020b, p. 13, 2022n, p. 2). Basin governments now acknowledge this (DCCEEW, sub. 77, p. 10) and it is highly unlikely the full suite of constraints‑easing will be complete by the new proposed 2026 deadline (DCCEEW 2023b).

Inquiry participants also argued that the original flow rates proposed by the MDBA in the Constraints Management Strategy were unrealistic and not supported by affected landholders. Criticising the development of the 2013 Constraints Management Strategy, the NSW Farmers’ Association claimed that:

… the delays in achieving implementation of the CMS [Constraints Management Strategy] have initially occurred when under the management in 2013/2014 by the MDBA, as affected landholders did not endorse the higher end flows proposed by the MDBA … Key concerns of landholders were the risk of elevated flooding, the flow targets, which were not considered feasible or realistic, and the reasoning as to how these targets were calculated. MDBA-led investigations were confined largely to remote desktop studies of what the potential impacts were likely to be. (sub. 76, p. 3)

#### Including constraints as supply measures has undermined social license for the projects and skewed incentives for Basin states

Constraints‑easing is a standalone component of the SDL adjustment mechanism, designed to enhance the outcomes of held environmental water, including the additional 450 GL/y.[[23]](#footnote-24) Most southern Basin constraints‑easing projects were later included in the supply measure package, and are considered to contribute substantially to the 605 GL/y offset.[[24]](#footnote-25)

Easing constraints requires low‑level inundation of private land on floodplains. However, both the NSW and Victorian governments have policies in place that prohibit flooding of private land without consent, reflecting their liability under their respective water acts.[[25]](#footnote-26) This means they will need to undertake detailed property‑level modelling and negotiate easements or similar instruments with affected landholders.

The prescriptiveness of the supply measure process has limited scope to adjust project parameters, which undermines meaningful engagement with those affected landholders and hampers negotiations. Louise Burge said:

At the heart of Government failures is a failure to value local knowledge, limited Government actual investigation of the types and extent of issues and a ‘top down’ approach for implementation, a factor now being reinforced in 2023. (sub. 98, p. 10)

Murray Valley Private Diverters also linked this top‑down approach, and the resultant mistrust, with the focus of State governments on delivering the supply measure offset, claiming that:

The [NSW Reconnecting River Country] program is not being implemented in a manner that builds trust, instead there is already a high incidence of mistrust and an appearance of divide and conquer to achieve flow objectives that will give the highest scoring card from the MDBA. (sub. 95, p. 13)

As with other supply measures, the focus on avoiding the risk of water recovery has meant Basin state governments have had an incentive *not* to modify, adapt or re‑scope constraints‑easing projects. The Murray Valley Private Diverters further noted that:

Restrictive MDBA timeframes to lodge projects, an inability to apply new learnings, new ideas and methodologies, is at odds with the concept of good practice in project development. (sub. 95, p. 11)

In some cases, opposition to constraints‑easing is linked to opposition to the 450 GL/y of additional water recovery. Some participants argued that both programs lacked a sound basis and should not be continued.[[26]](#footnote-27)

Focusing on both the water recovery offset and the link with the 450 GL/y means less focus on the environmental and operational benefits of eased river constraints (discussed below). These broader benefits have not been well communicated, and this has affected broader understanding and support for the measures outside of those directly affected. As put by Anne Jensen:

There has been major misinformation about potential damage from environmental flows and this needs to be strongly countered with correct information about the benefits of water for river health to all river communities … Going forward, there is a need to invest in selling the value of completing constraints projects better, provide support to landholders and regional department officers, and to counter misinformation equating environmental flows with the devastating impacts of the 2022 floods. (sub. 39, pp. 2, 3)

There are environmental benefits to be achieved by easing constraints, but ongoing delays have meant these are now considerably more costly to achieve. The focus has moved from their broader system‑wide environmental and operational benefits, towards a narrow focus on water recovery.

|  | Finding 2.2  Program design has not suited the complexity of constraints‑easing projects |
| --- | --- |
| Constraints‑easing projects have progressed slowly, with detailed property‑level modelling and extensive landholder engagement needed to identify and manage the impacts of higher flow rates. Including constraints in the supply measure package has led to a focus on maximising the water recovery offset, rather than the environmental and operational benefits of easing constraints. | |
|  | |

### The northern Basin toolkit measures lack dedicated focus

Although some elements of the northern Basin toolkit are in place, slow progress on other aspects appears to reflect weak accountability for delivery, as well as broader market issues affecting infrastructure project delivery.

#### Weak oversight, along with COVID–19 and flood events, has stymied full delivery

The Northern Basin Project Group (NBPG) is a committee of the Australian, New South Wales and Queensland governments and is responsible for monitoring progress. The NBPG is required under the amended 2013 IGA to report on project progress to the MDB Ministerial Council and the BOC on a six‑monthly basis (COAG 2019, p. 28). Only two annual progress reports are public (NBPC 2022, 2023).

Rather than being a standalone series of measures, elements of the toolkit package are highly interdependent on completion of other areas of Basin Plan implementation, and are affected by delays in those elements. For example:

* protection of environmental flows is contingent on water resource plans, which are not yet in place in parts of NSW (chapter 4)
* targeted water recovery is entirely subject to the Australian Government’s progress on Bridging the Gap (discussed above), which also relies on finalisation of cap factors through the NSW WRP accreditation process
* the Gwydir constraints measure is part of the broader NSW ‘Reconnecting Watercourse Country’ program; although not part of the supply measure package, it has also run into similar issues with landholder support (Gwydir‑Gingham Landholders, sub. 23).

The key aspect of the toolkit, then, is the series of environmental works and measures to be delivered by the New South Wales and Queensland governments. Delays caused by various weather events, COVID restrictions, and difficulties sourcing labour and materials are reported for these works (NSW Government, sub. 43, p. 6; NBPC 2023).

The MDBA claimed that ‘the commitment of Basin governments to implementing the northern Basin toolkit has slowed and valuable elements of the package will not be implemented by the agreed deadline’ (sub. 61, p. 2). However, the Queensland Government disagreed, noting that it has ‘implemented a number of measures and continue[s] with a commitment to progress proportionate to Commonwealth approval processes and funding’ (sub. 112, p. 5). The NSW Government also reiterated that it ‘remain[s] committed to delivering [our] projects under the Northern Basin Toolkit’, and that ‘three of the six NSW Toolkit projects … have moved beyond the business case with implementation underway’ (sub. 111, p. 5).

#### No firm assurances on environmental outcomes

Unlike supply measures, there is no requirement or expectation that the toolkit projects are ‘environmentally equivalent’ to the 70 GL/y reduction in water recovery. Instead, the projects only aim to ‘further enhance river health even with a reduced recovery volume’ (MDBA 2016a, p. 12). The annual reporting for toolkit projects is less frequent and detailed than the quarterly and annual progress reporting for the supply and constraints measures (MDBA 2022o, 2023b).

Because the toolkit measures are not included in the Basin Plan itself (being part of the 2013 IGA), there is no specific legislative requirement to ensure the environmental outcomes of the projects are achieved. No dedicated assurance monitoring is in place to monitor and report on environmental outcomes over time.

This means there is no built‑in mechanism to provide public confidence in the environmental outcomes achieved. As such, even if the projects are implemented in full, there is no guarantee that the environmental outcomes of these projects will align with those expected, or what the benchmarks are to gauge project effectiveness.

The NSW Government noted that ‘monitoring, evaluation and reporting plans have been developed for the two fish intervention projects of the Toolkit’ although these require a funding commitment from the Australian Government to implement (sub. 111, p. 5). They also state that the Australian, New South Wales and Queensland governments are currently ‘establishing an evaluation process around the ecological outcomes achieved through delivery of the environmental works projects and measures’ (NSW Government, sub. 111, p. 5). DCCEEW also pointed to the 2025 Basin Plan Evaluation and 2026 Basin Plan Review as opportunities to assess the environmental outcomes of the measures (sub. 127, p. 11).

The CEWH noted the importance of the toolkit in supporting the protection of environmental water, in line with the ‘prerequisite policy measures’ required under the Plan (sub. 69, p. 21). The most recent report on progress highlighted the opportunity, under the toolkit, to support even greater outcomes through Basin‑wide protection of environmental water: that is, the accounting and protection of Northern Basin environmental flows through the Menindee Lakes and to the southern Basin (NBPC 2023, p. 4). While potentially very worthwhile, it is unclear whether and how this option is being pursued, and how it fits within the framework of the toolkit and the Basin Plan.

|  | Finding 2.3  Slow progress on the northern Basin toolkit reflects unclear accountability for delivering program outcomes |
| --- | --- |
| Delays implementing the northern Basin toolkit measures are a result of inadequate accountability for delivery, as well as a lack of oversight and review of the measures. Public information about project progress has been sparse, and there is no framework in place to monitor the environmental merits of these projects as they progress. | |
|  | |

## Where do we go from here?

Amendments to the Plan are an opportunity to reset and make strong progress – but risks remain

The passage of the Restoring Our Rivers Bill is a significant shift in implementation of the Basin Plan since the Commission’s interim report in October.

In our interim report we noted that, at the time, the Bill would not do enough to resolve the mismatch of responsibility and accountability that has contributed to inadequate progress across the range of projects and as such would not ensure resetting the balance could be finalised.

Since the interim report was finalised, the Bill has been amended and passed by both houses of Parliament. The amendments include a requirement in the Water Act to report to Parliament on progress (s. 85AB) and a provision that allows the Australian Government to withdraw individual supply measures (s. 7.12(6A)). Both changes address key recommendations the Commission made in the interim report.

However, some key findings and recommendations are not addressed by these amendments.

### More time is necessary, but may not be sufficient

Delaying the reconciliation of supply measures to 2026 is necessary to provide more time to implement viable but incomplete supply measures. However, it also means delaying any robust interrogation of the expected environmental benefits of the projects, and clarifying the quantum of the expected supply measure shortfall.

The August agreement accepts that most constraints‑easing projects will not be complete by 2026. This means those projects will deliver a smaller water recovery offset and limit the environmental benefits of other projects that rely on constraints‑easing, such as the outcomes of the Enhanced Environmental Water Delivery project (MDBA 2023m, pp. 19–21). With the agreement not including an extension for funding of Victorian supply projects beyond June 2024 and the known unviability of some existing supply measures, including the Menindee Lakes project, a shortfall at reconciliation (end 2026) of more than 100 GL/y is still a material risk.[[27]](#footnote-28)

In evidence provided to the Senate Environment Committee, the Australian Government indicated that the full offset is unlikely to be achieved, even following the amendments. Responding to our interim report, the Deputy Secretary of DCCEEW said:

We would agree with the observation that basically the full 605 won’t be delivered by projects by the end of 2026; we utterly agree with that. (Senate Environment and Communications Legislation Committee 2023a, p. 67)

The amendments allow Basin state governments to propose new supply projects (up until 30 June 2025) if they can be operational by December 2026. However, noting the limited progress made on supply measures over the last five years, it is unlikely that enough new projects will be identified that:

* can compensate for the water recovery shortfall created by delaying constraints and re‑scoping the Menindee Lakes project, without impacting the outcomes of other supply measures
* represent value for public money when compared to direct water purchase
* can garner the support of affected communities, and
* can be designed, approved and fully implemented by December 2026.

The amendments to the Plan provide some additional accountability mechanisms for supply measure delivery, including the requirement for the departmental secretary to prepare an annual report on progress (discussed below).

Basin governments should endeavour to collectively deliver new and remaining cost‑effective supply measures within the extended timeframe. But Basin governments should also accept, and plan for, the risk that the full 605 GL/y offset will not be delivered by December 2026 and result in a significant water recovery shortfall in the southern Basin.

|  | Finding 2.4  Full delivery of the 605 GL/y supply measure offset by December 2026 is uncertain |
| --- | --- |
| Full delivery of the 605 GL/y supply measure offset by December 2026 is at risk because:   * key projects, including the Menindee Lakes project, will not be delivered as designed * constraints‑easing projects cannot be completed in full by December 2026 (which may also limit the offset achieved by other supply measures) * there are unlikely to be enough new supply projects that are implementable by December 2026, represent value for money andcanmake a substantial contribution to the water recovery offset.   There is a strong possibility of a significant water recovery shortfall in the southern Basin. | |
|  | |

### Market liquidity will constrain delivery of the 450 GL/y

The Restoring Our Rivers Act provides some additional clarity on the program to deliver an additional 450 GL/y, with an obligation on the Australian Government Minister for Water to ‘take all reasonable steps’ to deliver the water (Water Act, s. 85AC), alongside more flexibility in how an additional 450 GL/y of environmental water is made available.

By allowing for water purchases to contribute to the 450 GL/y, the amendments will reduce the cost of recovering water towards that target. However, based on current water prices, purchasing the remaining 424 GL/y will still not be possible within the existing WESA budget.[[28]](#footnote-29)

Attempting to purchase this volume of water by 2027 also risks significant disruption to water markets – even before considering the possible supply measure shortfall. As the ACCC said:

Delays in project delivery, with the associated uncertainty around water recovery strategy, not only inhibit implementation of the Basin Plan, but are also likely to be having a negative impact on potential water market participants’ confidence to make water‑related investment decisions. … These interventions may have unintended consequences depending on how they are structured and, even if they successfully recovered remaining water required, they would likely significantly affect market prices, certainty and confidence. (sub. 26, p. 9)

The NSW Irrigators’ Council, noting that less than 100 GL/y in entitlements is traded commercially each year on the water market, also said:

… the common notion that the Government could simply enter the market and rapidly purchase 450 GL is not correct. At best, it would take several years for 450 GL to be purchased, with the scale of Government intervention inevitably distorting the market for years … (sub. 103, p. 33)

Recovering the remaining 424 GL/y via purchases by 2027 would, on face value, more than double the volume of entitlement trade in the southern Basin each year, which has averaged 98 GL/y in the last three years (Aither 2023b, p. 18). This relatively low level of entitlement trade means that only a limited volume could be purchased each year without paying high premiums, and increasing water prices in ways that cause excessive disruption to water markets and Basin communities. The expectation of a significant government entry into southern Basin water markets will also affect the decisions of other market participants.

The Commission previously raised concerns about the assumptions underpinning the program to recover the additional 450 GL/y, including: the lack of any review point to assess the feasibility of the ‘enhanced environmental outcomes’ in schedule 5 of the Basin Plan (particularly with changes to the parameters of constraints‑easing measures), the absence of catchment‑specific water recovery targets, and the value for money of the overall program (PC 2018; chapter 5).

These concerns remain valid. Following the 2026 Basin Plan review, the feasibility and costs of recovering water in pursuit of the schedule 5 outcomes should be reassessed by the Australian Government.

|  | Finding 2.5  The costs of achieving the enhanced environmental outcomes (schedule 5 of the Basin Plan) through water recovery have risen substantially |
| --- | --- |
| The budget available under the Water for the Environment Special Account to recover the 450 GL/y will not be adequate to achieve the target, even with water purchases.  The 2026 Basin Plan review is an opportunity to assess how to cost‑effectively deliver the enhanced environmental outcomes that the 450 GL/y target is designed to meet. | |
|  | |

Implementing the new arrangement will require Basin governments to balance protecting taxpayers’ investment in the Plan and providing a degree of certainty to Basin communities about their futures. It is important for the Australian Government to operate transparently and credibly with Basin communities and industries as it undertakes further water recovery.

The Commission recommends that, in addition to the Restoring Our Rivers amendments:

* the Australian Government should withdraw unviable supply measures, but only after seeking advice from the BOC
* the Australian Government Minister for Water, through written direction to the departmental secretary, ensures that the new annual reporting:
  + includes progress on the northern Basin toolkit measures
  + outlines which supply, constraints‑easing and toolkit measure projects are still considered deliverable and represent value for money
  + provides guidance on the approach to addressing any shortfall against the supply measure offset.
* southern Basin governments withdraw all incomplete constraints‑easing projects from the supply measure package, and co‑develop a renewed implementation program following the MDBA roadmap
* the Australian Government’s renewed water recovery strategy includes gradually staged voluntary water purchases, coupled with a commitment from all Basin governments to assist communities, where warranted, to transition to a future with less available water.

### Clearer accountability for supply measure implementation

A mismatch of accountability and responsibility for supply measures can in part explain some of the limited progress on supply projects: the Australian Government is responsible for funding supply projects as part of its commitment to bridge the gap, but it has little control over project implementation beyond the conditions it places on Basin state governments via intergovernmental funding arrangements. In some cases, this has resulted in a stalemate – the Australian Government appears to have withheld funds from projects that cannot be delivered, but Basin states have been unwilling to amend or withdraw these projects from the supply package as that would confirm a water recovery shortfall.

In the interim report, the Commission recommended an amendment to the Basin Plan to require the Australian Government Minister for Water to withdraw a Commonwealth‑funded supply measure if the Minister considers that the measure will not enter into operation by the deadline in s. 7.12(6) of the Basin Plan (interim recommendation 2.1). This was designed to return decision‑making authority to the Australian Government, instead of the BOC. The Senate Committee report on the Restoring Our Rivers Bill agreed with this proposal and recommended it be formalised in legislation (Senate Environment and Communications Legislation Committee 2023b, pp. 27–28).

The Restoring Our Rivers Act has amended the Basin Plan to allow the Commonwealth to withdraw any supply measure notification, at any time, if it appears that the measure will not enter into operation by the end of 2026. This does not align with the Commission’s interim recommendation, which proposed that the Australian Government should be required to withdraw projects after certain conditions were met, and that the Australian Government should only be able to withdraw measures that are funded by the Commonwealth. This recommendation was intended to avoid any future stalemates where undeliverable projects remain in the supply measure package, provoking uncertainty.

The Australian Government should cease funding any supply measure that will not deliver the intended outcomes, or is no longer cost‑effective. However, before doing so, the Australian Government Minister for Water should seek advice from the BOC over options to amend, rescope or withdraw the project. This advice should be provided within three months of the request to avoid unnecessary delays. If funding is ceased, the measure should be withdrawn under s. 7.12(6) of the Basin Plan.

|  | Recommendation 2.1  The Australian Government should cease funding unviable supply measures |
| --- | --- |
| The Australian Government should cease funding any supply measure that is unlikely to deliver on its planned outcomes or is found not to be cost‑effective.  Before this decision is made, the Australian Government Minister for Water should seek the advice of the Basin Officials Committee. The advice should be provided within three months of the request, and could include a proposal to rescope the project and amend the notification to the Murray–Darling Basin Authority.  If funding is ceased, the measure should be withdrawn under s 7.12(6) of the Basin Plan. | |
|  | |

#### Annual reporting should include further information on government funding decisions

The Restoring Our Rivers Act amends the Water Act to require the Department to prepare an annual report on water recovery targets (s. 85AB). The report must outline activities undertaken to make progress on:

* increasing the volume of the Basin water resources that is available for environmental use by 450 GL/y
* Bridging the Gap water recovery targets
* SDL adjustment projects
* any other matter specified by the Minister in writing.

The report, which must also be tabled in Parliament, provides much‑needed transparency on Australian Government decision‑making, and should improve parliamentary accountability on how public funds are spent on Basin Plan implementation.

However, the report should also include the northern Basin toolkit measures, particularly Commonwealth‑funded measures that are delivered by the New South Wales and Queensland governments. These measures, and Australian Government funding decisions, risk being under‑scrutinised during the next phase of implementation if not covered by the annual reporting. By including the toolkit measures, and ensuring the MDBA reviews the outcomes of the measures in the 2026 Basin Plan Review, there is no need for an additional assurance mechanism as proposed in the interim report (interim recommendation 2.3).

The reporting on activities towards these targets should include assurances on the feasibility and value for money of all commitments made and activities undertaken. Likewise, any decisions to continue, amend or cease funding supply or constraints projects should be outlined in these reports.

Last, the reports should include an update on any expected shortfall against the supply measure offset, and planned actions to make good.

|  | Recommendation 2.2  Australian Government funding decisions should be publicly reported |
| --- | --- |
| The Australian Government Minister for Water should ensure that reports prepared under s. 85AB of the *Water Act 2007* (Cth) include:   * the northern Basin toolkit measures * statements on which supply, constraints‑easing and toolkit measure projects remain feasible and represent value for money, and which ones will no longer be funded * an update on any expected shortfall against the supply measure offset, and planned actions to make good. | |
|  | |

### Prioritise easing constraints and commit to procedural fairness

Constraints‑easing, if done effectively, provides opportunity to benefit a range of environmental sites in the Basin and to provide flexibility to river operators. Many inquiry participants pointed to constraints as an area where renewed focus is required to support environmental outcomes (box 2.3).[[29]](#footnote-30)

| Box 2.3 – Easing constraints – what participants said |
| --- |
| A broad range of participants highlighted the importance of progress constraints‑easing in the next phase of Basin Plan implementation. The Lifeblood Alliance, for example, said:  Environmental water needs to be able to get to the locations on the floodplain that need it most and to arrive downstream in sufficient volumes to flush salt out to sea and out of the system. … The removal of constraints to the delivery of environmental water is critical to the successful achievement of the Basin Plan, and have lasting private and public benefits, we have an obligation to maximise these benefits. (sub. 52, pp. 4–5)  Goulburn Valley Environmental Group noted that local environmental outcomes were improving, but were limited by the inability of environmental water holders to provide overbank flows:  We are confident of environmental improvement, but disappointed this has been limited by the Victorian government of flows to ‘in channel’ and denying fully utilising recovered water to maximise the improvements to the health of wetlands and low‑lying vegetation. (sub. 28, p. 2)  Renmark Irrigation Trust noted that ‘the benefit of the recovered water and any management of unregulated flows, cannot be maximised without the constraints on the River and floodplains being addressed’ (sub. 24, p. 5). And South Australian Murray Irrigators said:  It cannot be stressed stronger that constraints are the first actions that the government should take through all states to ensure that any water return volumes can be delivered if they can’t be delivered then their recovery is pointless and could cause devastation or floods and further cost local councils in infrastructure destruction. Addressing constraints is something that both sides of government have had the chance to implement and both sides of government have put it in the too hard basket and done little except study and review. Real action has not followed and should be a priority going forward. (sub. 96, p. 5)  Further upstream, the Murray River Group of Councils commented that:  … completion of the constraints relaxation projects is essential to the overall success of the Basin Plan … By reconnecting rivers to their floodplains more often and especially when operating in conjunction with the [Victorian Murray Floodplain Restoration Program] and other [SDL adjustment mechanism] projects, relaxing constraints would create real and significant benefits for the environment and will enable Basin Plan objectives to be met. (sub. 22, p. 10)  And the MDBA said:  It is the MDBA’s firm view that the constraints projects should remain a focus for delivery by all governments. They are complex and previous experience in constraint easing has shown they require time to properly engage with affected individuals and communities. However, they are essential to realising the full benefit of the investments which have been made to secure environmental water and to achieve the long‑term environmental outcomes sought by the Basin Plan. (sub. 61, p. 7) |
|  |

Constraints – whether operational or physical – limit the ability of environmental water managers to improve environmental outcomes in some wetlands and low‑lying floodplains. Under current rules, some of these areas may not receive environmental watering frequently enough to maintain ecological condition, which has a direct negative impact on the health of wetland plants, forests and woodlands, and on native fauna that rely on these for food or shelter. As connectivity between rivers and these wetlands decreases, so too does the scope for aquatic species to move between them, limiting both the availability of food for animals and nutrients for vegetation. There is also increased risk of blackwater events when water eventually reaches floodplains, as organic matter is not flushed frequently enough (CEWH, sub. 69, p. 20; MDBA 2013).

Improving environmental outcomes in the southern Basin is partly reliant on progress in easing constraints and adjusting operational rules to better deliver environmental outcomes, not just recovering water. As Environment Victoria put it:

… degradation isn’t the result of over-extraction alone. Instead, it is the result of the paradigm of ‘working rivers’ which repurposed rivers to make over-extraction possible, fundamentally altering patterns of flow. (sub. 99, p. 9)

As noted earlier, some of the environmental outcomes linked to the additional 450 GL/y also require constraints to be eased.[[30]](#footnote-31) But irrespective, easing constraints and enabling higher operational flow rates will allow the existing environmental water portfolio to be managed for greater environmental benefit (CEWH, sub. 69, p. 20). There is also evidence to suggest that, in response to community concerns, some constraints in the southern Basin have become more stringent since the Basin Plan modelling took place (MDBA 2020i, p. 32). This has further restricted the ability for environmental water holders to deliver water to environmental assets like floodplains.

Alongside other changes in water markets, constraints have also created increasingly ‘challenging delivery conditions for river operators’ (ACCC, sub. 26, p. 5), and limit the ability of river operators to meet consumptive demands along the system (Frontier Economics 2020, pp. 49–50).

Constraints‑easing projects have proved challenging for governments to implement. Although there are clear benefits, raising operational flow rates requires significant buy‑in from Basin communities, and must incorporate fair recourse to affected landholders. With most constraints‑easing projects needing at least another 5–10 years to implement, the program requires a dedicated, collaborative focus from Basin governments to set it up for success.

The Restoring Our Rivers Act directs the MDBA to develop a constraints implementation roadmap (complementary to the 2013 *Constraints Management Strategy*) by December 2024. This is an opportunity to establish a sound footing for constraints‑easing in the southern Basin. As put by Healthy Rivers Lower Murray:

A clear implementation plan is needed for Constraints projects, staged in incremental steps to start the process with small gains, to build community trust and to demonstrate that environmental flows are not the same as damaging flood flows (sub. 106, p. 2).

#### Remove constraints from the supply measures package and extend timeframes

As a first step, incomplete constraints‑easing projects should be removed from the supply measure package and implemented under a separate work program. Withdrawing constraints will allow for greater flexibility in delivery over a longer timeframe and could facilitate better engagement with affected landholders.

DCCEEW disagreed with the interim report recommendation to remove constraints from the supply measures package, arguing that ‘[retaining] the projects in the SDLAM program … provides a strong incentive for states to deliver against their constraints relaxation commitments and a suite of associated accountability measures’ (sub. 127, p. 10). This claim, however, does not acknowledge that including constraints in the supply measure package has not, to date, worked effectively as an incentive for Basin states.

Withdrawing constraints from the supply measure package will, in effect, confirm a shortfall at reconciliation – even though reconciliation has been delayed to 2026. But, because most constraints‑easing projects will not be completed by 2026 regardless, withdrawing constraints now will not meaningfully affect the shortfall that could emerge in 2026.

After the 2026 Basin Plan review, the Australian Government should assess the costs against the expected environmental and operational outcomes of further constraints easing. The Australian Government should consider allocating additional Water for the Environment Special Account funding towards constraints easing projects, if these are capable of delivering improved environmental outcomes from existing water holdings.

#### Consistent joint commitment to procedural fairness for landholders

One of the barriers to constraints‑easing is inadequate government engagement with the affected landholders, which according to one participant, generates a backlash of local opposition to ‘man‑made manipulated environmental flood flows’ (Beer, sub. 38, p. 2). Recent flooding events in the southern Basin also reinforced the concerns some floodplain landholders have about how high flow rates are managed and communicated by river operators (Central Murray Environmental Floodplains Group, sub. 6).

While there are legitimate concerns, in some cases, landholder objections can resemble a ‘holdout problem’, where the need for all affected parties to agree gives a small number of people an outsized ability to slow delivery of a project with community‑wide benefits. This is a key challenge where state governments have policies in place that ban involuntary flooding of private land in all circumstances (Victorian Government 1989, p. 457).

Ideally, all affected landholders should be afforded the same commitment to procedural fairness – especially for the River Murray constraints projects. This requires a joint strategy between the New South Wales and Victorian governments, supported by the Australian Government, which commits those states to a clear process over a long time period. The strategy should outline the ‘stages’ of landholder engagement and negotiation, clarifying opportunities for landholders to provide local input to the process. The strategy should also look to identify interactions with projects to improve disaster resilience and flood mitigation through the Basin, as part of flood reconstruction efforts.

Some participants called for compulsory acquisition of easements, at fair market value.[[31]](#footnote-32) This could be considered as a last resort where all other options are exhausted, and a standard of due process has been met by governments. Any compulsory acquisition by governments of an interest in private property, including an easement, would need to comply with relevant state laws. For example, the *Land Acquisition (Just Terms Compensation) Act 1991* (NSW) sets out rights to be given notice (usually at least 90 days), ‘just compensation’, and rights to appeal to the Land and Environment Court.

Importantly, any coordinated strategy should build on – not replace – the existing work done on the *NSW* *Reconnecting River Country* and *Victorian Constraints Measures* programs, both of which are currently inviting detailed property‑level input (NSW Government, sub. 43; Victorian Government, sub. 74).

DCCEEW submitted that the Australian Government ‘will engage an independent constraints facilitator to work with the states and communities to coordinate the roadmap and to ensure that better community and landholder consultation is undertaken’ (sub. 127, p. 7). If done effectively, this would address these cross‑jurisdictional issues.

#### Prioritise incremental improvements

The costs of delivering the flow rates planned under the *Constraints Management Strategy*, to both governments and landholders, are likely to have increased substantially and exceed the available budgets (WESA Review 2021, pp. 38–39). This does not mean the projects should be abandoned in their entirety. Rather, governments should instead find ways to prioritise incrementally higher flow rates in a gradual, iterative way, within the available funding, instead of retaining the ‘all‑or‑nothing’ mindset implicit in the 2013 strategy and constraints‑easing business cases.

The CEWH (sub. 69, p. 20) identified a range of ‘stepping‑stone’ projects that would ‘produce immediate benefits in terms of the ability of the CEWH to manage and deliver Commonwealth environmental water’. These priorities include restoring operating flows in the Murrumbidgee to the level already provided for in the water sharing plan, and specific improvements to environmental watering infrastructure. These types of incremental improvements can provide some catchment‑scale environmental benefits, even before other upstream and downstream constraints are eased.

No‑regrets projects should be prioritised. In the interim report, we took the position that River Murray constraints will be more complex to address, and that this should take place later in the sequence after lessons have been garnered from State implementation in the tributaries. Both the CEWH (sub. 116, p. 2) and DCCEEW (sub. 127, p. 10) disagreed with this analysis, noting that some activities could occur across multiple reaches in parallel. The Commission accepts that the detail of how projects are sequenced is a matter for the MDBA’s constraints implementation roadmap.

Depending on progress, the likely environmental outcomes, and the costs of achieving those, the Australian Government should consider further funding for constraints‑easing measures. In the near term, funding from the WESA could be reallocated towards constraints to provide funding certainty, in line with improved accountability on Australian Government funding decisions (discussed above).

|  | Recommendation 2.3  Reset and extend implementation of constraints‑easing projects |
| --- | --- |
| Basin governments should remove southern Basin constraints‑easing projects from the supply measure package.  The BasinPlan requires the Murray–Darling Basin Authority to develop a constraints‑easing implementation roadmap. This roadmap should include:   * pathways to incremental improvements in flow rates in each river, including evidence on the benefits of gradual increases in flow rates * a process to provide procedural fairness to affected landholders * a sequence for constraints‑easing projects.   Subject to making meaningful progress on incremental constraints easing, the Australian Government should assess the costs alongside the environmental and operational outcomes of further constraints easing, and consider allocating additional Water for the Environment Special Account funding towards constraints easing. | |
|  | |

### Renew the approach to water recovery

The Australian Government has now committed to a substantial water recovery task between now and 2027. The 2013 IGA includes a commitment from the Australian Government to prepare and review its water recovery strategy (ss. 3.1‑3.3).

A credible delivery pathway for water recovery over the next four years – including annual and catchment‑specific targets – is needed to provide certainty to Basin communities and water market participants, and to inform planning and investment decisions. Otherwise, the Australian Government risks being seen as just chasing a volumetric target, with no interest in the consequences or outcomes, or scrutiny on the costs.

A renewed strategy should:

* include all options, selected based on how cost‑effectively they meet water recovery targets
* ensure voluntary water purchases are gradually staged over time, and include guidance on annual targets
* outline a commitment to assist communities, where warranted, to transition to a future with less available water, and how this commitment will be met.

#### All options on the table, including a staged approach to voluntary water purchasing

Many inquiry participants argued for an immediate return to open tender water purchases, including towards the 450 GL/y.[[32]](#footnote-33) And others argued against them, largely in response to the perceived impact of previous rounds of water purchases on communities.[[33]](#footnote-34) Box 2.4 provides some of these perspectives. A limited survey also found general support among the broader Australian community for the reintroduction of buybacks (The Australia Institute 2023).

| Box 2.4 – What participants said about open tender water purchases |
| --- |
| In support of open tender water purchases, many participants emphasise their reliability and cost‑effectiveness compared to other options.  Recovering water for the environment through ‘buybacks’ is considerably less expensive than through irrigation efficiency upgrades … There would need to be compelling reasons to justify the additional public expense of efficiency measures. There are none. (EDO, sub. 91, attachment 1)  Open tender, voluntary water purchases must be resumed as a key cost-effective and transparent mechanism for meeting water recovery targets across the Basin. Reliance on infrastructure projects, both on and off farm, to recover water must be reduced, as these projects are high cost and low return in terms of environmental outcomes. (Lifeblood Alliance, sub. 52, p. 2)  Water buy‑backs from willing sellers needs to become more of a priority despite the push-back from big irrigation. Willing sellers are the most cost efficient and effective means to recover water for the environment. These buybacks will have the best value ROI of any planned recovery, far better than dubious water efficiency programs. (Trangie Local Aboriginal Land Council, sub. 40, p. 1)  … recovering water through irrigation infrastructure has cost Australian taxpayers 3.1 times more per ML than buying water back from willing irrigators. … Although both forms of water recovery have increased over time, irrigation infrastructure subsidies $/ML are significantly trending upwards at a faster rate. (Wheeler et.al., sub. 104, pp. 1–2)  Moira Shire Council observed the impacts of buybacks on the agricultural sector, including irrigation networks.  Water buybacks can have significant impacts on businesses in the region, particularly those reliant on irrigation. The reduced availability of irrigation water, especially during drought periods, can lead to a sharp decline in on‑farm production and a decreased demand for agriculture services. This can have severe consequences for the long‑term viability of irrigation industries and the irrigation infrastructure managed by Goulburn Murray Water within Moira Shire. Furthermore, the reduction in agricultural production may render some manufacturers economically unviable. (sub. 25, p. 2)  The Murray River Group of Councils pointed to the impacts on the wider community.  Buybacks damage communities. The evidence of this is not contestable. … many independent assessments and our own lived experience in our communities all clearly demonstrate that is not possible to recover water from the consumptive pool, either through buy backs or through on farm efficiency projects, without long term negative cumulative effects on people living in the Basin. (sub. 22, p. 11)  However, Beasley noted that many opponents of open tender purchases made assertions that were not supported by evidence.  Assertions have been made in the past (and are currently being made) that voluntary purchases of water for the environment (usually called “buy‑backs”) cause economic damage to rural or regional communities … These assertions are not fully supported by peer reviewed economic research or papers, or defensible economic reports. (sub. 47, p. 11)  Likewise, Environment Victoria noted:  … economists have pointed out that water buybacks have positive impacts on community spending and that government‑commissioned reports claiming a simplistic relationship between water use and farm production don’t hold true. (sub. 99, p. 14) |
|  |

The benefits, costs and broader impacts of different water recovery options are well‑established (ABARES 2020; Grafton and Wheeler 2018; PC 2010). Previous water recovery programs show that purchasing water is by far the quickest and most cost‑effective way for governments to obtain water entitlements for environmental use (Grafton and Wheeler 2018). By purchasing from willing sellers at market prices, direct water purchases protect property rights and encourage irrigators to adjust to a future with less water.

By contrast, recovering water through water‑use efficiency infrastructure projects, both on‑farm and off‑farm, are far more expensive on average. As of 2023, the average cost per ML/y of water recovery via water purchase, in 2022 dollars, sits at $2,808 compared to an average cost per ML/y via gap‑bridging irrigation infrastructure of $8,126 (Commission estimates based on Wheeler et al, sub. 104, p. 2).

Both on‑farm and off‑farm programs can have substantial unintended consequences (Wheeler et. Al., sub. 104, p. 3). For example, on‑farm water efficiency programs can have an outsized impact on water allocation market prices (ABARES 2020, p. 7). Although off‑farm projects do not have a similar impact on prices, there are fewer opportunities for these projects (ABARES 2020), while projects are becoming increasingly expensive (table 2.4).

Infrastructure projects can also delay – rather than prevent – farm‑level structural adjustment (PC 2018; appendix B). As Environment Victoria put it:

It is well‑documented that if investments do not meet basic cost‑benefit criteria for water saving, they delay the adjustment irrigation areas will inevitably face. In other words, they can lead to ‘gold plating’ assets that may subsequently become stranded while perpetuating a dependence on increasing external support – imposing substantial costs elsewhere. In effect, infrastructure investment may create an imperative to sustain the viability of those assets while perhaps neglecting more difficult, structural reforms. (sub. 99, p. 13)

However, the pace and location of previously large‑scale water purchasing programs has driven structural adjustment pressures that can be hard for smaller, irrigation‑dependent communities to adjust to (Sefton et al. 2020, p. 17). Rapid and uncoordinated water purchasing can also affect the viability of irrigation networks (National Irrigators Council, sub. 62, p. 6).

Some of the strengths of open‑market buybacks may not hold in the same way they used to, due to changes in southern Basin water markets since 2007. Previous buyback programs were able to recover water cost‑effectively because some farmers sold unused parts of their overall entitlements, while others sold out of necessity to restore cash flow (Wheeler and Cheesman 2013). With current water entitlement prices, it is unlikely that similar opportunities still exist – entitlement holders would already have had sufficient incentive to sell (NSW Farmers’ Association, sub. 123, pp. 10–11).

As discussed above, any future rapid water purchase program is likely to have significant impacts on water market prices, depending on both the rate of purchasing and the expectations set for market premiums. The speed of water recovery matters for socioeconomic outcomes. As put by the NSW Farmers’ Association:

The pace of change, in addition to the magnitude, has also been significant, with structural change occurring in the agricultural sector of the Basin at an alarming pace. There has not been enough support to assist communities in dealing with one of the largest reforms ever implemented in Australia. (sub. 123, p. 11)

Obtaining larger parcels of water may also require a greater reliance on land and water packages (Environment Victoria, sub. 99, p. 15), which may require direct negotiation but can contribute to broader environmental outcomes.

For these reasons, a sole reliance on large‑scale, rapid open‑tender water purchasing is not recommended. The Australian Government needs to operate a holistic program of gradual water recovery that considers all options on their merits, but maintains a primary focus on cost‑effectiveness.

Water infrastructure projects should remain part of the mix – albeit with better upfront and assessment monitoring of potential unintended consequences – but greater attention will need to be paid to rationalising irrigation network footprints. As Coleambally Irrigation Co‑operative Limited submitted:

The Basin Plan reduces the volume in the consumptive pool without addressing the irrigation footprint. In fact, policy settings encourage ‘green field’ irrigation developments or enable increased water use (on‑farm irrigation efficiency) which combine to increase the pressure on access to remaining volumes in the consumptive pool, causing increased annual allocation and water entitlement prices. … The Basin Plan and associated instruments … act to diminish the [irrigation infrastructure operator’s] capacity to adjust to the Basin Plan and a reduction in the consumptive pool, with the responsibility for maintaining the shared infrastructure left with remaining irrigators. (sub. 21, p. 9)

While off‑farm water infrastructure projects are generally the most expensive form of recovery, implementing water purchase programs in concert with a reduction in irrigation network footprints can lessen the impact on irrigation network viability. Reduced overall irrigation demand will also help balance supply and demand in the water market, and reduce the price impacts of environmental water recovery overall.

#### Coupling water recovery with community transition assistance

Purchasing water entitlements from willing sellers, and maintaining the integrity of property rights, compensates individual farmers as they reduce or cease irrigation. During the period when water recovery under the Basin Plan occurred, agricultural production rose overall: the real gross value of irrigated agricultural production (GVIAP) in the Basin increased by about 12% between 2013 and 2018[[34]](#footnote-35), despite the volume of water used in irrigation declining by over 16% over the same period (ABARES 2021).

However, past implementation shows that the cumulative impact of multiple willing sellers can create flow‑on pressure at the local scale for some Basin communities. Research indicates that larger diverse towns have adapted to the resulting reduced irrigation better than smaller remote communities with many larger towns seeing irrigated agriculture increase over the life of the Basin Plan (Sefton et al. 2020). Smaller, more remote communities that are highly dependent on irrigation, and are often already facing negative socioeconomic trajectories, have additional difficulty adjusting to the reduced water availability from water purchases (Sefton et al. 2020, p. 22).

Many of the affected communities are also adjusting to a changing climate, which is reducing the levels and reliability of Basin stream flows alongside increased frequency and severity of floods and droughts (chapter 6), as well as a broad swathe of short and long‑term environmental, social and economic changes, including reduced agricultural labour needs and a highly‑developed water market.

Attributing past water purchases as the cause of all negative socioeconomic impacts on Basin communities is not supported by the evidence. But conversely, the position that there has been no net economic impact from water purchases ignores the distributional impacts of water recovery (driven by the operation of the water market) for different Basin communities, and does not acknowledge the additional impact of water recovery on top of rapid structural changes occurring in some communities.

Future water recovery should occur alongside a clear commitment from Basin governments to assist communities, where necessary and warranted, to transition to a future with less certain water availability.

Water recovery decisions need to have regard to comprehensive and credible socioeconomic information, and some participants raised concerns with the quality of existing monitoring and modelling of socioeconomic impacts (Wheeler et. Al., sub. 104, pp. 3–5). The Australian Government’s water recovery strategy should incorporate socioeconomic monitoring that identifies the likely adjustment pressures exacerbated by specific purchases or projects, and their cumulative impact, to inform more effective targeting of transitional assistance. This will also provide greater transparency on the expected socioeconomic impacts of Basin Plan water recovery, compared to other drivers of change.

Assessments of the socioeconomic impacts of water purchasing programs are often contentious. One way of potentially addressing this problem is to establish a shared process, encompassing: preparing terms of reference for socioeconomic analyses, selecting the consultants, and reviewing draft reports. Under a shared process, decisions on each of these steps could be made by a working group comprising officials from the Australian and relevant Basin state governments, alongside representatives of First Nations, environmental, irrigator, farming and Basin community interests. The working group could also assist the development of associated assistance programs. A shared, formal process can be an effective way of giving socioeconomic impact and assistance work greater credibility and legitimacy across different interest groups.

This type of shared process was established by New South Wales as part of developing the first water sharing plans in the early 2000s. Because these plans involved significant reductions to water availability, concerns over the socioeconomic impacts of these reductions created hostility. As part of this process, community advisory committees were given control over socioeconomic assessment options, including the choice of different impact management strategies (PC 2003, pp. 35–36). The shared process brought stakeholders together with a common responsibility which required constructive engagement across diverse interests.

##### Community transition assistance program design

Good program design – coupled with careful targeting of assistance to communities in high need and regular program evaluation – is crucial to making a meaningful difference to long‑term community outcomes (and providing value for money to taxpayers).

However, designing and implementing effective adjustment programs for regional communities experiencing structural change is notoriously difficult. There are very few examples of successful adjustment programs, both in the Basin and across the Australian economy. Some participants pointed to the Victorian Government’s establishment of a coordinating Latrobe Valley Authority to assist that region’s transition away from coal mining, and compared that to the types of support (and funding) provided to Basin communities. The Committee for Greater Shepparton observed that:

… government support to the Latrobe Valley in response to the Hazelwood Power Station closure is approximately ten times that provided to [Goulburn Murray Irrigation District] communities in response to direct job losses associated with the implementation of the Basin Plan (sub. 80, p. 11)

Any future Basin adjustment programs should have clear, bespoke objectives and leverage existing regional development frameworks where possible. But the difficulty delivering successful economic adjustment programs also underscores the need for a robust monitoring, evaluation, reporting and program improvement framework, to assess whether funding is delivering on objectives and identify where improvements could be made (PC 2017). Program design must also learn from the lessons of previous adjustment programs in the Basin (box 2.5). Involving affected community members in the development of adjustment assistance programs can be an effective way of giving voice to stakeholders, and building a sense of ownership and trust in the program.

Based on the evidence on the effectiveness of past programs, a well‑designed assistance program:

* leverages the existing competitive strengths of the region (PC 2017, p. 22)
* is well‑integrated with prevailing regional development strategies and frameworks (PC 2017, p. 209)
* builds on and enhances private sector investment in the community (Mouque 2012, p. 2)
* has a robust monitoring, evaluation, reporting and improvement framework (PC 2017, p. 152) .

| Box 2.5 – Some lessons from recent adjustment programs |
| --- |
| Basin governments have implemented multiple economic transition and adjustment programs in the Basin during the period of Basin Plan implementation. The most recent example is the Australian Government’s *Murray–Darling Basin Economic Development Program* (MDBEDP).  Most projects funded to date under the MDBEDP are tourism projects, including parks and walking trails. Funding has also been provided to help local governments encourage professionals to relocate to their area, improve local health amenities, and develop cultural and arts centres. Examples of projects funded under the program include:   * $617,950 for Yarrawonga to Burramine Cycling and Walking Trail in Moira Shire * $600,000 for St George CBD Upgrades and Beautification – Victoria Street * $250,000 for Water Reservoirs and Public Area Murals in Warren Shire Council * $100,000 for Tatura Library Redevelopment Fit Out in Kyabram‑Tatura.   The objective of the MDBEDP is to fund community economic development programs, supported by selection criteria and an evaluation strategy for funded projects. However, several participants questioned how well this type of program targeted communities most in need. Inland Rivers Network, for example, said:  … funding programs aimed at assisting impacted communities have been very poorly targeted with no transparency or reporting on benefits of the investment. Many were treated as pork‑barrelling exercises and did not go to the areas that needed the most support. (sub. 82, p. 4)  Evaluation is critical to understanding whether programs are achieving their objectives, benefiting the intended beneficiaries, and providing value for money to taxpayers. To date, there has been no extensive program evaluation across the 132 MDBEDP projects on achieving the goal of economic development. It is also not clear how many of the beautification and walking trails projects align with an objective of economic development.  The lack of evaluation makes it difficult to know the benefits and cost‑effectiveness of adjustment assistance programs, or to glean lessons and insights for future assistance programs. This can add to community scepticism about whether Basin communities are benefiting from adjustment assistance. The Victorian Farmers Federation argued that ‘there have been no true programs that have assisted rural communities adjust to less water’ (sub. 34, p. 8).  Sources: DCCEEW (2022a), MDBA (2016a, 2017a), Sefton et al. (2020). |

|  | Finding 2.6  Adjustment assistance should draw on local strengths and be closely monitored for effectiveness |
| --- | --- |
| Basin Plan implementation has taken place during a period of socioeconomic change in the Murray–Darling Basin. Reduced water availability under the Basin Plan has had relatively small impacts on aggregate socioeconomic outcomes in the Basin, compared to other drivers of change – including climate variability and reduced on‑farm labour. However, water purchases have contributed to adjustment pressures in some Basin communities, especially smaller and more remote irrigation‑dependent communities.  Adjustment assistance can help communities better adapt to structural change, but designing a program that generates demonstrable and lasting economic benefits is not easy. Evaluation of adjustment assistance is not generally done well, but the available evidence suggests assistance is typically more effective where it leverages the competitive strengths of the local community and is well‑integrated with prevailing regional development strategies and frameworks. Ongoing monitoring and adaptation of adjustment programs is crucial for success. | |
|  | |

#### An updated water recovery strategy

The Australian Government should update its water recovery strategy to provide clear guidance to markets, industry participants and community members on how water recovery will proceed over the next phase of Basin Plan implementation. The Commission’s 2018 advice (recommendation 5.2) remains relevant and should also be adopted.

The strategy should outline how water recovery will be staged over time to lessen market impacts and enable community adjustment, including approximate annual water recovery targets. This will provide guidance for water market participants and some confidence to Basin communities that the speed of water recovery will be realistic and not excessively disruptive.

The water recovery strategy should also include:

* a commitment to all available water recovery options, including community and industry developed proposals, with projects prioritised based on availability, their cost‑effectiveness and likely socioeconomic outcomes
* clear guidance on the priorities of different water recovery targets, including addressing the possible supply measure shortfall and aligning water recovery with progress in constraints easing
* socioeconomic monitoring and interface with community adjustment programs
* commitments and mechanisms to ensure transparency and community engagement
* monitoring, evaluation, reporting and improvement.

|  | Recommendation 2.4  Develop a renewed approach to water recovery |
| --- | --- |
| Given the substantial water recovery task, the Australian Government should develop and implement – without delay – a renewed approach to water recovery.  This approach should consider all water recovery options, including voluntary water purchases. Any purchasing should be undertaken gradually, to avoid driving water market disruption and community adjustment pressures. Water purchases should also be coordinated with irrigation network rationalisation where necessary to avoid impacts on irrigation network viability.  The Australian Government should update and publish its water recovery strategy to clarify how this renewed water recovery program will proceed. The strategy should outline:   * the sequencing of different water recovery targets (both the 450 GL/y and any expected 605 GL/y shortfall), based on the progress of supply and constraints measure implementation * how different water recovery options will be used, based on the availability of projects, their cost‑effectiveness and likely socioeconomic impact * when and how community adjustment programs will be implemented, based on socioeconomic monitoring * requirements for monitoring, evaluation, reporting and improvement on adjustment program design. | |
|  | |

#### Is there a role for the risk assignment provisions of the Water Act?

The Water Act also provides a method to compensate entitlement holders for any reductions in entitlement reliability as a result of the Act. This is done through a cost‑sharing formula between the Australian Government and the relevant State, subject to Australian Government guidelines, under a process known as risk assignment (DAWE 2020).

Some participants suggested that not using administrative reductions to recover water was a missed opportunity (for example, Newman, sub. 114). The risk assignment provisions provide a method of last resort: if there are too few willing sellers, and no cost‑effective water‑use efficiency projects, the relevant state governments can elect to reduce entitlement reliability through administrative means, and compensate entitlement holders at market rates for the reduced value of their property right. The Queensland Government recently did this on a small scale in the Condamine‑Balonne groundwater zone as part of meeting water recovery targets (section 2.2).

Triggering risk assignment is an expensive and controversial approach, and may not be consistent with the Australian Government’s commitments under the 2013 IGA. In addition, administrative reductions can be an economically inefficient way to return water to the environment, as it may undermine confidence in the property right a water entitlement provides (PC 2010, p. 120). Administrative reductions could be expected to also affect entitlements held by the CEWH, reducing their contribution to the Bridging the Gap target and potentially requiring even *more* water recovery to meet the SDLs.[[35]](#footnote-36) The provisions should only be used on a limited basis as a last resort.

#### Could an alternative delivery model improve the efficiency of water recovery?

With a substantial water recovery task ahead, there are sound reasons for the Australian Government to ensure the delivery model is fit for purpose.

Inquiry participants – largely representing the irrigation sector – highlighted shortcomings in the existing delivery model across multiple elements of resetting the balance. The National Irrigators’ Council, for example, called for:

Basin Governments to evaluate not only the timelines, but the project delivery model for these infrastructure projects. This model from approvals, to budget, to time to build, should be assessed to see if they are the most appropriate way to manage these large projects. (sub. 62, p. 12)

Murray Irrigation (sub. 65, p. 14) called for a review of the delivery model to develop ‘a more cost and time‑effective project delivery partnership model with the MDB‑States and with the entities delivering projects’, while CICL (sub. 21, p. 3) noted the inflexibility in the current model, as government programs are unable to consider projects that have elements of both supply and efficiency measures. Murray Irrigation further noted the ‘gradual degrading of effort, and it seems capacity, to deliver complex water management projects in the supply works, constraints and policy reform of the system’ (sub. 118, p. 2).

Participants also raised issues with the quality of engagement by DCCEEW. Gwydir Valley Irrigators Association, for example, said:

The recent consultation on the buy-back tenders their [the Department’s] engagement and consultation was deplorable and disrespectful to the communities in which they were trying to engage and communicate with. (sub. 89, p. 16)

Murrumbidgee Irrigation (sub. 73, p. 3) pointed to the previous Water for Rivers model as an example of a previous ‘highly successful’ approach to water recovery (box 2.6).

| Box 2.6 – Water for Rivers joint government enterprise |
| --- |
| In the 1990s, community concerns over deteriorating environmental outcomes in the Snowy River, a consequence of flows diverted for the Snowy Mountain Scheme, led to a negotiation between the NSW, Victorian and Australian governments on how to best return water to the Snowy. The governments agreed to establish a joint government enterprise in December 2003, trading as Water for Rivers, to return average flows of 212 GL/y to the Snowy River and 70 GL/y to the River Murray (Australian Government et al. 2002; s. 10-13).  Water for Rivers had the objective of funding water savings and purchasing entitlements, as well as commissioning environmental and riverine works nominated by the joint governments (s. 10.3). Draft business plans, which included proposals to undertake water projects and directly purchase entitlements, were submitted to joint governments for approval, requiring information on the likely third‑party impacts of any project (s. 13.1). The deed also outlined limits to entity operations, including a requirement to prioritise water efficiency projects over purchase, and ensure least‑cost projects are pursued (s. 13.2).  Water for Rivers was a small, expertise‑based public corporate entity, based in Albury NSW. In contrast to some recent infrastructure programs, projects funded by Water for Rivers included network rationalisation to reduce network footprints and transmission costs network viability, as well as a commitment to cost recovery (Water for Rivers 2010, pp. 9–12).  Previous Commission research noted the effectiveness of this model, noting that ‘this institutional arrangement can improve the independence of water recovery, lower its administrative costs, and allows flexibility and innovation in the approach to the water recovery task’ (PC 2010, p. 292).  Water for Rivers was wound up in 2013, ten years after being established, having recovered 90 GL/y for the River Murray and 121 GL/y to the Snowy River (MDBA 2017c). |
|  |

##### A government‑owned corporate entity to deliver water recovery projects?

In our interim report, we considered the merits of a new corporate Commonwealth entity responsible for water recovery, and sought views on this mode.

Some participants supported the idea in principle.[[36]](#footnote-37) Healthy Rivers Lower Murray (sub. 106, p. 3) noted the benefits of separating water recovery from other government agencies, and increasing the transparency of water recovery and accounting. The NSW Irrigators’ Council (sub. 110, p. 3) and the NSW Farmers’ Association (sub. 123, p. 4) likewise noted the value of independence, which could help overcome the ‘trust deficit’ within Basin communities and provide greater opportunities for local industries and communities to provide input into water recovery decisions.

Murray Irrigation said:

… the Basin Plan should begin to better reflect principles and a focus on supporting and facilitating outcomes at a local level, while providing appropriate integrity mechanisms rather than attempting to manage resources and processes through administrative mechanisms from Canberra.

The aim of the entity should be to enable open and transparent exploration of ideas on a no prejudice basis and refer proposals and/or businesses cases for an investment decision, with an appropriate recommendation to the funding decision maker. (sub. 118, pp. 3- 5)

However, many participants did not support the idea, pointing to the time it would take to establish relative to the deadlines included in the amended Basin Plan (Ricegrowers’ Association of Australia, sub. 105, Inland Rivers Network, sub. 109, Lifeblood Alliance, sub. 119). Others pointed to the large number of government entities already involved in Basin Plan implementation. And NSW Farmers’ Association questioned:

… whether there lies the need to create a whole new entity, when so much bureaucracy exists already within the delivery of the Basin Plan … We question whether the process to establish, build trust in, and begin operations of the new entity will take time that is just not available. (sub. 123, p. 4)

The National Irrigators Council (sub. 130, p. 11) noted the need to rethink the delivery model considering ‘poor implementation by Governments’ and the need for greater flexibility, but also viewed that ‘this must be done in the context of the likely time constraints and risks to Basin communities’. Campaspe Shire Council (sub. 115, p. 8) also argued that ‘the main problems with implementation are not related to acting nimbly or procurement’ and disagreed that a new entity was needed.

The Victorian Government agreed that there are ‘concerns about the performance of the Commonwealth department in the area of water’ (sub. 131, p. 2), but said a new corporate agency is not necessarily the solution.

##### Future institutional design principles

Given a longer implementation period, the benefits of establishing a new commercially‑focused entity could outweigh the set‑up costs through more streamlined project administration. However, on balance, the new timeframes set out in the Restoring Our Rivers Act do not provide an opportunity to establish a new water recovery entity and give it an opportunity to build credibility. Another institution involved in Basin water management is also difficult to justify at this time. If it becomes apparent that the amended water recovery timeframes will not be met, the case for establishing a dedicated entity could be reconsidered.

Institutional design remains important for effective and efficient water recovery, and many inquiry participants highlighted important principles for governments to consider in future recovery programs. Characteristics of an effective water recovery institution should include:

* Independence: the ability to depoliticise project administration and decision making
* Collaboration: ability to work on the ground with proponents and streamline project development and approval
* Trust and credibility: having a clear mandate, and adequate expertise, would provide greater clarity to Basin communities.

|  | Finding 2.7  Effective institutional arrangements are central to efficient water recovery |
| --- | --- |
| A corporate Commonwealth water recovery entity operating at arms lengths from governments could offer several advantages over current institutional arrangements for effective and efficient water recovery. Characteristics of an effective dedicated water recovery entity would include:   * Independence: the ability to depoliticise project administration and decision making. * Collaboration: the ability to work on the ground with proponents and streamline project development. * Trust and credibility: having a clear mandate and the flexibility to engage expertise as needed would provide greater clarity and confidence to Basin communities.   However, there is not enough time to establish and realise the benefits of a new corporate water recovery entity within the amended Basin Plan timeframes. If it becomes apparent that the amended water recovery timeframes will not be met, the case for establishing such an entity could be reconsidered. | |
|  | |

# Environmental water planning and management

|  |  |
| --- | --- |
| Key points | |
|  | Significant progress has been made implementing the Environmental Watering Plan over the past five years. Key planning and implementation frameworks are now finalised.  Long‑term watering plans are in place in all Basin states.  Pre‑requisite policy measures are in effect.  There is now a Northern Basin Environmental Watering Group.  In 2021, the Murray Lower Darling Rivers Indigenous Nations joined the Southern Connected Basin Environmental Watering Committee as an advisory member. |
|  | Providing and managing water for the environment is resulting in environmental benefits. Since 2009, over 15,000 gigalitres of Commonwealth environmental water has been delivered to the Murray–Darling Basin. This has supported increased connectivity; improved native vegetation and wetland conditions; the protection of hundreds of species of waterbirds, native fish, frogs and plants (including 45 threatened and endangered species); and the migration and breeding of native fish, frogs and waterbirds. |
|  | But there is more to achieve. Stopping and reversing long‑term declines in native fish and waterbird populations requires sustained effort. Environmental outcomes fall short of the outcomes that could have been achieved had more progress been made on constraints‑easing and supply measures. Rivers are not regularly connecting to key wetlands on the floodplain, there are too many cease‑to‑flow events in the northern Basin, and at the end of the system, flow targets are not consistently being met. |
|  | The reform focus for environmental management is now on simplifying and embedding current best practice approaches into the Environmental Management Framework.  The Basin‑Wide Environmental Watering Strategy needs to adapt to remain relevant. It should include clear guidance, under all water availability scenarios, on the priority for achieving flow connectivity at the system scale relative to watering within an individual water resource plan area.  Basin annual environmental watering priorities are general in nature, do not change significantly on an annual basis, and provide limited value in prioritising environmental water use. The 2026 review of the Basin Plan should assess the value of Basin annual environmental watering priorities and whether requirements for annual priorities should be amended or removed.  First Nations peoples’ objectives and outcomes for providing shared benefits from environmental water use, under all water availability scenarios, should be included in the Basin‑Wide Environmental Watering Strategy and long‑term watering plans. |

Sustaining the health of the Basin’s water‑dependent ecosystems – impacted by historical over allocation and overuse of water in the Murray–Darling Basin – is being addressed under the Basin Plan’s arrangements for planned and held environmental water.[[37]](#footnote-38) Environmental water is critical to supporting the health of rivers and wetlands and it provides benefits to the communities and First Nations people that rely on the rivers and wetlands. Connectivity is the foundation of river health – flows that connect rivers to floodplains support nutrient cycling, replenish refuge pools and wetlands to maintain water quality, and activate movement and breeding of native fish and waterbirds. Environmental water management aims to restore more natural flow regimes to rivers, creeks and wetlands.

This chapter assesses the effectiveness of environmental water planning and management. Features of the Environmental Watering Plan (chapter 8 of the Basin Plan) are set out in section 3.1 and section 3.2 looks at the management of environmental water holdings. Section 3.3 evaluates progress implementing the Environmental Watering Plan since 2018. The assessment looks at the implementation of the Basin Plan’s requirements for environmental water planning and management, including long‑term and annual planning, coordination, shared benefits of environmental water and the integration of environmental water and natural resource management. Section 3.4 discusses opportunities for improvement in each of these areas.

The completion of water recovery under the Basin Plan and progressing constraints‑easing on river operations will also have a significant impact on achieving the Basin Plan’s objectives for the environment (chapter 2). Monitoring outcomes, regular reporting and evaluation of environmental water planning and management are essential to assessing progress against the objectives of the Basin Plan and improving adaptive management and decision making (chapters 6 and 9).

## 3.1 About the Environmental Watering Plan


The Basin Plan provides a framework for prioritising, planning and using water for the environment. The Environmental Watering Plan sets out objectives, targets and annual and multi‑year planning activities (figure 3.1). It also prescribes activities to maximise environmental benefits including coordination, using local knowledge and experience, having regard to Indigenous values and social and economic outcomes and strategies to deal with a variable and changing climate.

The Environmental Watering Plan is a central part of the Basin Plan. It seeks to achieve the best possible environmental outcomes using the water made available for the environment by the Basin Plan. The three overarching environmental management objectives for the water‑dependent ecosystems of the   
Murray–Darling Basin are to:

* protect and restore water‑dependent ecosystems of the Murray–Darling Basin
* protect and restore the ecosystem functions of water‑dependent ecosystems
* ensure that water‑dependent ecosystems are resilient to climate change and other risks and threats.[[38]](#footnote-39)

Figure 3.1 – The Environmental Watering Plan

Chapter 8 of the Murray–Darling Basin Plan



The Environmental Watering Plan includes the Environmental Management Framework which sets out requirements to guide the long‑term and annual planning of environmental water. Key outputs of the Environmental Management Framework include:

* **The Basin‑Wide Environmental Watering Strategy** (BWEWS). The BWEWS sets out the long‑term watering plan including the expected improvements resulting from environmental water on river flows and connectivity, native vegetation, waterbirds and native fish. Its purpose is to explain the context within which the Basin annual environmental watering priorities will be set, identify Basin‑wide environmental watering priorities over the long term, coordinate the management of environmental water and guide the development of consistent long‑term environmental watering plans.
* **Long‑term environmental watering plans** (LTWPs). These plans provide details on the magnitude, nature and location of the priorities for environmental water to guide environmental watering at a catchment scale. They must identify priority environmental assets and ecosystem functions in the water resource plan (WRP) area, ecological objectives and ecological targets for those assets and functions, and environmental watering requirements to meet those targets.
* **Basin annual environmental watering priorities** (Basin AEWPs). Basin AEWPs identify watering priorities at the Basin scale. They may identify priority environmental assets and priority ecosystem functions that have Basin‑scale significance for environmental watering during that water accounting period, priority environmental assets and priority ecosystem functions whose environmental watering during the period will require complex arrangements, and any potential for synergies in environmental watering activities.
* **State annual environmental watering priorities** (State AEWPs). These outline priorities for the watering of environmental assets and ecosystem functions within each catchment. State AEWPs must identify the assumptions on which the priorities were based, and possible co‑operative arrangements between holders of held environmental water, managers of planned environmental water, and owners or managers of environmental assets.

The Environmental Watering Plan also specifies the principles to be applied, and the principles and method to be used, to determine the priorities for applying environmental water. And there are intermediate targets and longer‑term targets for maintaining flows, river condition, hydrological connectivity and water‑dependent species such as vegetation, birds and fish. The targets are used to measure progress towards achieving the environmental objectives in the Basin Plan (figure 3.1).

## 3.2 Held environmental water is being actively managed by environmental water holders

Water recovery is the means by which the Sustainable Diversion Limits are achieved. Water entitlements are transferred from consumptive use to the held water portfolio of environmental water holders to be actively managed to achieve the environmental objectives of the Basin Plan.

Environmental water holdings are the same types of entitlements held by other water users. Environmental water holders can use, trade or carryover each parcel of water based on the best use for the environment. The main environmental water holder in the Basin is the Commonwealth Environmental Water Holder (CEWH). Some Basin state governments (the New South Wales, Victorian and South Australian governments) also own entitlements to water for the environment (figure 3.2).

There has been very little change in water recovery since 2018 (chapter 2). And as highlighted in figure 3.3, there are significant differences in the volume of allocations and water delivered between drought   
(2017–2020) and wet (2021–2023) years.

Carryover allows water entitlement holders to retain the unused portion of their water allocation from one year so that it can be used in subsequent years and is available to consumptive water users and environmental water holders in most regulated systems. It allows all entitlement holders to flexibly manage their water availability between seasons to help meet discrepancies between water supply and demand in wet years versus dry years (PC 2021c, supporting paper C, p. 37). The CEWH uses about 70% of its annual allocation each year on average, and carries over about 30% of allocations (CEWH, sub. 69, p. 9).

Trade in environmental water allocations can provide opportunities for environmental water holders to manage low flows as well as to top‑up medium flood events for the benefit of water‑dependent ecosystems. Trade can help maximise environmental benefits by putting environmental water to better use in different locations or at a later time, to better match the hydrographs of environmental needs. It allows for increased flexibility and reduced risk by better aligning seasonal water resource variability with needs (PC 2021, supporting paper C, p. 38).

Figure 3.2 – Held environmental water entitlements in the Basin by ownera

As at 30 June 2022

This column chart presents the volume of held water entitlements in the Murray-Darling Basin. The unit of measurement is gigalitres per year that factors in long term diversion limit equivalence factors. The data includes 1949 GL held by the Commonwealth Environmental Water Holder, 533 GL held by NSW Government agencies, 485 GL held by the Victorian Environmental Water Holder, 86 GL held by the SA Minister for Water and the River Murray and 1 GL held by private organisations.

**a.** The Living Murray water portfolio is part of state government entitlements included in the chart data. The Living Murray portfolio is managed by the MDBA to give effect to joint government decisions. The jointly held entitlements consist of 489 GL/y owned by: VEWH (223.5 GL/y), New South Wales government agencies (223.1 GL/y) and the South Australian Minister for Water and the River Murray (42.5 GL/y). The CEWH holds environmental water entitlements in all Basin states except the ACT. All held environmental water in Queensland is owned and managed by the CEWH. **b.** GL/y: gigalitres per year, LTDLE: Long‑term diversion limit equivalence factors (estimates of the actual long‑term use associated with water entitlements, that allow comparison between entitlements on a consistent basis).

Source: MDBA (sub. 61, response to information request, pp. 9–10).

Figure 3.3 – Commonwealth environmental water availability and use

This time series column chart presents annual data on the Commonwealth Environmental Water Holder’s allocation of water, water that is carried over and water that is delivered to achieve environmental outcomes, between 2012-13 and 2022-23. The gigalitres of water availability and use was highest between 2021 and 2023 and lowest between 2017 and 2020.

Source: DCCEEW (2023c).

The CEWH has not traded (bought or sold) environmental water allocations since the Commission’s assessment in 2018. However, the Victorian Environmental Water Holder (VEWH) has traded environmental water allocations on seven occasions since December 2018. The purchase of allocations was used to meet environmental watering shortfalls and revenue raised from the sale of environmental water allocations was used to improve the management of environmental water and outcomes for the environment such as the development of watering and monitoring plans, research and the construction of fishways (Victorian Government, response to information request, sub. 74, p. 18).

There is an accountability obligation on environmental water holders to achieve the best outcomes that they can with the water resources they steward. To maximise environmental outcomes, it is important that environmental water holders actively trade water allocations and carry forward revenues. However, decisions to sell environmental water allocations can be contentious, particularly during periods of water scarcity and when significant public investment has been used to procure entitlements. Under the *National Water Initiative*, governments agreed that water for the environment held as an access entitlement may be traded on the temporary market, ‘when not required to meet the environmental and other public benefit outcomes sought and provided such trading is not in conflict with those outcomes’ (COAG 2004, paragraph 35).

This limit (on trade) is about ensuring trading arrangements are consistent with the use of the water for environmental purposes, and are not primarily about raising revenue. But, the concern is that environmental water holders may fail to maximise environmental and community benefits by trading too little. It is important that over time, the CEWH and other environmental water holders fully utilise trade in allocations to maximise benefits for the environment (PC 2021c, supporting paper C, p. 38).

The CEWH reported that it is investigating options to streamline its trading process and improve its responsiveness to market conditions (sub. 69, p. 9).

## 3.3 Looking back: 2019 to 2023

### Significant progress implementing the Environmental Watering Plan

Significant progress has been made since 2018 implementing the Environmental Watering Plan. Key planning and implementation frameworks are now finalised.

#### Long‑term watering plans are now in place

In 2020, LTWPs for all surface water WRP areas were in operation. The Environmental Management Framework is now fully implemented (section 3.4).

#### Pre‑requisite policy measures were in effect within the timeline

Pre‑requisite policy measures (PPMs), referred to as ‘unimplemented policy measures’ in the Basin Plan[[39]](#footnote-40), are operating rules which enable more efficient use of held environmental water in the southern Basin. PPMs provide:

* credit for return flows from environmental watering events for environmental use downstream (rather than being used to supply the demands of other users)
* the ability for environmental water holders to order water from a specific storage to top up or ‘piggy back’ on naturally occurring high flow events (PC 2018, p. 25).

In its 2018 assessment, the Commission discussed the importance of PPMs being implemented on time. On 1 July 2019, PPMs to support the efficient use of environmental water were deemed to be in effect by the Murray–Darling Basin Authority (MDBA). This was in line with the timeline in the Basin Plan. The Independent River Operations Review Group conducted a review of the MDBA’s assessment to ensure that the criteria was consistently applied and robust and evidence‑based conclusions were reached. The findings supported the MDBA’s assessment process and the conclusion that the measures are in effect in all relevant jurisdictions (MDBA 2020f).

In 2021, the Environmental Water Protection Strategy and Implementation Plan were developed by the MDBA in collaboration with the states, the Commonwealth, and the Commonwealth Environmental Water Office and endorsed at the Basin Officials Committee (BOC). The implementation plan underpins environmental water protection improvements across the Murray–Darling Basin, to strengthen collaboration on the operating arrangements for environmental water (MDBA, sub. 61, response to information request, p. 16).

Despite progress, water for the environment is still not protected throughout the entire river system. For example, the NSW Government has established rules to protect Commonwealth environmental water that is released from northern tributaries to Menindee Lakes. However, as environmental water enters Menindee Lakes it is no longer recognised as environmental water. As discussed by the CEWH, accounting and protecting water through Menindee Lakes, would increase environmental flows into the southern Basin and maximise the outcomes of water recovered in the northern Basin (sub. 69, p. 21).

#### An Environmental Watering Group to coordinate connected watering events in the northern Basin

In 2018 the Commission recommended establishing a northern Basin environmental watering committee as an intergovernmental mechanism for planning and coordinating environmental watering events in the northern Basin (PC 2018, p. 290). The Northern Basin Environmental Watering Group (NBEWG) was established in 2019 to coordinate planning and the delivery of water for the environment across the northern Basin to enhance connectivity using cross‑border and multi‑catchment coordination. The NBEWG’s other roles and responsibilities include:

* supporting event‑based delivery of water for the environment
* improving communication and reporting about the benefits of water for the environment
* developing strategies to support community engagement, including with First Nations people, irrigators and other stakeholders
* holding an annual planning meeting for environmental water holders and river operators
* ensuring First Nations peoples’ values are consistently considered in environmental water planning (MDBA 2023h).

The NBEWG includes representatives from the New South Wales and Queensland governments, and the Australian Government, including the MDBA, the CEWH and the Australian Government Department of Climate Change, Energy, the Environment and Water. Representatives from the South Australian and Victorian governments attend the group’s meetings as observers. In 2023, the NBEWG terms of reference were reviewed and updated to include membership for two First Nations people in an advisory role (MDBA, sub. 61, p. 23). NBEWG communiques are published on the Australian Government Department of Climate Change, Energy, the Environment and Water website (DCCEEW 2022b).

#### First Nations representatives provide input on the Southern Connected Basin Environmental Watering Committee

In 2021, the Murray Lower Darling Rivers Indigenous Nations (MLDRIN) joined the Southern Connected Basin Environmental Watering Committee (SCBEWC) as an advisory member to support consideration of First Nations peoples’ knowledges and values and the outcomes from environmental watering activities that Aboriginal people want. Collaboration between First Nations people and environmental water holders on environmental water decision making is discussed in section 3.4.

### Outcomes from providing and managing environmental water

Providing and managing water for the environment, both planned and held, is a major reform that has provided environmental benefits, particularly at the local scale. The MDBA described environmental water planning and management as ‘a clear success and arrangements are world leading’ (sub. 61, p. 13). Some of the benefits include: improved native vegetation and wetland condition; protection of rare and threatened biodiversity and the migration and breeding of native fish, frogs and waterbirds.

The State of the Environment Report found that that the use of environmental water recovered under the Basin Plan, is restoring the health of rivers and wetlands and mitigating fish deaths and algal blooms (DCCEEW 2021a). The National Irrigators Council also noted that ‘over the last couple of years, the CEWH has delivered bird and fish breeding events throughout the Basin and that should be celebrated’ (sub. 62, p. 21). And Murray Irrigation Limited spoke about changing attitudes towards environmental watering since the Basin Plan commenced.

… customers have developed very different and more positive views in regard to successful watering of wetlands than was the case even 15 years ago. There is overwhelming support for the use of the company’s operational staff working with environmental agencies to utilise the network to deliver environmental water into the multiple creeks and streams that transect their properties to create healthier creeks and the growing number of significant wetlands located on private property. e.g. the planned wetting and drying of the large network of Murray and Edwards anabranch creeks and streams. (sub. 65, p. 11)

#### Benefits from environmental water through extreme dry and floods

The environmental benefits derived from environmental water are challenging to quantify. However, benefits from the use of environmental water are evident, particularly at the local scale. Participants pointed to the benefits of environmental water during prolonged dry periods. The CEWH, for example, said:

In extremely dry years (2017–20), Commonwealth environmental water played a pivotal role in breaking cease‑to‑flow events, maintaining flows to enable fish breeding and waterhole replenishment, as well as supporting core riparian and wetland habitat to promote a quick recovery of ecosystems once conditions improved. (sub. 69, p. 7)

Key outcomes from the use of Commonwealth environmental water are summarised in box 3.1.

During droughts, environmental water has helped to avoid environmental decline. For example, water delivered for the environment to support the Coorong, Lower Lakes and Murray Mouth during the recent drought prevented environmental degradation of the extent observed during the Millennium Drought (MDBA 2020h, p. xiii).

| Box 3.1 – Outcomes from the use of Commonwealth environmental water |
| --- |
| Since 2009, 15,000 gigalitres of Commonwealth environmental water has been delivered to rivers, wetlands and floodplains of the Murray–Darling Basin. This has supported:   * more than 22,000 kilometres of waterways (the same distance as driving around Australia twice) * more than 370,000 hectares of lakes, wetlands, estuaries and floodplains * 10 Ramsar wetlands that have been recognised internationally for their ecological importance * hundreds of species of waterbirds, native fish and plants, including threatened species such as silver perch, Murray cod and Murray hardyhead * the flushing of more than 3.3 million tonnes of salt through the barrages.   The significance of Commonwealth environmental water is most apparent at the end of systems in dry years – the Barwon‑Darling in the northern Basin and the Lower Murray in the southern Basin. Between 2014 and 2021 Commonwealth environmental water:   * supported a 10% increase in flows in the Barwon‑Darling River in 5 out of the 7 years * supported a 30% increase in flows in the Murray River in 3 out of the 7 years * accounted for 100% of flows into the Coorong in 3 out of the 7 years.   Flows into the Coorong contribute to flushing salt from the Basin, maintaining healthy salinity levels in the Coorong, and maintaining connection between the river and the Coorong to facilitate fish movement. Although barrage releases did not meet the target of greater than 2000 GL/year (3‑year rolling average) between 2014 and 2021 environmental water ensured that 2‑year minimum flows did not fall below 600 GL (a minimum flow target to be achieved 100% of the time). Without Commonwealth water, in only 1 out of the 7 years would barrage flows have been more than 650 GL/year (a minimum flow target to be met in 95% of years). With Commonwealth water, this flow target was met 6 out of the 7 years.  During the 2017–2020 drought, Commonwealth environmental water use in the northern Basin:   * played a vital role in breaking cease‑to‑flow periods in a number of valleys. For example, the Barwon‑Darling at Walgett experienced five cease‑to‑flow events from 2017–2020, the longest was 328 days. Without the use of Commonwealth and New South Wales environmental water, it is estimated that this cease‑to‑flow period would have totalled 666 days * maintained flows to enable fish breeding and waterhole replenishment, as well as core riparian and wetland habitat to provide a quick recovery when ecosystem conditions improved.   Since 2014, 45 threatened and endangered species have benefited from environmental water including:   * the establishment of new populations of Murray hardyhead * southern bell frog recruitment in the Murrumbidgee and Mid and Lower Murray River valleys * 36 waterbird species of conservation significance which included providing habitat in the Barmah‑Millewa Forest for up to 25% of the threatened Australasian bittern population * aromatic peppercress, found at monitoring sites in the Lachlan River for the first time in 2020‑21.   Source: CEWH (sub. 69, pp. 1–15). |
|  |

Similarly, in the western region of Victoria, the VEWH reported:

The diligent use of the water for the environment entitlement over the last four dry years has helped to prevent extensive drying of rivers, hyper‑saline conditions and widespread fish deaths – such as those in the Wimmera and Glenelg systems during the Millennium Drought. (VEWH 2022, p. 10)

During the drought, sites that received environmental water had critical ecosystem functions protected. Some of the benefits of environmental water can be attributed to planned and held environmental water maintaining habitats and river connectivity. Providing refuges was important for maintaining breeding grounds during drought and targeting threatened species. For example, the delivery of water for Murray hardyhead was viewed as particularly important, as reduced natural flows were a key threat to their recovery (Victorian Government, sub. 74, p. 4).

Differences in outcomes can be seen between sites that are prioritised for environmental water and those that are not, highlighting the benefits of environmental water and the importance of sound prioritisation settings. The ACT Government, for example, commented that:

In 2019, environmental flows between Bendora and Cotter Dams supported a large breeding event of the Blackfish that is highly significant following the population decline that resulted from the 2020 bushfires. Blackfish populations above Corin Dam, without environmental flows, have not recovered from the bushfires and remain at risk. (sub. 85, response to information request, p. 5)

Environmental watering can have benefits beyond individual wetlands and river reaches. For example, governments are increasingly forming partnerships with First Nations people to improve the delivery of environmental outcomes and to deliver, where possible, Aboriginal peoples’ preferred outcomes from environmental water management (section 3.4).

After the three years of above average warm and dry conditions to early 2020, many areas of the Basin experienced a turnaround from drought conditions to flooding. During the summer and autumn of 2021 to 2022, the northern Basin experienced the largest natural flows in more than 10 years, improving connectivity across the Basin and filling storages. The South Australian Government reported that planned environmental water:

… in the form of unregulated flows has been critical in inundating vast areas of floodplain and wetland habitat that has not received water for many years, supporting native fish recruitment and survival, substantially freshening the CLLMM [Coorong, Lower Lakes and Murray Mouth], as well as enabling various more local scale environmental water operations. (pers. comm., 25 September 2023)

In wetter catchments across the Basin, there were positive responses to high inflows including waterbird breeding at key sites, vegetation growth and recruitment of native fish (MDBA 2022e, p. 4). For example, the NSW Government reported the most extensive colonial waterbird breeding events in more than a decade.

At least 14 waterbird species established more than 80 individual breeding colonies, with more than 250,000 nests across 6 major wetland complexes in the Macquarie, Narran, Gwydir, Lachlan, Lowbidgee and mid‑Murray. (NSW DPE 2022c)

After flood events, water for the environment can provide a crucial role for ‘topping up wetlands’ when, after high inflows water recedes quickly, before birds have completed their breeding cycles. For example, in Dharriwaa (Narran Lakes) in 2022, to mitigate the risk of breeding birds abandoning their nests, the CEWH established a grant program to purchase water from on‑farm storages on the Narran River to maintain water levels (DCCEEW 2022d). At the Ramsar‑listed Hattah Lakes, environmental watering combined with natural floods also resulted in a significant increase in waterbird breeding.

Monitoring after environmental watering in late 2021 found 1900 nests and more than 6500 chicks of colonial nesting waterbird species as well as 800 chicks of other waterbird species such as grebe and duck. Three threatened species were also recorded as breeding, including blue‑billed duck, musk duck and white‑bellied sea‑eagle.

During 2022 flooding, monitoring detected 10 species of colonial nesting waterbird species using 7000 nests for over 25,500 chicks, with a further 18 water bird species detected breeding for an additional 1700 chicks. (Victorian Government, sub. 74, p. 4)

Inquiry participants also reported improved environmental outcomes in the lower Murray (South Australia) from environmental water and recent floods – for example, River Lakes and Coorong Action Group (sub. 15, pp. 5–6) and Healthy Rivers Lower Murray (sub. 37, p. 3).

Following the floods, the delivery of water for the environment played a critical role improving water quality, and mitigating the impacts of low dissolved oxygen levels. Water for the environment was used in the Edward–Kolety Wakool, Lower Darling (Baaka) and Murrumbidgee rivers to help native fish survive low‑oxygen water conditions caused by natural flooding. Environmental water was also delivered in the Murray Valley to help fish migration and bird breeding at Barmah–Millewa Forest (an internationally important Ramsar site) (MDBA 2023a, pp. 16–17).

#### There are positive outcomes but more to achieve

The CEWH, while acknowledging the positive outcomes and achievements from the use of environmental water, highlighted why there is still more to do.

Waterbird populations have experienced long term declines over the past 40 years, while native fish populations have declined by 90 per cent over the past 150 years – arresting and reversing these declines requires long term and sustained action.

Due to operational and physical constraints, rivers are not regularly connecting to key wetlands on the floodplain including in the Gwydir, Lower Darling Baaka, mid Murrumbidgee, Goulburn, mid Murray (including Werai Forest) and Lower Murray valleys. In some cases, even delivering elevated in channel environmental flows is restricted.

In the northern Basin, there are still far too many cease to flow events, which compromises recovery of rivers and their dependent communities.

At the end of the system, flow targets to ensure salt is flushed from the system and healthy salt levels are maintained in the internationally significant Coorong, are not consistently being met. (sub. 69, pp. 1–2)

Concerns were also raised by other participants on environmental water and river health (box 3.2).

Responding to concerns about river health, the CEWH noted that:

Issues such as increased carp numbers, hypoxic events, tree health degradation and bank erosion are typically a result of a long history of river regulation and not environmental water management. In fact, in many cases, environmental water is helping to reduce bank erosion and declining tree health and mitigate the impacts of poor water quality. (sub. 116, p. 3)

| Box 3.2 – Participants’ concerns about environmental management and river health |
| --- |
| Speak Up  Increased carp breeding events, increased hypoxic blackwater events, increased native fish deaths have consistently been reported since implementation of environmental watering events  The Barmah choke has lost 25% capacity since implementation of the Basin Plan.  There are serious local concerns about the degradation of forest health and loss of trees at sites that are repeatedly subject to environmental watering programs, along with rising water table concerns …  And despite over a decade of implementation, fish kills in the Darling still shock the nation … (sub. 2, p. 3)  Riverina and Murray Joint Organisation  The [Barmah] Choke’s current capacity of 7000ML/day has been steadily diminished (historically 10 400ML/day) by high sustained flows, causing erosion and bank slumping. The reduction in the Choke has resulted in overbank flows and unseasonal flooding events that incur greater conveyance losses and push volumes of water through other waterways or overland. This has ultimately have given rise to irreversible environmental degradation nearby. (sub. 58, p. 14)  Jodie Hay  Environmental watering demands has resulted in constant high flow occurring in the Gunbower Creek which has resulted in unprecedented erosion of the Gunbower Creek banks especially upstream of the Hipwell Rd Regulator in the locally known Narrows … This bank erosion has caused the loss of the nesting environment for the platypus and kingfishers. (sub. 63, p. 5)  Friends of the Merbein Common  The greatest expectation of the MDB Plan was for the rejuvenation of the Murray Darling Flood Plains with Environmental Flows. This has been the greatest disappointment. The management of Environmental Allocations to benefit the environment has been too conservative, too timid and failed community expectations. (sub. 8, p. 1)  Gingham Lower Gwydir landholders  Environmental water allocations, intended to maintain ecosystem health and restore the water dependent habitats for migratory bird breading events always seem to come at a cost to the local landholder who are in our view part of the environment and have been so well before water regulation began. (sub. 23, p. 1)  Upper Murrumbidgee Catchment Network  The environmental outcomes set out in the Basin‑wide Environmental Watering Strategy (BWS) cannot be achieved in the Upper Murrumbidgee River for:  a. Connectivity, including for base‑flow and fresh targets.  b. Native fish, with one example being the objective for “no loss of native fish species currently present within the Basin.” … (sub. 140, p. 2) |
|  |

The CEWH further commented that water quality ‘is a shared responsibility for all water users, including water managers and river operators’. If water quality issues are the sole responsibility of environmental water holders it would compromise the outcomes that can be achieved with environmental water (CEWH, sub. 116, p. 4). Similarly, environmental water should not be expected to be available to respond to emergency situations including the provision of critical human water needs (chapter 7).

Completing water recovery under the Basin Plan and easing constraints on river operations will have an impact on achieving the Basin Plan’s objectives for the environment. Water delivery arrangements in the Murray–Darling Basin were established before held environmental water became a substantial component of water in the system. While water delivery arrangements have evolved under the Basin Plan, they reflect a system that is largely designed to support the delivery of consumptive water. And as the CEWH said:

‘Retrofitting’ environmental water planning and delivery onto this consumption‑driven framework has its limitations. (sub. 69, p. 19)

To make best use of water recovered for the environment, there is a need to change river operating rules and practices. This includes relaxing constraints, increasing connectivity along rivers, upgrading or removing infrastructure (weirs, regulators, pumps, fishways) and implementing the Northern Basin Toolkit (chapter 2; CEWH, sub. 69, p. 19).

The variability in climate and environmental conditions over the last five years is evidence of the challenges faced by environmental water managers to deliver environmental outcomes. It is also a reminder that providing and effectively managing environmental water is critical to managing the Basin’s water‑dependent ecosystems so they can better deal with drought, flood events and adapt to a more variable and dryer climate.

Environmental water is in high demand, supply is limited and decisions about priorities are required, particularly during drought. During droughts, ecological health, water availability and water quality depend on more than the actions of environmental water holders. There was evidence of significant ecological decline in some Basin waterways during the 2018–2020 drought. There was also the significant fish death events from low flows that occurred in the Darling River near Menindee between December 2018 and January 2019. Commenting on the latest drought, CEWH said:

The 2017–2020 drought was the worst on record for the northern Basin. It was characterised by extended cease to flow periods, well in excess of ecological tolerances and significantly worse than those experienced during the Millennium Drought. Towns went without access to fresh drinking water, large scale fish deaths occurred, permanent waterholes dried up and local ecological assets moved to critical need. The numerous cease to flow periods were only broken during this time with water for the environment. (sub. 69, p. 4)

The wetter conditions in 2022‑23 provided a reset for many of the Basin’s water‑dependent ecosystems. However, two wet years are not enough to turnaround decades of environmental degradation from historical over‑allocation and overuse of water in the Basin. Predictions of a warmer, drier future, with more frequent droughts and extreme weather events (MDBA, sub. 61, p. 2), emphasise the importance of effective environmental planning and management.

And not all Basin catchments benefited from wetter conditions in 2022‑23. Flooding in parts of the Basin impacted communities and the environment. Low oxygen levels (caused by flooding induced blackwater events and high temperatures) resulted in millions of fish deaths at Menindee in February 2023 (chapter 7). Some areas of the southern Basin also remained relatively dry and water has not reached some parts of floodplains where there are species struggling to recover from drought (MDBA 2022e, p. 4).

## 3.4 Effectiveness of environmental water planning and management

It is important to reflect on the lessons learnt during the challenges of the last five years and concerns expressed by participants (box 3.2) and look at where environmental water management policy and frameworks can be improved. The factors we considered when assessing the effectiveness of the implementation of the Basin Plan’s requirements for environmental water planning and management and opportunities for improvements included:

* the long‑term planning frameworks for achieving environmental objectives through environmental watering, including the effectiveness of the BWEWS and LTWPs
* the annual planning and management of environmental water, including the effectiveness of Basin AEWPs and State AEWPs (and whether Basin AEWPs should be retained)
* the coordination and engagement undertaken by environmental water holders
* maximising the shared benefits of environmental water, with a particular focus on outcomes for First Nations people
* natural resource management: while sitting alongside the Basin Plan, natural resource management is important to maximise the benefits of environmental water and ensure outcomes from environmental water delivery and management are not eroded by other pressures such as invasive and pest species.

The recommendations outlined in this chapter seek to improve current environmental watering planning frameworks, including governance arrangements and practices. Key considerations include improving the accountability of environmental water managers to deliver the environmental outcomes of the Basin Plan through more effective planning, and increasing collaboration with First Nations people on environmental water decisions that impact them.

### Long‑term planning

#### Updates to the Basin‑Wide Environmental Watering Strategy are required

Under the Basin Plan,[[40]](#footnote-41) the MDBA is required to prepare a BWEWS that:

* outlines the expected detailed long‑term outcomes from environmental watering for priority rivers, wetlands and key ecosystem components and functions
* explains the context within which annual environmental watering priorities will be developed
* helps to coordinate the management of environmental water at the Basin scale by setting policies and principles for prioritising the use of environmental water under different climate scenarios.

In 2018, the Commission found that, while the 2014 BWEWS had provided a strategic foundation for environmental water planning and informed portfolio planning and watering decisions, it did not provide clear guidance on how to prioritise the assets or types of watering events that were most important for achieving the Basin Plan objectives and outcomes. We also noted that the BWEWS would need to build on learnings and incorporate new knowledge to be effective (PC 2018, p. 278).

The BWEWS is reviewed every five years. The first review in 2019 led to some common sense updates to contemporise the strategy, largely reflecting policy changes and new scientific knowledge. The updated strategy had an additional objective to ‘maximise environmental outcomes through effective and efficient environmental water management’[[41]](#footnote-42) and the refinement of water management strategies to promote collaboration between water managers (MDBA 2019c, p. 1).

The BWEWS review signalled that a second update to the BWEWS in 2022 would include the material changes identified in the BWEWS 2019 review. The changes were to be informed by a MDBA work program, to be established in collaboration with First Nations people, Basin governments and environmental water managers (MDBA 2019c, p. 2), to investigate:

* First Nations peoples’ objectives and outcomes for the shared benefits of environmental water
* water management strategies to improve flow coordination
* the best possible environmental outcomes from environmental watering while investigating opportunities to improve social and economic outcomes
* improved SMARTness (including specificity, measurability and achievability) of expected environmental outcomes and better links to Basin Plan objectives
* additional environmental themes where it could be demonstrated that they add value to Basin‑wide environmental watering (including ecosystem functions)
* assessing climate risks to the expected environmental outcomes and water management strategies (MDBA 2020d, pp. 88–94).

However, the updates were not made in 2022. The MDBA fulfilled the requirement to review and update the BWEWS in 2019, but the opportunity to implement more important reforms was missed (such as the inclusion of an objective for shared benefits from environmental water, incorporating First Nations peoples’ values and uses, and climate adaptation). The third edition of the BWEWS is due to be published in November 2024 (MDBA, sub. 126, p. 3). The MDBA has initiated a work program for this update and established a working group with representatives from the CEWH and Basin states to oversee the development of the next BWEWS (sub. 61, response to information request, p. 11).

Inquiry participants pointed to areas for improvement and argued the BWEWS could be a more effective tool for guiding environmental water decision‑making. For example, the Victorian Government said that:

More work is needed to make the objectives and targets in the BWS more specific and to also point to the combination of sites or assets that need to be managed to achieve the overarching objectives. (response to information request, sub. 74, p. 13).

A number of participants expressed concern about the lost focus on connectivity at the whole of Basin scale and called for the next iteration of the BWEWS to prioritise connectivity. For example, the ACT Government said that ‘environmental water planning is yet to transition from sub‑catchment, catchment and state‑based management to basin‑scale and in the national interest’ (sub. 85 p. 6). The Nature Conservation Council also commented generally on the importance of connectivity.

Connectivity is critical. Flows that connect rivers to each other and break their banks onto floodplains support nutrient cycling. Such flows replenish refuge pools and wetlands to maintain water quality, and trigger movement and breeding of native fish and waterbirds. (sub. 50, p. 7)

The MDBA is currently working with research partners on a Basin‑wide conservation prioritisation framework to identify places of high conservation value and to prioritise management actions to conserve their critical assets, values and functions. With an expected completion date of mid‑2025, the framework will not be included in the 2024 BWEWS. However, it will inform the review of the Environmental Watering Plan to be conducted as part of the 2026 Basin Plan Review and future versions of the BWEWS (MDBA, sub. 126, p. 3). The development of this framework and the inclusion of priority management actions for the conservation of key Basin environmental assets in the BWEWS has the potential to provide greater direction to, and accountability for, the CEWH’s management of environmental water.

To increase its relevance and effectiveness, the BWEWS also needs to:

* provide guidance, under all water availability scenarios, on the priority for achieving flow connectivity at the system scale relative to watering within a WRP area. By better articulating the relative priorities in connected systems, the BWEWS would provide increased direction, accountability and transparency about priorities at the whole‑of‑Basin scale
* identify risks to achieving environmental objectives in a changing and more variable climate, which is expected to increasingly influence the degree to which environmental outcomes are achieved (chapter 6) (MDBA 2020d, p. 94).

#### Long‑term watering plans are an important component of the framework

In accordance with the Basin Plan,[[42]](#footnote-43) Basin states have prepared a LTWP for each surface water WRP area. An update has been completed for LTWPs in Victoria, Queensland and South Australia. LTWPs detail the magnitude, nature and location of the priorities for environmental water to guide environmental watering at a catchment scale. They can be informed by long‑term plans for individual assets, often as a requirement of State legislation or policy. LTWPs are required to:

* be consistent with the BWEWS
* set out the long‑term objectives for the use of environmental water
* identify local priority environmental assets and ecosystem functions
* provide details of the watering requirements needed to meet the corresponding ecological targets in the Basin Plan (PC 2018, p. 276).

During consultations, the Commission heard that the implementation of LTWPs has been highly successful. LTWPs are an important component of the Environmental Management Framework because they are undertaken at the catchment scale and are both a top‑down and bottom‑up mechanism. They facilitate local input into environmental water planning activities and the prioritisation of assets within a catchment. LTWPs have improved the setting of State AEWPs and provided valuable information to the CEWH on the investment and use of its holdings to support environmental assets.

However, the MDBA Review of the Environmental Watering Plan (2021e) reported that some LTWPs do not draw sufficiently on ecological information when defining Priority Environmental Assets and Priority Ecosystem Functions. This information is important to determine environmental watering requirements. The review recommended that the MDBA continue to provide advice and support to Basin state governments as needed to update and review LTWPs and include sufficient ecological information for Priority Environmental Assets and Priority Ecosystem Functions (MDBA 2021e, p. 17).

LTWPs are improved and adapted through a process of revision. LTWPs must be updated every five years, or earlier, to align with when the BWEWS is updated.[[43]](#footnote-44) They must also be updated if a WRP is accredited or amended.[[44]](#footnote-45) Key changes made to LTWPs as Basin states have completed updates in 2020–2022 include:

* improved articulation of target and objectives for water‑dependent ecosystems
* improved description of the duration, frequency, depth and timing of environmental watering requirements
* improved co‑operative arrangements
* updated lists of priority environmental assets and functions
* better alignment with the Basin Plan
* increased information included from State water planning instruments
* improved consideration of First Nations involvement in planning
* incorporation of updates on constraint management and complementary actions
* improved articulation of risks (MDBA, sub. 61, response to information request, p. 11).

The MDBA provides advice to Basin states to assist them updating their LTWPs. The MDBA will look at how guidance on preparing LTWPs can be improved in the next update of the BWEWS and the next Basin Plan review (MDBA, sub. 61. p. 41). The MDBA has an interjurisdictional working group to support the update of the BWEWS, which includes those with responsibility for updating LTWPs in each Basin state to ensure alignment (Victorian Government, sub. 74, response to information request, p. 10).

### Annual planning

The Environmental Management Framework[[45]](#footnote-46) sets out requirements for the annual planning of environmental watering to guide the decisions of environmental water holders. The MDBA is required to identify annual environmental watering priorities at the Basin scale (Basin AEWPs) and Basin states are required to identify annual environmental watering priorities at the local level (State AEWPs).

#### State annual environmental watering priorities are effective

The Basin Plan[[46]](#footnote-47) requires State AEWPs for each surface water WRP area for the purpose of guiding the annual planning, prioritisation, and use of environmental water at the catchment scale. State AEWPs must have regard to the BWEWS and relevant LTWPs, and outline priorities for environmental watering within each catchment. The MDBA requires the state AEWPs by 31 May each year (unless otherwise agreed). While not a statutory requirement, the CEWH also prepares an annual water management plan to inform decisions on where and when to deliver water to benefit the environment (DCCEEW 2023j).

Priorities for environmental water must consider a variety of local factors, such as cultural value, feasibility, watering history and trade‑offs and are developed through a process of adaptive management. The Victorian Government said that the key changes to Victoria’s AEWPs since 2018 include:

* refinement of watering actions for environmental assets in partnership with Catchment Management Authorities (CMAs), key delivery partners and stakeholders
* improved assessment and recognition of First Nations peoples’ priorities and outcomes, and social benefits
* commencement in 2022‑23 of increased First Nations peoples’ self‑determination under Victoria’s Water is Life: Traditional Owner Access to Water Roadmap (sub. 74, response to information request, p. 11).

Priorities for environmental water vary under different seasonal conditions. In wet conditions the objective is to reconnect rivers to floodplains and wetlands and enhance recruitment of key species. During dry seasons, the priority is instead to protect at‑risk environmental values and avoid critical loss. The NSW Government said:

During dry conditions and drought, priorities for water delivery to environmental assets change. Some sites will end up going dry. This is natural for waterways that have natural wetting and drying phases. Water delivery is prioritised to maintain minimum flow rates and inundation to sites that are identified as critical drought refuges. (sub. 43, response to information request, p. 10)

In 2018, the Commission heard that ‘State AEWPs were fundamental for articulating what is needed at the local level on an annual timeframe. State AEWPs are used as a basis for priority‑setting and coordination in the southern Basin, and also assist in informing the CEWH’s environmental water portfolio plans’ (PC 2018, p. 285).

On this inquiry, we heard that a key value of the state annual prioritisation process is the regular, focused community engagement it facilitates and that State AEWPs support robust planning and decision‑making for environmental water, with clear linkages to the BWEWS, LTWPs, and Basin Plan.

The Commission is not recommending any changes to State AEWPs.

#### Basin annual environmental watering priorities are redundant

The MDBA collaborates with the Australian Government and state environmental water managers to prepare Basin AEWPs. The stated purpose of Basin AEWPs is to identify watering priorities that give effect to the BWEWS.[[47]](#footnote-48) That is, to help water managers make decisions about delivering environmental water and guide better outcomes at the Basin scale. The priorities consider recent seasonal conditions, past outcomes of watering actions, likely water availability and each state’s watering priorities. They are guided by the objectives of the BWEWS. The Basin AEWPs are formed at a mix of geographic scales from site‑specific to Basin‑wide, reflecting the ecology of species that are the focus of the strategy (MDBA, sub. 61, response to information request, p. 12).

In 2018, the Commission found that the Basin AEWPs were:

* released too late to be considered by environmental water managers in their planning processes
* more of a check‑list than a tool to direct environmental watering decisions
* becoming increasingly redundant as significant environmental water holders were moving to rolling multi‑year plans.

We recommended that, as part of the 2020 review of the Environmental Watering Plan, the MDBA should examine the usefulness of Basin AEWPs and whether the Basin Plan requirements for these annual priorities should be amended or removed (PC 2018, pp. 286–287).

From the 2018‑19 water year, the MDBA changed the approach to Basin AEWPs, by developing ‘rolling multi‑year watering priorities’ that spanned multiple years under differing water resource availability scenarios (MDBA 2018a, p. 3). These multi‑year priorities work together with the annual priorities and are guided by the BWEWS.

The effectiveness of this new approach was considered in the 2020 review of the Environmental Watering Plan. The review found that the principles and method for determining environmental watering priorities were ‘fairly or extremely appropriate’. However, an exception was the Basin AEWPs, which practitioners and advocates deemed to be ‘not at all’ or only ‘slightly effective’. The review recommended that the MDBA continue to change the approach to the Basin AEWPs and promote a culture of learning and adaptation (MDBA 2021e, pp. 7, 13).

In 2023, the method for determining Basin AEWPs was improved by new analysis of waterbird and vegetation vulnerability (CEWH 2023). Key findings of this analysis have been used in Basin AEWPs for native vegetation and waterbirds in the 2023‑24 water year (MDBA, sub. 61, response to information request, p. 12).

Despite these improvements, the Commission heard that AEWPs remain ineffective, with timing a particular issue. The link between Basin AEWPs and the BWEWS is also not clear and the mechanisms in the Environmental Management Framework need to work better together. The South Australian Government, for example, said:

There is limited formal interaction or connection between State and Basin‑wide annual watering priorities. Basin‑wide annual watering priorities are generally broad in nature and typically overlap with state priorities. Most practical annual planning is undertaken in advance of Basin‑wide annual watering priorities being developed. SA would like to see improved connections with Basin‑wide priority planning, regular basin‑scale measurement and assessment of ecological condition (e.g. birds, fish, vegetation). (pers. comm., 25 September 2023)

MLDRIN raised issues about how First Nations peoples’ values and uses of environmental water are included in Basin AEWPs.

… it is not clear how the MDBA is having regard to Indigenous values and Indigenous uses in the preparation of the annual priorities, as required by the Basin Plan. The current 2023‑24 Basin annual environmental watering priorities document includes only a high‑level description of engagement and research activities with Basin Nations. Basin Nations input is not reflected in the substantive annual or rolling priorities … While MLDRIN has had some discussions with the CEWH and MDBA about supporting Basin Nations input to the Basin‑wide Watering Strategy review, it is unclear how this would support direct input to the priorities. (sub. 92, p. 21)

And the Victorian Government argued that ‘there is a great opportunity’ to strengthen the AEWPs.

First, by reviewing the extent to which environmental watering in the preceding 1‑2 years have met expected requirements for Basin Wide outcomes and highlighting areas and watering actions that have not been delivered as required and therefore may need additional attention in the coming year. Second, by using an objective assessment of condition and risk across the basin to identify specific watering actions and issues that need to be addressed in particular parts of the basin. (sub. 74, response to information request, p. 12)

The Basin Plan Environmental Management Framework would benefit from simplification. And in practice, in their current form, Basin AEWPs are redundant. The priorities are general in nature, do not change significantly on an annual basis, and provide limited utility in prioritising environmental water use. The Basin AEWPs are released too late to be useful in the planning process for environmental water managers.

The following mechanisms in the Environmental Framework are sufficient to ensure that environmental water planning is efficient and effective.

* The BWEWS sets the long‑term environmental watering priorities at the Basin scale.
* LTWPs draw together local, First Nations peoples’ and scientific knowledges to guide the management of water for the environment over the longer term.
* State AEWPs set the rolling multi‑year and annual priorities at the local scale, are developed to be consistent with the BWEWS, and are informed at the local level.
* Environmental water holders coordinate through the NBEWG and SCBEWC, which allows for trade‑offs and prioritisation at the connected‑system scale.

To simplify the environmental watering planning process and remove unnecessary administration, the Basin Plan requirement for the MDBA to produce annual watering priorities should be reviewed.

### Coordination and engagement by environmental water holders

Environmental water management requires effective collaboration and coordination in the delivery of environmental water. And a range of people and organisations are involved, including environmental water holders, state and territory government agencies, community stakeholders, Traditional Owners and river operators.

The planning mechanism for coordination in the Basin is the BWEWS. Coordination across water holders has significantly increased and become more sophisticated and collaborative over the past five years, with environmental watering committees now operating in both the northern Basin (NBEWG) and southern connected Basin (SCBEWC).

The NSW Government commented that ‘the influence of the Basin Plan Framework for improved coordination of environmental watering events is evident in recent connectivity and fish flow events in the northern Basin and piggybacking and return flows accounting in multi‑site events in the southern Basin’ (sub. 43, p. 12). The MDBA reported that:

Since 2018, environmental water management across the southern connected Basin has evolved from largely site‑based with occasional multi‑site watering to now include large‑scale coordinated watering events to improve downstream and system‑wide connectivity outcomes (southern spring flow). The number, scale, ambition, efficiency, and most importantly outcomes of coordinated watering events have significantly increased over the last five years. (sub. 61, response to information request, p. 16)

Coordination of environmental water delivery is important for delivering environmental outcomes in both dry and wet seasons (box 3.3).

Participants told the Commission that SCBEWC and NBEWG are important to enable effective coordination of environmental watering and are on the whole functioning effectively.

Effective coordination and delivery partnerships are important for delivering environmental water to where it is needed, at the right time. For example, the CEWH’s partnership with Murray Irrigation Limited (MIL) has resulted in MIL’s network of channels and escapes being used to deliver small volumes of oxygenated water to create areas of better‑quality water to support native fish and other aquatic life at critical times (CEWH, sub. 69, p. 8).

MIL has been an important partner contributing to the implementation of the Plan in NSW. For more than 15 years, MIL has worked with the Commonwealth and NSW Government Environmental Agencies to strategically deliver water, sometimes in very large annual volumes, to achieve environmental benefits … . MIL sees itself as not just delivering a modern and responsive service to irrigators, but increasingly as a key partner in the delivery of water supply and other services to the regional and downstream environment, which are vital to strengthening our region and the MDB. (MIL, sub. 65, pp. 15–16)

During consultations, irrigators spoke positively about their partnerships with governments for the delivery of environmental water. Renmark Irrigation Trust, in its submission to the inquiry, said:

The Trust’s partnership with the Commonwealth Environmental Water Holder, which aimed to bring Trust and Renmark Paringa Council owned floodplain land back to health, has also been a win/win arrangement; good for the riverine ecosystem, good for our business and local economy and good for our community. (sub. 24, p. 1)

| Box 3.3 – Coordinated flows |
| --- |
| Environmental water holders work together and with river operators to coordinate the delivery of water for the environment.   * In 2019, during drought conditions, environmental water holders delivered over 2,000 GL of environmental water through the Murray system, including 27 coordinated events between water holders, resulting in improved system connectivity outcomes (MDBA, sub. 61, response to information request, p. 16). * In spring 2020, more than 320 GL in coordinated flows were planned and delivered across the Murray, Goulburn and Murrumbidgee rivers. Nearly 25 agencies worked together to deliver flows to multiple Ramsar wetlands (achieving a River Murray peak flow of 17,806 ML/day at Yarrawonga – below the regulated constraint of 18,000 ML/day). A flow above 15,000 ML/day extended for 18 days and achieved significant environmental outcomes for the Ramsar‑listed Barmah‑Millewa Forest (MDBA, sub. 61, response to information request, pp. 16–17). * In 2021‑22, coordinated flows were being planned and delivered under unregulated and wet conditions. Environmental water holders worked together with land and water managers, river operators and local landholders to build flows to support mid‑Murray ecosystems while staying within mid‑Murray constraint levels. Many billabongs, creeks and flood‑runners on both sides of the Murray received their first drink since 2016 (MDBA, sub. 61, response to information request, p. 17). * In the northern Basin, the CEWH and the NSW Government have coordinated multiple environmental releases to provide in‑valley and downstream environmental outcomes, including the northern connectivity event (April to July 2018), the northern fish flow event (April to July 2019) and the northern refresh flow (April to May 2023) (CEWH, sub. 69, p. 29). |
|  |

These partnerships and collaborations have been instrumental to the CEWH’s credibility and its success in facilitating the delivery of environmental outcomes.

Local input into environmental water prioritisation and delivery is important for community buy‑in to Basin Plan implementation. The CEWH has strengthened engagement with Basin communities and stakeholders over time. Local engagement officers live and work in regional towns throughout the Basin and have extensive networks and understanding of local issues. The CEWH’s local engagement model is regarded as highly effective.

‘Localism’ is vital to engage local communities in environmental watering planning and decision making. Engagement of local areas coordinators and rangers by the CEWH has gone a long way to establishing partnerships and trust through consultation and should be further encouraged as a way of sharing information out of and to Canberra. (National Irrigators Council, sub. 62, p. 22)

At the valley scale, state government agencies have established Environmental Watering Advisory Groups (EWAGs). The CEWH is an active member of these groups, which provide community members with the opportunity to provide advice and input to environmental water planning, and receive updates on environmental water use, outcomes and issues (CEWH, sub. 69, p. 10).

The NSW Government commented that:

There has been a substantial expansion of communicating and consulting on management of water for the environment and related outcomes, and it is a continuing journey. NSW uses Environmental Water Advisory Groups (EWAGs) in several valleys, some operating for many years, to successfully guide and inform environmental watering decisions to achieve Basin Plan and LTWP objectives and targets. All EWAGs ensure the views and understanding of First Nations, local communities, industry, and environmental stakeholders are considered when priorities and planning decisions are made. (sub. 43, p. 11)

For many years, in Victoria, CMAs have had an established network of stakeholders from local communities and peak bodies that engage on a range of issues, including the development and implementation of regional waterway strategies, environmental water management plans and annual seasonal watering proposals. In more recent years, as the environmental water portfolio has expanded, some CMAs have established EWAGs to engage with interested individuals and private landholders. For example, the North Central CMA, with the VEWH and the community‑based Enhancing Northern Waterways Advisory Group, recently planned winter‑spring watering to support waterbird chicks that hatched over a successful breeding season due to the natural floods in Gunbower in 2022 (Victorian Government, sub. 74, response to information request, p. 20).

Inquiry participants said EWAGs have been a positive step in Basin Plan implementation. For example, the Inland Rivers Network (IRN) said:

IRN supports the level of community engagement in environmental water planning, as exercised in NSW through Environmental Water Advisory Groups (EWAGs). Having the CEWH and state environmental water holders and other water related agencies making combined decisions with community on‑ground knowledge is a good model that needs to be replicated. (sub. 82, p. 5)

But despite improved coordination and engagement between environmental water holders, as discussed earlier, there are concerns about how well the Basin Plan can deliver coordinated flows to improve environmental outcomes at the whole‑of‑Basin level. The BWEWS should provide clear guidance, under all water availability scenarios, on the priority for achieving flow connectivity at the system scale relative to watering within a WRP area. By better articulating the relative priorities in connected systems, the BWEWS would provide better direction, accountability and transparency around priorities on achieving outcomes from coordinated environmental water flows at the whole‑of‑Basin scale. Governance and engagement is discussed further in chapter 9.

### Delivering shared benefits from environmental water

When managing held environmental water, environmental water holders are obliged to focus primarily on environmental outcomes. However, additional benefits can often be achieved that are compatible with environmental benefits sought from the use of environmental water, and align with the objectives of the Basin Plan.[[48]](#footnote-49)

Environmental watering contributes both directly and coincidentally to other community benefits.

* For First Nations people, healthy rivers and wetlands are essential to spiritual, cultural and physical wellbeing (chapter 5). Where environmental and cultural water outcomes intersect, environmental water holders can contribute to achieving cultural outcomes.
* Site‑specific watering events can provide recreational opportunities, such as fishing, canoeing and rowing regattas. For example, the VEWH said they ‘have timed the release of water for the environment into some rivers that are popular with kayakers, so that river levels were higher over a long weekend – when most kayakers wanted to paddle’ (VEWH 2019b).
* Environmental watering of rivers, lakes and wetlands can provide coincidental benefits by contributing to the strength of local economies and to the health and wellbeing of community members (PC 2021c, p. 116).

Understanding these additional benefits is important for allowing opportunities for alignment with environmental water use.

#### Collaborating with First Nations people on environmental water decisions

Basin Governments have made efforts to improve the ways in which they collaborate with First Nations people in environmental water planning and management.

At the Basin scale, First Nations representative groups advise on environmental water planning and delivery through the NBEWG and SCBEWC. Annual workshops with the CEWH support First Nations peoples’ inputs into environmental water planning at the Basin scale. The CEWH is also developing arrangements to increase MLDRIN’s capacity to advise on environmental water management in the southern Basin in the longer term (CEWH, sub. 69, p. 17).

The CEWH engages directly with individual First Nations and has developed successful partnerships such as a 10‑year partnership with the Nari Nari Tribal Council, which supports the planning, delivery and monitoring of Commonwealth environmental water on Nari Nari Country (CEWH, sub. 69, p. 17).

The CEWH’s approach is evolving towards forming partnership and co‑management arrangements with First Nations people, and elevating their role in the management framework from consultative to decision‑making (CEWH, sub. 69, p. 17). In the 2023 Australian Government Budget, the CEWH received $3.5 million to establish a *First Nations Environmental Water Partnerships Pilot Program*. The program will support the development and implementation of partnership agreements with First Nations organisations in the Basin (DCCEEW, sub. 77, p. 17).

The CEWH and MDBA have worked together on projects to increase First Nations peoples’ involvement in environmental water decision making.

* The *First Nations Environmental Water Guidance Project* commenced in 2019‑20. The MDBA and CEWH partnered with the Northern Basin Aboriginal Nations and MLDRIN, to better integrate First Nations peoples’ outcomes into environmental water management (MDBA 2023e). The project helped frame the way that First Nations people, the MDBA, the CEWH and other environmental water holders work together in setting annual priorities for the use of environmental water (PC 2021c, supporting paper C, p. 45).
* In 2021‑22, MLDRIN worked with the MDBA and the CEWH in the southern Basin to develop the *First Nations Environmental Watering Statement*. The statement provides First Nations guidance to environmental water managers around system scale watering (across multiple Nations). In 2023, the statement was updated to include First Nations advice around changing resource conditions (watering during and after wet times) (MDBA, sub. 61, p. 23).
* The MDBA *Living Murray Indigenous Partnerships Program* supports a network of Indigenous facilitators operating across The Living Murray Icon Sites to help engage with local First Nations people to inform management of water for the environment and monitor the outcomes of water use (MDBA, sub. 61, response to information request, p. 29).
* Since 2018‑19, the MDBA has reported on how First Nations values and uses of water were considered in the planning and delivery of water for the environment in the Murray–Darling Basin. Information is sourced from the CEWH, the MDBA, Basin state governments, and First Nations people (MDBA, sub. 61, p. 23).
* Environmental water managers are also working with First Nations people to improve outcomes reporting through ‘Rivers, the veins of our Country’ case studies and stories (MDBA, sub. 61, pp. 23–24).

State government agencies lead engagement with First Nations people on environmental water use at the site or valley scale. The NSW Environment and Heritage Group (EHG) and First Nations communities are working together on several Nation‑led initiatives to support the planning and delivery of water for the environment under the EHG *Healing Country Program* (NSW Government, sub. 43, p. 19).

In Victoria, the *Water is Life: Traditional Owner Access to Water Roadmap* focuses on increasing the role of Traditional Owners in determining how environmental water can be used for healing Country (Victorian DELWP 2022b). This includes developing new guidelines for Traditional Owners to submit seasonal watering proposals; undertaking pilot environmental watering projects; and developing a framework for the transfer of environmental water allocations to Traditional Owners (Victorian Government, sub. 74, response to information request, p. 15).

Examples of collaborations with First Nations people in planning environmental watering activities and delivering cultural outcomes where possible, are provided in box 3.4.

There is still scope for governments to enhance partnerships with First Nations people in environmental water planning and management. The most recent First Nations participation in water for the environment report observed that there is disparity between First Nations peoples’ inputs and consistency of engagement across the Basin (MDBA 2022i). Input to environmental water planning is made largely through frameworks and processes not determined or endorsed by First Nations people (MDBA 2022i, p. 23).

Auntie Janine and Craig Watson of the Latji Latji Mumthelang First Peoples, for example, said:

… every step of water delivery has been wrong which is particularly related to our lack of connection to decision‑makers. … We as First Peoples have not been properly connected to decision makers. There is disconnect between our interests on country and these reaching and being considered by the eventual decision makers above Local Government departments and Authorities. A recent example of this relates to repairing massive blowouts which had occurred at a burial site area near Mildura, where a consistent lack of water in the right places, at the right times has made the soil structures in the area very susceptible to wind‑driven dispersal and the resulting exposure of the remains of our ancestors. We had to rebury these remains; but the risk of it happening again remains strong, without getting allocations of water on country at the right time and place. (sub. 78, p. 2)

The NSW Aboriginal Land Council, commenting on the delivery of shared benefits from the use of environmental water, said:

All governments and the Commonwealth Environmental Water Holder (CEWH) must prioritise partnerships with First Nations communities throughout the Basin to ensure environmental water programs deliver on cultural outcomes. Aboriginal participation and the incorporation of Traditional Ecological Knowledge (TEK) must be increased at all levels of water management planning across the entire Basin Area. (sub. 144, p. 2)

| Box 3.4 – Achieving outcomes for First Nations people: some case studies |
| --- |
| Bringing life back to Dharriwaa  Dharriwaa, as named by the Yuwaalaraay/Euahlayi people (also known as the Narran Lakes), has been an important meeting place for First Nations people in north‑west NSW for thousands of years. The site is internationally recognised for its cultural and ecological importance. Environmental water has helped the wetland come back to life after drought and the long‑term effect of over‑allocation.  From being so dry and seeing the vegetation come back to life makes our soul sing, that’s why we feast, dance and have ceremony, we feel so connected to Dharriwaa Gooni‑Ma, Mother earth Narran Lakes our Meeting Place, said Tanya Morgan, who is a Youalaroi Traditional Owner from Narran Lakes Country. (MDBA 2022l, p. 10)  Yarning circles along the Lower Murray  Six yarning circles were held recently [in 2021] along the Lower Murray from Tailem Bend to Meningie where the Ngarrindjeri community, the Ngarrindjeri Aboriginal Corporation (NAC) and the [South Australian] Department for Environment and Water came together to share their experience and knowledge around water management and the River Murray … these gatherings were about understanding and documenting Ngarrindjeri cultural values, stories and priorities to better inform decision‑making for the planning and delivery of water for the environment to Ngarrindjeri Ruwe (Country). Tim Hartman, Chief Executive Officer from ‎the NAC, said that as Ngarrindjeri, they have a cultural obligation to care for and manage country.  ‘Yarning circles help build, share, and express knowledge though a process of open dialogue and deep reflection,’ Tim said. (SA DEW 2021)  Horseshoe Lagoon: an environmental water partnership with Taungurung  Taungurung Land and Water Council (TLaWC) is leading the way at Horseshoe Lagoon demonstrating how cultural values, environmental objectives and on‑Country knowledge sharing are critical to long term water management, healing Country and meaningful collaboration. Culturally significant to Taungurung Traditional Owners, Horseshoe Lagoon near Seymour (Victoria) continues to show promising responses to environmental flow deliveries. Since the water has returned, it is again a living wetland full of birds, frogs and turtles.  Watering activities at Horseshoe Lagoon provide an opportunity to heal knowledge through developing TLaWC capacity and confidence in water management. In 2019, Taungurung women held a Welcome to Country at the site, marking and celebrating the return of water through environmental flows. Water was again delivered to the lagoon in 2020 and 2021, with TLaWC responsible for managing the pumping and delivery. Taungurung rangers also carried out aquatic plantings at the site in 2022.  ‘We work in collaboration and with the support of our partners. We have taken on more and more responsibilities with time and the support of our partners is essential. Goulburn Broken CMA, Parks Victoria and the VEWH have shown true support for this purpose,’ said TLaWC’s Water Management Officer. (Victorian Government, response to information request, sub. 74, p. 15) |
|  |

Governments recognise that partnerships with First Nations people in water management must be a continued focus for implementing the Basin Plan. The MDBA, for example, said:

While progress is being made towards improved First Nations participation in environmental water management, many of the current collaborations and partnerships have been established through government mechanisms that are not often designed with effective First Nations relationships and outcomes in mind. Much more remains to be done. (sub. 61, pp. 22–23)

First Nations people are increasingly seeking to collaborate with Basin governments on environmental watering activities to improve the health of water‑dependent ecosystems and contribute to broader First Nations values where possible. Building meaningful partnerships to deliver shared outcomes from environmental watering activities requires resourcing by Basin Governments, and a commitment to establishing long‑term, formal partnerships.

Governments are also planning to enhance and strengthen First Nations peoples’ involvement in environmental water management over the longer term. For example, the Victorian Government is working towards recognition of Traditional Owners as environmental water holders (sub. 74, response to information request, p. 15).

Ambitions articulated by Basin governments to improve collaboration with First Nations people in environmental watering activities are encouraging. The challenge remains for Basin governments to develop decision‑making processes and deliver environmental watering activities in partnership with First Nations people, to achieve environmental and cultural benefits throughout the whole Basin.

#### Embedding shared benefits, objectives and outcomes in the Environmental Management Framework

Although delivering environmental water to achieve shared benefits is incorporated into the current water management practices of environmental water holders, it is yet to be embedded in the Basin Plan’s Environmental Management Framework. As MLDRIN put it:

Despite being a critical component of the Basin watering framework, the BWS [Basin‑wide Environmental Watering Strategy] has not demonstrated proper, genuine, and realistic consideration of Basin Nations’ rights and interests in relation to environmental water management. The current BWS provides general commentary on the benefits of engaging First Nations in environmental water planning and points to areas of ‘Future Work’ to be addressed in more detail through future revisions of the strategy. The BWS does not include any substantive provisions to guide inclusion of Basin Nations, or consideration of Basin Nations outcomes, in environmental water planning by the CEWH or Basin States. (sub. 92, p. 20)

To inform asset and catchment scale environmental water planning across the Basin, it is important that shared benefit objectives and outcomes from environmental water are clearly specified in the BWEWS. In 2018, the Commission said that opportunities to contribute to social or cultural outcomes, where these do not compromise environmental outcomes, should be actively pursued. We also recommended the BWEWS include a secondary objective that environmental watering should seek to contribute to social or cultural outcomes where environmental outcomes are not compromised (PC 2018, p. 280). And while the objective was not included in the 2019 BWEWS update, the MDBA said it will be included in the next update (expected in 2024) (MDBA 2020d, p. 89).

First Nations peoples’ objectives and outcomes for shared benefits of environmental water is an area identified by the MDBA for ongoing development in the BWEWS. The MDBA has also committed to working with First Nations people to include their objectives and outcomes for shared benefits of environmental water in the next BWEWS (MDBA 2022i, p. 11).

First Nations peoples’ objectives, values and outcomes also need to be better incorporated at the local level in LTWPs. MLDRIN reported that:

Overall, while some LTWPs included consultation with Basin Nations, and some include content describing Nations’ values and objectives, it is generally not clear if, or how, Basin Nations’ inputs have informed the substantive components of the Plans (e.g., objectives, targets, and environmental water requirements). (sub. 92, p. 22)

Basin state governments recognise that there is a need to focus on improving engagement with First Nations people to better capture the watering priorities of First Nations people and improve the effectiveness of LTWPs. The NSW Environment and Heritage Group is partnering with MLDRIN to revise LTWPs and work through the best approaches to achieve meaningful input led by First Nations people. And the NSW Department of Primary Industries, Fisheries is working with local First Nations communities in the Peel valley to develop a culturally appropriate methodology that couples First Nations peoples’ knowledges and values with fish and flow management frameworks to inform environmental water management (NSW Government, sub. 43, p. 19).

First Nations peoples’ objectives and outcomes, under all water availability scenarios, for providing shared benefits from environmental water use (where compatible with environmental objectives) should be included in the BWEWS and LTWPs. Consistent with commitments made under the *National Agreement on Closing the Gap* (Australian Governments and Coalition of Aboriginal and Torres Strait Islander Peak Organisations 2020), these objectives and outcomes must be developed by First Nations people through genuine partnerships with governments (chapter 5).

An important consideration is how to achieve agreed shared benefits during climatic extremes in an increasingly dry climate. During periods of water scarcity, environmental water allocations are reduced, and other community benefits from environmental watering may be more difficult to achieve. For this reason, First Nations peoples’ objectives and outcomes for providing shared benefits from environmental water use, should be developed for different climate scenarios including wet, average and dry years.

Environmental watering is limited to providing cultural and other community benefits that are compatible with environmental objectives. Cultural flows that are owned and managed by Traditional Owners have the potential to provide more significant benefits to First Nations people and fulfill the aspirations of First Nations people for self‑determined decision making about water rights and the management of Country. Progress on providing cultural flows in the Basin is discussed in chapter 5.

### Natural resource management is important for maximising the benefits of environmental water

Achieving the environmental objectives of the Basin Plan requires more than just environmental watering. For example, invasive species or the impact of infrastructure on native species can undermine the benefits from water delivered to the environment.

In 2018 the Commission recommended that ‘Basin States should manage the risks to achieving the environmental watering objectives set out in LTWPs by delivering complementary waterway and natural resource management measures’ (PC 2018, p. 294).

Complementary natural resource management measures include:

* installing fishways and fish diversion screens
* control of pest species
* investments to address cold water pollution
* riparian management activities and habitat restoration (MDBA 2020d, p. 52).

Natural resource management (NRM) programs that complement environmental water planning and management are important to deliver (and prevent erosion of) long‑term outcomes, as well as to manage changing conditions. This is especially important in the context of Australia’s drying and highly variable climate. The Commission’s *National Water Reform 2020* inquiry recommended that NRM programs should give priority to the key environmental assets identified in water planning processes, provide funding and undertake the required works to protect those assets. During periods of water scarcity, NRM should focus on the protection of reserves and refuges and making sure that their regenerative capacity is protected (PC 2021c, p. 108).

Many participants called for a greater focus on natural resource management to support environmental objectives under the Basin Plan (box 3.5).

| Box 3.5 – Participants called for a greater focus on natural resource management |
| --- |
| Leeton Shire Council  Issues like poor water quality, cold water pollution, habitat degradation, feral animal control, weed management, barriers to fish passage and invasive species need a real and integrated focus if the Basin Plan goals are to be realised fully … Government should embrace an integrated approach to environmental management, rather than seeing the addition of environmental water as the sole solution to biodiversity challenges (sub. 72, p. 4)  National Irrigators’ Council  The irrigated agriculture sector has long advocated the need for complementary measures to improve connectivity and habitat for native fish, concerted action on terrestrial and aquatic animal and plant pest species, and to address cold water pollution. A dedicated focus on these measures is becoming increasingly pressing, where it is underpinned by the outcome of scientific work on native fish, impacts of terrestrial and aquatic pest species etc. Without complementary measures, the water reserved for the river and the environment will not produce the desired environmental outcomes and the expectations of communities. (sub. 62, p. 12)  NRM Regions Australia  Regional NRM organisations consider, plan for, and implement many of the suggested complementary measures, including in‑stream and riparian habitat restoration, control of pest and weed hazards, erosion control measures, and meaningful engagement with communities. However, regional NRM organisations need more investment to undertake and support delivery of these activities at a Basin scale. (sub. 36, p. 3)  Lachlan Valley Water  … there also needs to be a focus on how there can be environmental outcomes achieved not only from water management but whether complementary measures such as improving fish passage, improved control of non‑native fish species, dealing with cold water pollution, control of feral species and weeds that are causing degradation of wetlands, infrastructure to improve the delivery of water to environmental sites and improving the management of riparian zones will produce a better overall outcome from the management of environmental water. (sub. 54, p. 5)  Cotton Australia  … Basin States should manage the risks to achieving the environmental watering objectives set out in long‑term watering plans by delivering complementary waterway and natural resource management measures (such as habitat restoration or weed and pest control). (sub. 68, p. 17) |
|  |

Basin governments reported that they are increasingly integrating water and NRM planning. One example is the Native Fish Recovery Strategy, which is a joint government initiative developed in partnership with Basin state governments, First Nations people and the wider community to support healthy and resilient native fish populations in the Basin (other examples are provided in box 3.6). And there is potential to scale up this Strategy to further improve environmental outcomes (DCCEEW, sub. 77, p. 18).

| Box 3.6 – Integrating water and natural resource management, some examples |
| --- |
| The NSW Local Land Services is delivering a number of projects that will contribute to environmental outcomes, such as:  The Riparian Restoration Project to restore riparian areas suffering cumulative damage from recent droughts, bushfires and flooding across NSW  Fencing Northern Basin Riverbanks Program to minimise the impacts of livestock on priority reaches in the northern Murray–Darling Basin. (NSW Government, sub. 43, response to information request, p. 14)  In Victoria, the Department of Energy, Environment and Climate Action and the Victorian Environmental Water Holder work with Catchment Management Authorities to manage environmental water with complementary works. These works cover a range of areas including: control of pest plants and animals; revegetation; fishway construction; riparian fencing; construction of regulators; snag removal; native fish breeding; and irrigation nutrient management (Victorian Government, sub. 74, response to information request, p. 17).  Similarly, the South Australian Department of Environment and Water, National parks and natural resource management agencies such as the Murraylands and Riverland Landscape Board co‑operate on water delivery planning and operations, grazing management, pest plant and animal control, visitor management in reserves, and groundwater management activities (South Australian Government, pers. comm., 25 September 2023). |

The importance of coordinating environmental water management with NRM will increase as the environment faces increasing pressures from a changing and more variable climate. The BWEWS notes the importance of integrating land and water management activities to achieve environmental outcomes (MDBA 2020d, p. 52). And the BWEWS update in 2019 included actions to integrate environmental watering with NRM, including that planning and management should:

consider the flow requirements to ensure return on investment of natural resource management actions (e.g. flow delivery is appropriate to support fishway operations)

align watering actions to support the establishment and maintenance of management actions such as revegetation and habitat restoration activities

prioritise natural resource management actions in locations that have high ecological value and can be supported by water planning and delivery

coordinate natural resource management actions and the planning and management of water to support the ecological needs of native fish. (MDBA 2020d, p. 69)

Including these actions in the BWEWS was an important step to embed the significance of NRM to achieve environmental outcomes under the Basin Plan. As LTWPs are updated, Basin state governments should take a proactive approach to identify further opportunities for integrating land and water management activities at the local level to deliver environmental outcomes.

Findings and recommendations

With implementation and policy frameworks in place, the focus now for environmental water management is simplifying and embedding current best practice approaches into the Environmental Management Framework to ensure that environmental water is managed efficiently and effectively to contribute to achieving the objectives of the Basin Plan. The drought and flood conditions in recent years are a reminder that managing our water‑dependent ecosystems requires continuous learning and adaptation. And the challenge of a variable and changing climate provides further impetus for making improvements to this key element of the Basin Plan.

|  | Finding 3.1  Identifying key Basin environmental assets and priority management actions in the Basin‑Wide Environmental Watering Strategy |
| --- | --- |
| In 2025, the Murray–Darling Basin Authority is expected to publish a Basin-wide conservation prioritisation framework to identify places of high conservation value and prioritise management actions to conserve their critical assets, values and functions. The development of this framework and its inclusion in the Basin‑Wide Environmental Watering Strategy has the potential to provide greater direction to, and accountability for, the Commonwealth Environmental Water Holder’s decision making on environmental watering. | |
|  | |

|  | Recommendation 3.1  Improving the effectiveness of the Basin‑Wide Environmental Watering Strategy |
| --- | --- |
| The Murray–Darling Basin Authority’s next update to the Basin‑Wide Environmental Watering Strategy should include:   * an objective that environmental watering should seek to contribute to social or cultural environmental outcomes (where compatible with environmental outcomes) * First Nations peoples’ objectives and outcomes, under all water availability scenarios, for shared benefits from environmental water use (where compatible with environmental objectives) at the Basin‑wide scale * clear guidance, under all water availability scenarios, on the priority for achieving flow connectivity at the system scale relative to watering within a water resource plan area * risks to achieving environmental objectives, in a changing and more variable climate. | |
|  | |

|  | Recommendation 3.2  The adaptive management of long‑term watering plans |
| --- | --- |
| In the next iterations of long‑term watering plans, Basin state governments should include:   * First Nations peoples’ objectives and outcomes under all water availability scenarios for shared benefits from environmental water use (where compatible with environmental objectives) for each water resource plan area * planning and management actions to integrate the management of environmental water with natural resource management (such as habitat restoration or weed and pest control). | |
|  | |

|  | Recommendation 3.3  Basin annual environmental watering priorities require review |
| --- | --- |
| As part of the 2026 review of the Basin Plan, the Murray–Darling Basin Authority should assess the value of Basin annual environmental watering priorities and whether the Basin Plan requirements for these annual priorities should be amended or removed. | |
|  | |

|  | Recommendation 3.4  Delivering shared benefits from the use of environmental water |
| --- | --- |
| First Nations peoples’ objectives and outcomes for providing shared benefits from environmental water use for inclusion in the Basin‑Wide Environmental Watering Strategy and long‑term watering plans should be developed by First Nations people through genuine, resourced partnerships with the Murray–Darling Basin Authority (for the Basin‑Wide Environmental Watering Strategy) and Basin state governments (for long‑term watering plans), consistent with commitments made by all governments under the National Agreement on Closing the Gap. | |
|  | |

# Water resource plans

|  |  |
| --- | --- |
| Key points | |
|  | Basin state governments play a key role in the Basin Plan by preparing and implementing water resource plans (WRPs). The Basin Plan sets out what these plans must include – such as, importantly, how much water can be taken for consumptive use from each catchment. |
|  | All WRPs are now accredited and in operation in Victoria, Queensland, South Australia and the Australian Capital Territory. Ten of the 20 plans for New South Wales remain outstanding. Water take reporting by the Murray–Darling Basin Authority (MDBA) over the past four years reveals that sustainable diversion limits have been breached in New South Wales, but until the plans are accredited, the limits cannot be enforced by the Inspector‑General of Water Compliance (IGWC). |
|  | While WRPs reflect, to a significant extent, existing state arrangements, the process of making, assessing and accrediting the plans has been slow and complex. |
|  | The number and complexity of the requirements for WRPs has made the plans difficult to develop and assess and will make them difficult to amend, inhibiting adaptive water policy.  Some WRP requirements could be simplified, removed or made less prescriptive. The MDBA should work with stakeholders to do this in its upcoming review of the Basin Plan, guided by the principle of subsidiarity and the fact that the core role of WRPs is to implement sustainable diversion limits.  Basin states should also be able to make non‑contentious amendments to WRPs without the changes needing to be formally assessed by the MDBA. The Water Act should be amended to enable these low‑risk changes to be fast‑tracked. |
|  | Where WRPs are in place, there is evidence that annual reporting on water take, sustainable diversion limit compliance and metering is working well. The IGWC has conducted audits and is developing a compliance framework for WRPs. However, it is too early to evaluate whether WRPs are meeting the objectives and outcomes of the Basin Plan. |
|  | There is room to improve the WRP reporting arrangements in the Basin Plan. The MDBA, in consultation with the IGWC and Basin states, should revise the annual WRP compliance reporting template to ensure it:  does not duplicate information collected elsewhere  reflects the WRP compliance framework  helps assess whether WRPs are delivering on the objectives and outcomes of the Basin Plan, including as part of the 2025 evaluation. |

## Water resource plans are fundamental to implementing the Basin Plan

Water resource plans (WRPs) are fundamental to implementing the Basin Plan. They are the mechanism through which state governments implement sustainable diversion limits (SDLs), which is the long‑term average annual volume of water for consumptive use that can be taken from the Basin.[[49]](#footnote-50) They also include, among other things, water quality standards and set out how water will be managed during extreme events. The Basin Plan sets 55 requirements for WRPs – setting a consistent standard across the Basin, but also allowing state governments to tailor plans to different areas (figure 4.1).

Figure 4.1 – Key elements of water resource plans

Key elements of water resource plans

This figure shows how the different parts of chapter 10 of the Basin Plan which water resource plans must include relate to each other

Source: adapted from MDBA (2013b, p. 11).

To a significant extent, WRPs reflect pre‑existing state arrangements and instruments, but state governments have had to adjust some of their arrangements to meet the standards in the Basin Plan. For example, all Basin states have had to develop accounting methods that show how they meet SDLs.

### Status of plans

There should be 33 WRPs across the Basin – 14 surface water plans, 14 groundwater plans, and five plans that each cover both surface and groundwater. All the plans for Victoria, Queensland, South Australia and the Australian Capital Territory (ACT) are now in place. Eleven plans for New South Wales (NSW) remain outstanding (table 4.1).

Table 4.1 – Status of WRP accreditation by jurisdiction

December 2023

|  | WRP Areas | WRPs accredited | WRPs under assessment |
| --- | --- | --- | --- |
| New South Wales | 20 | 10 | 8 |
| Victoria | 5 | 5 | n/a |
| Queensland | 3 | 3 | n/a |
| South Australia | 3 | 3 | n/a |
| Australian Capital Territory | 2 | 2 | n/a |

Sources: MDBA (2022s, p. 6), NSW DPE (2023e).

The NSW Government submitted all of its plans to the Murray–Darling Basin Authority (MDBA) in 2020, but later withdrew them following formal advice from the MDBA that the plans did not meet all requirements, including those for planned environmental water and Aboriginal consultation (NSW DPE 2022b). The timeline for WRP development and accreditation is set out in figure 4.2. Ten NSW plans are now accredited and eight are with the MDBA for assessment.[[50]](#footnote-51) Of the remaining two plans yet to be submitted to the MDBA (the Namoi and Gwydir WRPs), the NSW Government has not indicated an anticipated resubmission date (NSW DPE 2023f). [[51]](#footnote-52)

In some circumstances, the Australian Government Water Minister may ask the MDBA to prepare a WRP for a Basin state. However, as a number of inquiry participants noted (for example, ACT Government, sub. 85. p. 4), these last‑resort ‘step in’ powers[[52]](#footnote-53) have not been exercised, and the Inspector‑General of Water Compliance (IGWC) is on the record as saying they should have been (Siebert and Hollingworth 2022). Participants in this inquiry have stated that finalising NSW WRPs is urgent and the Minister for Water should use step‑in powers if necessary (MacMillan, sub. 125).

Widespread (and ongoing) delays with making and submitting WRPs suggest that the step‑in provisions are not an effective incentive for Basin states to complete their WRPs within the legislated timeframes. In practice, exercising these step‑in provisions would be challenging – there are a number of legal requirements that must be met prior to the Minister exercising the step‑in powers[[53]](#footnote-54) and Basin states still retain constitutional powers for water management.

As such, there are no significant consequences for the Basin states not meeting legislated WRP deadlines and limited options for the Australian Government to induce them to develop and submit plans in a timely way.

Figure 4.2 – Timeline of water resource plan development and accreditation

Timeline of water resource plan development and accreditation 

This figure shows the key milestones and dates since the Basin Plan was legislated in 2012 for Water Resource Plan development and accreditation. It includes when WRPs were accredited, supporting material provided by the MDBA to assist the process, legislative changes and when WRPs have been withdrawn and resubmitted for assessment. 

Sources: DPE (NSW) (2022b, 2023e), MDBA (2019e, 2019f, 2020n, 2020m, 2020o, 2020l, 2021i, 2021h, 2021j, 2022h, p. 4, 2022q, 2022r, 2022p, 2022p, 2022s, 2023a, p. 6).

|  | Finding 4.1  Incentives to complete water resource plans on time are weak |
| --- | --- |
| The Basin Plan does not adequately incentivise Basin states to complete their water resource plans within the legislated timeframes, and Basin state governments face no significant consequences for failing to do so. | |

### The Basin Plan relies on all WRPs being in place

The absence of accredited plans in New South Wales brings into question ‘the overall effectiveness and efficiency of the current arrangements’ (MDBA, sub. 61, p. 9). While some arrangements have been made to ensure key commitments[[54]](#footnote-55) are met in the absence of WRPs (MDBA 2022g), there are serious implications for environmental outcomes to not having all WRPs in place.[[55]](#footnote-56)

Where a WRP is not in place in one part of the Basin, this affects other parts of the Basin and the overall effectiveness of the Basin Plan. For example, the ACT Government said that in the absence of the NSW Murrumbidgee WRP being accredited, ‘[p]lanned environmental water between Tantangara Dam and the ACT border is not protected from extraction’ (sub. 85, p. 4). The ACT Government further explains the critical value of WRPs in water management across jurisdictional boundaries:

The value‑add of WRPs is to improve water management across jurisdictional boundaries and between catchments, protect the inherent rights of the environment, and provide water security for downstream communities. For WRPs to be effective, all WRPs must be in place, meet the requirements prescribed under the Basin Plan and have genuine consideration of cross‑border water resource management for Basin‑scale outcomes. (sub. 85, p. 4)

WRPs must have regard to connected water resource plan areas. For example, they must:

* account for water with significant hydrological connection to the water resources of the SDL resource unit[[56]](#footnote-57)
* specify the impacts of interception where there are connected water resources[[57]](#footnote-58)
* enable environmental watering between connected water resources.[[58]](#footnote-59)

And water quality management plans must be developed having regard to the impact of the measures in these plans on the ability of another Basin state to meet water quality targets.[[59]](#footnote-60) Where WRPs are not in place, these connectivity issues may not be given sufficient consideration (box 4.1).

| Box 4.1 – Concerns about connectivity in the Murray–Darling Basin |
| --- |
| Connectivity between WRP areas in the northern Basin was raised as a particular concern in regional visits the Commission made as part of this inquiry and in submissions.  NSW water sharing plans do not address connectivity, there are no end of valley flow targets and no end of system flow targets, that is the simple but catastrophic failing of the basin plan. (Pastoralists Association of West Darling sub. 42, p. 1)  [NSW South‑West Water Users Association] believes it is important that flow triggers in the Northern Tributaries, Barwon‑Darling and Lower Darling, and storage volumes in the Menindee Lakes be determined to ensure that protecting the health of the river is made a priority … Targets cannot be tokenistic; targets need to be scientifically backed, demonstrating benefits for whole of river health. The recognition that all WSPs are connected and have repercussions in other valleys urgently needs addressing. (sub. 16, p. 4) |
|  |

#### The Inspector-General of Water Compliance cannot enforce WRPs that are not accredited

Another important implication is that the IGWC cannot enforce WRPs that are not accredited. Therefore, for most of New South Wales, ‘there is no SDL compliance’ and ‘no practical consequence for NSW in failing to deliver commitments on time’ (IGWC, pers. comm., 31 July 2023).

When a water resource plan is in place, the full legal suite of monitoring, risk assessment, and compliance tools such as inquiries, audits, and investigations are available to undertake compliance and enforcement. (IGWC 2023h, p. 12)

Outstanding WRPs are also said to undermine trust between Basin Governments and Basin communities. A number of participants expressed concerns about the outstanding plans in New South Wales. For example, the Renmark Irrigation Trust said:

There is a sense that the system has failed to ensure all Basin States are meeting their requirements with the same degree of equity and that insufficient authority has been provided to the Commonwealth agencies to enforce these requirements. (sub. 24, p. 4)

While bilateral agreements with the MDBA require the NSW Government to report on water take, ‘the bilateral agreement is not the legislative tool which can be used to determine and enforce SDL compliance’ (IGWC 2023h, p. 12).

#### Recent reforms seek to deal with overextraction in areas without WRPs

Transitional and annual water take reporting over the past four years indicates that annual extraction limits have been exceeded in multiple NSW valleys in the northern Basin (MDBA 2019d, 2020k, 2021b, 2022c). The most recent SDL compliance report suggests this trend has continued, with two SDL resource units assessed as non‑compliant (IGWC 2023h). Under the Basin Plan,[[60]](#footnote-61) an unintended consequence of failing to have WRPs in place after 1 July 2019 is that a jurisdiction can use more water than they should, without having to ‘pay it back’.

Once a water resource plan is accredited and operational, the register of take commences with a cumulative balance of zero. This means that any interim debits or credits on the interim registers for New South Wales are not carried forward. (IGWC 2023h, p. 14)

The *Water Amendment (Restoring Our Rivers) Act 2023* seeks to remedy this situation by requiring the MDBA to make a one‑off adjustment to the register of take in these circumstances, to reflect any credits or debits that would have otherwise accrued after 1 July 2019. This appears to have been the original intent of an agreement made at the December 2018 Murray–Darling Basin (MDB) Ministerial Council.[[61]](#footnote-62)

#### Floodplain harvesting arrangements compliance with SDLs is yet to be tested

Inquiry participants also raised concerns about floodplain harvesting in New South Wales (box 4.2). Floodplain harvesting licensing now covers 80% of the volume of water taken through floodplain harvesting in New South Wales (rollout is complete in the NSW Border Rivers, Gwydir, Macquarie and Barwon‑Darling valleys with the Namoi valley expected to be complete by the end of 2023) (NSW Government, sub. 43, response to information request, p. 4).

While individual entitlements to access water are a state responsibility and outside the Basin Plan, the volumes that will be authorised to be extracted under floodplain harvesting licences still need to be within the SDLs set for the WRP areas they are granted in. In the *Annual water take report 2020–2021* the MDBA emphasised the importance of WRPs for managing floodplain harvesting:

For SDL resource units in New South Wales, where floodplain harvesting has grown and pushed total use above the limits, the intention is to restrict take by floodplain harvesting where necessary to return total diversions to the SDLs in each resource unit … The Authority keenly anticipates the completion and implementation of this New South Wales program [Healthy Floodplains Program] and relevant strategies to monitor and manage floodplain harvesting included in proposed WRPs. (MDBA 2022c, p. 41,43)

However, none of the WRPs covering these valleys have been accredited, so it is unclear how the floodplain harvesting licences that have been granted will be managed so that the SDLs will be met.

We have licensing of floodplain harvesting in northern NSW above the legislated legal level of cap (while every other southern basin irrigator operates under) with no end of system flows to protect connectivity, despite connectivity remaining a key principle of the plan … Overextraction … of the Darling River has resulted in fish kills and poor water quality. Why isn’t the Federal Government focusing on licensing floodplain harvesting under the cap to prevent this from happening again and again? (Southern Riverina Irrigators sub. 97, p. 3)

| Box 4.2 – Concerns around floodplain harvesting remain |
| --- |
| The NSW Floodplain Harvesting Policy was introduced by the NSW Government in 2013 to bring existing floodplain harvesting extractions into the water entitlement system (NSW DOI 2018). Previously landholders with approved works had legally been able to extract water in this way without restriction. Under the policy, landholders’ extraction volumes will instead be tied to entitlements granted by the NSW Government, as is the case for other forms of consumptive water take. The new floodplain harvesting entitlements will be identified within water resource plans and will be subject to the requirements around determining permitted and actual annual water take to meet sustainable diversion limits (SDLs).  Concerns raised with the Commission about the NSW Floodplain Harvesting Policy include:   * the process for increasing baseline diversion limits and sustainable diversion limits to accommodate the level of floodplain harvesting is complex, ambiguous and key information is not publicly available (Nature Conservation Council of NSW, sub. 50, p. 9; Temba Orchards, sub. 87, p. 2) and new estimates of baseline diversion limits do not justify an increase in total diversions (Environmental Defenders Office, sub. 91, p. 13) * floodplain harvesting appears to have increased licenced water diversions when implementation of the Basin Plan is to address overallocation (Environmental Defenders Office, sub. 91, p. 13; Jodie Hay, sub. 63, p. 2; Nature Conservation Council of NSW, sub. 50, p. 9; Southern Riverina Irrigators, sub. 97, p. 3; Temba Orchards, sub. 87, p. 2;) * lack of metering coverage in the northern Basin means the volume of extractions by floodplain harvesting is underestimated (Jodie Hay, sub. 63, p. 2) * no confidence that floodplain harvesting licensing will improve the health of the rivers (Dharriwaa Elders Group, sub. 86, p. 5) * floodplain harvesting licensing in the northern Basin prevents continuing and growing overextractions at the expense of historical flows to the southern Basin (Dharriwaa Elders Group, sub. 86, p. 5; Southern Riverina Irrigators, sub. 97, p. 4; Temba Orchards, sub. 87, p. 2;).   The Environmental Defenders Office reflect many of these concerns in its submission.  We note that current SDLs were developed on the basis that floodplain harvesting accounted for approximately 210 GL of water across the entire Northern Basin (which includes Queensland) … The volumes that [are] to be licensed across Northern NSW are likely to well exceed this figure … However, it is our legal opinion that any increase in BDLs [baseline diversion limits] should result in an increase in water recovery and reduced SDLs – not maintenance of the same recovery volume and increased SDLs. Indeed, the method proposed by the MDBA is likely to be unlawful insofar as it is unlikely to result in SDLs that reflect an [environmentally sustainable level of take], as required by s. 23(1) of the Water Act. (sub. 91, attachment 3, p. 13) |
|  |

The New South Wales Government’s revised modelling of baseline diversion limits estimates in the northern Basin, inclusive of floodplain harvesting, indicates the limits are ‘more than 40 GL per year lower than the estimates made in 2012 and more than 140 GL per year lower than the accredited ‘Cap model’ estimates from almost two decades ago’ (NSW sub. 111, p. 8). The NSW Government also said:

It is estimated that implementation of the NSW Floodplain Harvesting Policy will lead to a more than 25% reduction in floodplain harvesting across the northern Basin and return in the order of 60 GL per year on average to floodplains, rivers and creeks. (sub. 111, p. 9)

The IGWC noted that ‘the effects of these reforms are not likely to be seen on the SDL accounts until the 2023‑24 water accounting year’ (IGWC 2023h, p. 13).

|  | Finding 4.2  Without water resource plans, the Murray–Darling Basin Plan cannot be fully implemented |
| --- | --- |
| Half of the water resource plans for New South Wales remain outstanding more than 10 years after the Basin Plan was put in place and almost four years after an already extended deadline. Without all water resource plans in place across the Basin, the Murray–Darling Basin Plan cannot be fully implemented or properly enforced. With 10 of 20 plans outstanding, there is a greater risk of over extraction in New South Wales compared to other Basin states. | |

## Making and assessing water resource plans

WRPs are prepared by Basin states and then assessed for compliance with the Basin Plan by the MDBA. If a WRP complies with the requirements in the Basin Plan[[62]](#footnote-63), the MDBA submits the plan to the Australian Minister for Water and recommends the Minister accredit the plan (figure 4.3). Basin states must consult stakeholders when preparing the plans. As discussed in chapters five and nine, engagement on some plans, particularly engagement with First Nations, has been poor.

Only one of the 33 WRPs across the Basin was made in time to meet the original 2019 deadline and 10 plans are still not accredited. There are a number of reasons for these delays, including the COVID‑19 pandemic and natural disasters (NSW Government, sub. 43, p. 7). New South Wales has also needed to amend a number of its state‑based water management policies in response to compliance reviews in 2017,[[63]](#footnote-64) before finalising their WRPs. And preparing the plans cannot be rushed – adequate time is needed to ‘conduct the detailed analysis and consultation required to understand local issues, identify and test feasible solutions and make the necessary amendments to rules and supporting documents’ (PC 2018, p. 26).

But the extent of the delays in making the plans suggests there is a problem. Two key contributing factors are the number and complexity of requirements that WRPs must meet and the process of preparing and assessing the plans.

Figure 4.3 – Water resource plan path to accreditation

Water resource plan path to accreditation 

This figure shows a timeline of the stages involved in developing a water resource plan and the participants and decision makers. The three stages are: development; assessment and accreditation 

Source: adapted from MDBA (2018b, p. 4).

### Number and complexity of requirements

Delays in preparing and assessing WRPs are partly the result of the number and complexity of the requirements that these plans must satisfy. The Basin Plan sets out 55 requirements for WRPs and many of the requirements are multi‑faceted and interlinked. For example, under Part 3 of chapter 10 of the Basin Plan (‘Incorporation and application of long‑term annual diversion limit’), a water resource plan must set out the method for determining the maximum quantity of water that the plan permits to be taken for consumptive use during a water accounting period. The method must account for nine specific matters (such as return flows), be consistent with other provisions of the WRP, and comply with the rules for take. Rules for take need to ensure that the requirements under Part 4 of chapter 10 (‘The sustainable use and management of water resources’[[64]](#footnote-65)) – which relate to environmental assets and ecosystem function – can be met, and any identified risks have been assessed and strategies put in place[[65]](#footnote-66).

The MDBA said meeting all the requirements in the Basin Plan placed ‘a substantial burden’ on Basin states in preparing plans and on the MDBA in assessing them (sub. 61, p. 4) and the number and complexity of the requirements has:

… led to highly complex WRPs that comprise multiple documents and incorporate a range of state instruments and strategies. This complexity, with cross‑referencing across numerous state instruments, strategies and plans means WRPs are prone to drafting errors and internal inconsistencies resulting in an invalid instrument which cannot be accredited. (sub. 61, response to information request, p. 2)

Every Basin state said that developing WRPs was a difficult and resource‑intensive exercise (box 4.3).

| Box 4.3 – The development and accreditation of water resource plans: what Basin state governments said |
| --- |
| Victorian Government  The Murray–Darling Basin Authority (MDBA)’s process for accreditation was extremely resource intensive for the MDBA and for Victoria. Of note was that the intensive effort was not directed towards the areas of largest risk or opportunity, and appropriate effort was not anticipated or resourced within the MDBA, leading to long delays and backlogs. In Victoria’s case, while WRPs were lodged on time, there was an extended period without feedback which seemed to be caused by inadequate MDBA resourcing to review the plans after lodgement. (sub. 74, response to information request, pp. 2–3)  South Australian Government  The development and accreditation of [South Australia’s] three WRPs was a rigorous but prolonged process. The documents required for each WRP contain a significant amount of information and were resource‑intensive to prepare. (SA Government, personal communication, 18 September 2023)  Australian Capital Territory Government  WRPs are conceptually an important Commonwealth planning instrument with detailed requirements described in the Basin Plan. However, the design of the document, the scale of the water management area, scope of requirements and interpretation of those requirements, limit their effectiveness. The process to accredit plans and low materiality threshold for amendments create a barrier for incorporating better scientific knowledge, refined content and to embed policy improvements designed by jurisdictions to address future resource challenges. The accreditation process is labour intensive and requests for relatively minor text amendments trigger reaccreditation. (sub. 85, p. 4)  New South Wales Government  Getting to this stage has involved a significant body of work involving the development of 31 amended or replacement Water Sharing Plans (WSPs) under NSW legislation, nine long term water plans (LTWPs), 20 water quality management plans, 20 Incident Response Guides, 20 risk assessments, 10 ecological monitoring, evaluation and reporting (MER plans), 20 area description reports, 20 WRP consultation reports and significant work on 18 associated surface water modelling reports (sub. 43, p. 7).  Development and accreditation of WRPs has been resource intensive for Basin States and the MDBA. A key area for improvement in the efficiency and effectiveness of Basin Plan implementation is the accreditation process for WRPs. The MDBA needs to be provided with greater flexibility in how the exhaustive list of considerations for WRPs are assessed. Documentation and analysis requirements need to reflect the priority and materiality of issues and the risk to the resource. (sub. 43, p. 7) |
|  |

Some also suggested that the time and effort required to prepare the plans was disproportionate to their value. For example, the ACT Government said the WRP for the ACT ‘provides no value‑add, represents the ACT water management arrangements that pre‑existed the Basin Plan, and only stifles opportunities to improve water resource management and sustainable development’ (sub. 85, p. 4).

The Victorian Government expressed a similar sentiment about the value of WRPs, saying the state was ‘largely compliant with the Basin Plan’ before it even completed its WRPs.

… there was minimal immediate changes to water planning and management in Victoria as a result of the WRPs. (sub. 74, response to information request, p. 4)

The NSW Government said there was ‘considerable duplication’, because WRPs rely heavily on their water sharing plans, ‘which also have consultation requirements’ (sub. 43, p. 7).

Similarly, the South Australian Government said that in its experience, ‘the amount of effort required for the various other components was not proportionate to the intended or actual use’ and that ‘there have been very few changes in how SA’s water planning and management practices have changed as a result of WRPs being implemented’ (SA Government, pers. comm., 18 September 2023).

The complexity of WRPs also makes it difficult for communities to engage with the plans and provide meaningful feedback (PC 2018, pp. 188–190). The documents are long and technical and consultation timeframes are often short.

### Inadequate guidance and shifting expectations

The MDBA’s processes for assisting the development of and assessing WRPs has also been criticised. Guidance material was said to have been ‘iteratively developed as issues arose’ and sometimes issued too late (ACT Government, sub. 85, response to information request, p. 4; Victorian Government, sub. 74, response to information request, p. 3; SA Government, personal communication, 18 September 2023).

The MDBA acknowledged these criticisms and said that working through all 55 requirements and sub‑requirements has been an iterative and time‑consuming process and caused delays in accreditation (sub. 61, response to information request, p. 2).

In 2018, the Commission found that the process of developing WRPs was onerous and unnecessarily costly because there was inadequate guidance and little clarity on the MDBA’s expectations for accreditation (PC 2018, p. 195). The Victorian Government said the process would have been more efficient and effective had the MDBA developed a ‘clear and objective assessment framework … to avoid the shifting of expectations during the preparation and assessment phase’ (sub. 74, response to information request, p. 3).

The difficulty of assessing plans and providing clear guidance is no doubt partly a result of the complexity and prescriptiveness of the requirements as well as being the first time the process had been undertaken (MDBA 2020h, p. xii). The MDBA said that while it continues to improve the efficiency of its accreditation processes, it is constrained by the provisions in the Basin Plan and Water Act (MDBA, sub. 61, response to information request p. 3). The MDBA has limited discretion; it is required by the Water Act to formally assess whether each WRP fulfils the requirements in chapter 10 of the Basin Plan (MDBA 2020j, p. 10,11).

|  | Finding 4.3  Preparing and assessing water resource plans is unnecessarily difficult |
| --- | --- |
| The process of preparing and assessing water resource plans is onerous and time‑consuming. This is in part because the requirements in the Basin Plan are unnecessarily complex and prescriptive. | |
|  | |

### Less prescription needed, and a greater focus on outcomes

What can be done to make the process of preparing, assessing and amending WRPs more efficient?

In regulatory theory, a distinction is commonly made between ‘rules‑based’ and ‘goals‑based’ laws. Rules‑based laws are generally more precise, specific and certain, but less flexible. Goals‑based laws are less prescriptive, more flexible, and more open to interpretation and judgment.

Some participants[[66]](#footnote-67) called for a move away from a ‘legalistic’ focus on the 55 requirements and towards an ‘outcomes focused’ approach to making and amending WRPs. While there are advantages and disadvantages to making the requirements for WRPs more goals‑based, it seems clear that the current approach is too onerous and that at least some of the requirements should be less prescriptive and more focused on outcomes. The MDBA said the 2026 Review provides an opportunity to address ‘unnecessary complexity’ in the 55 requirements of the Basin Plan and alleviate some of the burden on Basin states and the MDBA, including in making and assessing amendments (MDBA, sub. 61, response to information request, p. 3).

The Commission recommends the MDBA review the requirements for WRPs with a view to making them less prescriptive and more focused on outcomes. The principle of subsidiarity should be a guiding consideration in this review, given many of the arrangements included in the plans should remain largely the responsibility of state governments, with the implementation of SDLs being a core purpose of WRPs.

Submissions on this recommendation in the interim report were largely supportive[[67]](#footnote-68) with a number[[68]](#footnote-69) emphasising that there is scope to improve existing requirements as part of simplification, such as those around planned environmental water protection, connectivity and First Nations engagement. The IGWC supported the interim recommendation in‑principle, stressing ‘the importance of simplification not reducing accountability, transparency or enforceability of the Commonwealth’s water laws’ (sub. 133, p. 5).

The prospect of WRP requirements being simplified should not be used as an excuse to further delay finalising WRPs in New South Wales. Nor should the outstanding NSW WRPs be assessed against a different set of requirements to those already assessed, accredited and in operation. The MDBA said these changes ‘should only happen after NSW has completed its first generation of WRPs’ (MDBA, sub. 61, response to information request, p. 3). By all WRPs meeting the original 55 requirements in the Basin Plan, a consistency in the water management arrangements in the Basin will have been achieved.

|  | Recommendation 4.1  Simplify requirements for water resource plans |
| --- | --- |
| In its 2026 Basin Plan Review, the Murray–Darling Basin Authority should consider how the requirements for water resource plans could be simplified and whether some requirements should be removed or made less prescriptive and more focused on outcomes. The principle of subsidiarity should be a guiding consideration in this review, given many of the arrangements included in the plans are largely the responsibility of state and territory governments, with the implementation of sustainable diversion limits being a core purpose of water resource plans. | |
|  | |

### Amending the plans is set to be difficult

WRPs need to be amended over time to account for new information and changing circumstances. Changes have already been canvassed for plans in Victoria and South Australia (SA Government 2022; Victorian Government 2022). All WRPs will probably need to be amended after the Basin Plan Review 2026.

Regular amendments to WRPs would support adaptive water management and it is important that Basin states are not deterred from making these changes. WRPs should not be ‘set and forget’ instruments; they should evolve and adapt over time.

Most amendments need to be assessed by the MDBA for consistency with the Basin Plan and the MDBA has released guidelines about this process (MDBA 2021c, 2021d). Some Basin states are concerned that the problems faced making and accrediting WRPs will be faced again when they amend their plans. The ACT Government suggested that the process for amending WRPs creates a barrier to incorporating better scientific knowledge and making improvements to address future challenges (sub. 85, response to information request p. 4). A difficult amendment process risks making WRPs static and outdated policy documents.

Even if the requirements for WRPs are simplified, as recommended above, with the current settings the process of amending the plans is likely to be more lengthy and costly than it needs to be.

#### A risk‑based approach to amendments

Some types of changes to WRPs can already be ‘fast‑tracked’. The Water Act states[[69]](#footnote-70) that regulations may prescribe ‘minor’ or ‘non‑substantive’ amendments that are taken to have been accredited, provided the MDBA is notified of the change.[[70]](#footnote-71) Examples of such minor amendments include changes to spelling and punctuation, references, formatting and technical errors. These are a narrow range of changes. All other amendments need to be assessed by the MDBA and accredited by the Minister. The MDBA seeks to ‘tailor the amendment process to the scale and complexity of the proposed amendment’ so ‘simple amendments are not onerous’ (MDBA 2021c, p. 4), but it is nevertheless constrained by the Water Act and regulations. For example, changes that the South Australian Government considered minor (e.g. references to legislation) will nevertheless need to be assessed by the MDBA (SA Government 2022).

To ensure WRPs can be updated regularly and efficiently, a greater range of changes should be eligible for this ‘fast‑tracked’ process. These would be changes that are uncontentious, low‑risk, and clearly compliant with the Basin Plan. Many amendments that are not related to how SDLs are met may fall into this category. When deciding which amendments should be reviewed by the MDBA, it will be important to consider where the MDBA is most likely to add value, such as to amendments about improvements in modelling and methods for estimating and measuring water take.

This would be a more ‘risk‑based’ approach to amending WRPs. To ensure the arrangement is not misused, the MDBA could be empowered to ‘call‑in’ an amendment to check that it complies with the Basin Plan. While the IGWC currently has no role in the accreditation process, they could be consulted – as the WRP compliance agency – about where the risks from changes to each WRP are greatest.

Several participants supported the interim recommendation for a risk‑based approach to amending WRPs but stressed the importance of getting the details right.[[71]](#footnote-72) Others did not support the recommendation because they preferred there be regular, independent review of all WRPs against the objectives of the Water Act and the Basin Plan.[[72]](#footnote-73) The IGWC observed that:

Improvements will be required to current water resource plans. The operations of the Inspector‑General to date have found current arrangements for amending a water resource plan to be a challenging issue … Current arrangements do not appear to adequately promote continuous improvement in plans in an efficient way. (sub. 133, p. 5)

The Commission remains of the view that amendments to water resource plans should be processed in a risk‑based way. This does not diminish the importance of WRPs – which are intended to operate in perpetuity – being periodically reviewed. The five‑yearly evaluations of the Basin Plan are the appropriate mechanism for assessing the efficiency and effectiveness of all water resource plans (chapter 9).

The MDBA in their submission to the Interim Report said they will ‘consider whether there is an opportunity to simplify the process of amending and remaking WRPs in the course of reviewing the Basin Plan’s regulatory design in 2026’ (sub. 126, p. 4).

|  | Recommendation 4.2  A risk‑based approach to amending water resource plans |
| --- | --- |
| The *Water Act 2007* (Cth) should be amended to allow the accreditation of amendments to water resource plans to be fast‑tracked, where those amendments are low‑risk and clearly comply with the Basin Plan. | |
|  | |

## Compliance and reporting

As noted above, most WRPs have only been in place for three years and 10 remain outstanding (as at December 2023). This means it is too early to assess their effectiveness in supporting Basin Plan outcomes. The Basin Plan brings a system‑wide approach to water management and without all WRPs in place, any assessment of their contribution to Basin Plan outcomes – many of which rely on connectivity – would be partial and constrained. Nonetheless, the Commission has identified some arrangements that are working well, and others that need improvement.

### SDL accounting and compliance frameworks are in place

The SDL water accounting and compliance framework came into operation on 1 July 2019 as scheduled. Initially both were implemented by the MDBA, but the IGWC took responsibility for compliance in 2021.[[73]](#footnote-74)

WRPs set out the maximum amount of water permitted to be extracted for consumptive use (permitted take) in a water accounting period, and any associated rules for water use in each WRP Area. Data about permitted and actual take is collated by the MDBA and published annually in the SDL registers of take (MDBA 2022b).[[74]](#footnote-75),[[75]](#footnote-76) The MDBA also publishes an annual water take report which analyses the data in the registers (including for NSW SDL resource units[[76]](#footnote-77)) and looks at longer term trends (MDBA 2022c).

The IGWC can only enforce WRPs that have been accredited. Of the 109 SDL resource units in the Basin, the first SDL compliance report (2019‑20) only covered six units; the reports for 2020‑21 and 2021–2022 covered 55 units (IGWC 2022e, 2023h). There has been no recorded non‑compliance against those 55 SDL resource units over this period (IGWC 2023h).[[77]](#footnote-78)

Since the IGWC was established in 2021, the MDBA has updated its SDL accounting and reporting framework (MDBA 2022m) and the IGWC is developing its SDL compliance framework (sub. 75, p. 12).

### Improvements to metering and measurement are being tracked

WRPs must specify measures for maintaining and, if practicable, improving the proportion of take that is measured in the WRP area and the standard to which take is measured.[[78]](#footnote-79) Basin states also agreed to undertake a number of actions on metering accuracy and coverage within specific timeframes under the Murray–Darling Basin Compliance Compact (MDB Ministerial Council 2018).

Recent reviews of metering coverage and accuracy found a lack of progress and room for improvement in reporting (MDBA 2021g; Pearson 2022, p. 12). Pearson found there ‘is a lack of clear, easily understood and consistent information about compliance efforts’ and recommended that the IGWC ‘develop … a consistent set of metrics to provide an overview of water take compliance levels and the extent and reliability of metering and measurement, by category and sub‑category of water take across the Basin’ (Pearson 2022, p. 12).[[79]](#footnote-80)

The IGWC has produced annual metering report cards for the last two years to track the progress of Basin states in meeting their metering and measurement commitments under the Murray–Darling Basin Compliance Compact by 2025. The report cards highlight where Basin states are making improvements in the proportion of water take metered (for example, NSW moved from 78.4% to 81.8% of water take metered between 2020‑21 and 2021‑22, while Queensland data on percentage of water take measured for 2020‑21 and 2021‑22 was not available) and the standard it is measured at (IGWC 2023a, 2023b).

The IGWC has also driven improvements in water measurement by setting metering standards, developing guidelines and convening quarterly forums for compliance and enforcement officers in each Basin state (sub. 75, p. 19).

### Audits on WRP compliance obligations

The IGWC currently sets out compliance priorities in the annual work plan, taking a risk‑based approach to focus regulatory activities, such as audits, where the risks and consequences of possible or actual non‑compliance are greatest (IGWC 2021, p. 3). Priorities and corresponding actions for the IGWC over the last three work plans have included managing increasing groundwater use, trade enforcement, WRP compliance and fostering Basin‑wide regulatory cooperation (IGWC 2021, 2022a, 2023c).

To date the IGWC has completed three audits,[[80]](#footnote-81) the most recent on the management of overland flow harvesting in the Lower Balonne (IGWC 2023d). While the audit found that the Queensland Government was meeting requirements of the Condamine‑Balonne WRP in relation to overland flow licensing and the management of flow events, the IGWC made six recommendations to improve the effectiveness of systems and processes. The Queensland Government accepted recommendations to develop guidance about key compliance activities, implement alternative audit strategies, ensure the requirement to report measured take was consistent and enforceable and verify self‑reported take (QLD DRDMW 2023a). Two recommendations about onsite audits and communicating with entitlement holders were accepted in part.

The audit function plays an important role shining a light on how Basin states are managing key requirements under their WRPs, particularly where the requirements are not captured under state management arrangements – such as the requirement about managing risks to water resources in response to climate change.

### **The** IGWC is developing a compliance framework

In 2018, the Commission found that the requirements for annual compliance reporting had yet to be agreed on, risking unnecessary compliance costs. The IGWC recently released its regulatory policy and is in the process of developing a WRP compliance and enforcement framework.

* The regulatory policy outlines the approach the IGWC will take to compliance (risk‑based, outcomes focused, proportionate) (IGWC 2023g).
* The WRP compliance and enforcement framework will specify the IGWC’s approach to WRP compliance enforcement under the Water Act and the Basin Plan. The framework has been commissioned to a consultant and is scheduled to be completed by 31 March 2024 (IGWC, personal communication, 31 July 2023).

The IGWC receives a lot of the information it needs to undertake its compliance responsibilities from the MDBA through the register of take and the annual water take reports. The two agencies have a Memorandum of Understanding setting out how they will work together to support their separate roles and responsibilities (IGWC and MDBA 2022, p. 4).

An independent review of the IGWC that is looking at whether the IGWC has the powers necessary to carry out its functions, is due in January 2024 (Plibersek 2023b).

### **Reporting on WRP compliance to inform evaluations of effectiveness and efficiency going forward**

As WRPs are made and accredited, quality compliance reporting and regular evaluation – to assess how well they are working – will be important. The Basin Plan requires Basin states to report annually to the MDBA on compliance with WRPs[[81]](#footnote-82). And every five years, the efficiency and effectiveness of WRPs (including whether WRPs provide a robust framework under a changing climate) are assessed as part of the Basin Plan evaluation by the MDBA.[[82]](#footnote-83)

#### Annual WRP compliance reporting needs improving

The MDBA has developed a template for annual reporting on WRP compliance. It has two parts. Part A has four high level questions which all Basin states must address.[[83]](#footnote-84)

* Is the state agency aware of non‑compliance with rules and/or obligations created by WRPs?
* What level of confidence does the state agency have in compliance with the rules and obligations contained in WRPs?
* Have there been any amendments or changes to provisions of the state instruments (legislation, regulations) and state policies described in the WRPs or referenced in the accredited text of the WRPs, and are any being planned?

Responding to the Part A compliance questions, Basin states have so far tended to only report against the WRP provisions that relate to SDLs, and not other aspects of WRPs.

Part B requires Basin states to provide responses to more detailed questions on WRP provisions. To date, only Victorian and Queensland have been required to respond to questions under Part B.

Participants pointed to ways to improve the WRP reporting arrangements in the Basin Plan. The IGWC, for example, said the current schedule 12 matter 19 reporting arrangements were ‘inefficient and ineffective’ and ‘reflect a qualitative self‑assessment as opposed to a quantitative data and information set which supports robust assurance’ (sub. 133, p. 6).

In our interim report we asked for participants views on whether it was still necessary for Basin states to provide reports each year to the MDBA on compliance with WRPs, and more generally on how reporting on the effectiveness of WRPs could be simplified or otherwise improved.

A number of Basin states emphasised the need to reduce duplication in reporting and focus on outcomes.

Future Matter 19 reporting to the MDBA should not duplicate similar reporting through other channels, such as SDL reporting to the MDBA or as will be required under the newly published IGWC SDL Compliance Framework. We recommend that the MDBA, IGWC and Australian Government streamline reporting requirements on Basin States. Reporting requirements can be improved by being less prescriptive, removing duplication and by being more outcomes focused. (NSW Government, sub. 111, p. 9)

Any new compliance reporting should not be duplicative of current reporting and/or audit requirements and processes. (Queensland Department of Regional Development, Manufacturing and Water, sub. 112, p. 8)

Other participants spoke about the importance of holding Basin states to account for commitments under the Basin Plan via effective reporting (box 4.4).

| Box 4.4 – Participants views on annual Water Resource Plan compliance reporting |
| --- |
| Inland Rivers Network  It is imperative that Basin state governments continue to be required to report on compliance with their water resource plans … There is a key role for the Inspector General in providing independent assessment of compliance with water resource plans. An adequate regulatory process must be developed and the language of the Water Act and Basin Plan changed (for example from ‘may have consideration’ to ‘must have consideration’) so that the Inspector General can hold the states to account. (sub. 109, p. 5)  NSW Irrigators’ Council  At its core, compliance with the Basin Plan should be able to be demonstrated through SDL compliance. This ultimately is the main indication of Basin Plan compliance … There needs to be increased reporting on the positive outcomes of the Basin Plan, to overcome risk of public perception seeing the Plan as a failure. (sub. 110, p. 15)  Lifeblood Alliance  Basin states should absolutely continue to be required to report on compliance with WRPs and SDLs. The WRP is the key interface between the Basin Plan and state instruments, and must be demonstrated to be working as intended. As outlined above, the problem lies with the content of the WRPs – when the states just provide a list of their own management plans and strategies and say ‘we are compliant with these and are therefore compliant with our WRP’ the process becomes pretty meaningless. (sub. 119, p. 7)  NSW Farmers Association  NSW Farmers agrees with the Commission’s comments that the establishment of the Inspector‑General of Water Compliance (IGWC) role has been a positive addition to implementation framework of the Basin Plan. We encourage exploration of how this role could be expanded to take on more responsibility for compliance alongside the continued responsibility of the state governments, to avoid overlap of reporting requirements or the creation of another overseeing body within the framework. (sub. 123, p. 6)  Murraylands and Riverland Landscape Board  Whilst it is always important for Basin States to provide transparent reporting on key compliance matters, any streamlining of reporting is supported. (sub. 132, p. 4) |
|  |

As matter 19 reporting under schedule 12 is the only requirement on Basin states to report annually on WRP compliance (as opposed to SDL compliance), the IGWC advised against removing it (sub. 133, p. 6). However, the IGWC also said that ‘changes to reporting are needed to ensure the right data and information is collected, and to allow conclusions to be drawn on activities, inputs, outputs and outcomes delivered through water resource plans’ (sub. 133, p. 6).

In the absence of a WRP compliance framework (which the IGWC is working on), it is almost impossible to design effective and efficient reporting. How do Basin states know what success looks like? Once finalised, the WRP compliance framework should provide key markers for what will need to be reported by Basin states annually in matter 19 to demonstrate compliance. However, information collected on WRPs needs to have an eye beyond compliance.

#### Information collected through WRP reporting does not enable an evaluation of their effectiveness and efficiency

In 2018, the Commission recommended that ‘the MDBA (as Basin Plan regulator) in consultation with Basin Governments should finalise and publish a detailed terms of reference to assess the effectiveness and efficiency of WRPs in preparation for the five‑yearly evaluation in 2020’ (PC 2018, p. 199). As highlighted above, the MDBA were unable to properly evaluate the effectiveness and efficiency of WRPs in 2020 as they were not all in place.

While the MDBA said the annual Basin state WRP compliance reports will be used as an input to answer Key Evaluation Questions[[84]](#footnote-85) (sub. 61, p. 3), it is unclear how the information in some of these reports (QLD DRDMW 2022; Queensland Government 2022; Victorian DELWP 2022a; Victorian Government 2022) will help inform the assessment of the effectiveness and efficiency of WRPs in the five‑yearly evaluations. The MDBA acknowledged that ‘the adequacy of arrangements for reporting on WRPs cannot be properly and fully determined until all plans are accredited and operational’ (MDBA, sub. 126, p. 4).

Once the WRP compliance framework in finalised, the MDBA should revise the annual WRP compliance reporting template (in consultation with the IGWC – as the WRP compliance regulator – and Basin states) to ensure the information that is collected is not duplicating information collected elsewhere, and allows an assessment of the utility of WRPs for delivering on the objectives and outcomes of the Basin Plan as part of the 2025 evaluation (section 9.3).

|  | Recommendation 4.3  Revise annual water resource plan compliance reporting |
| --- | --- |
| The Murray–Darling Basin Authority, in consultation with the Inspector‑General of Water Compliance and Basin states, should revise the annual water resource plan compliance reporting template to ensure it:   * does not duplicate information collected elsewhere * reflects the water resource plan compliance framework * helps assess whether water resource plans are delivering on the objectives and outcomes of the Basin Plan, including as part of the 2025 evaluation. | |

# The values of First Nations people

|  |  |
| --- | --- |
| Key points | |
|  | More than 100,000 First Nations people from over 40 Nations live in the Murray–Darling Basin. Aboriginal and Torres Strait Islander people have deep connections to their land, waters and waterways, and tens of thousands of years of knowledge about caring for water and river country. However, since colonisation, First Nations people have had limited opportunities to determine when, where and how they use water. |
|  | The Murray–Darling Basin Plan (the Basin Plan) includes mechanisms for First Nations people to provide input into the development and implementation of water management arrangements – including in the areas of water resource plans, environmental management and knowledge building. |
|  | The policy landscape has changed since the Basin Plan was put in place. In 2020, all Australian governments signed the National Agreement on Closing the Gap, which includes commitments to shared decision‑making and transforming government organisations so they work better for First Nations people. |
|  | Basin governments have improved how they work, engage and partner with First Nations people over the last five years, particularly in environmental watering activities. However, there are continuing concerns about Basin Plan engagement processes. First Nations people, particularly in New South Wales, said they see little evidence that governments consider their values, objectives and desired outcomes in Basin water planning and management decisions.  Recent reforms to the Basin Plan require the Secretary of the Australian Government Department of Water to report annually about First Nations engagement activities. Basin states should provide information on their own First Nations engagement activities for the purposes of this report.  Basin states should publicly report on how the input of First Nations people and organisations is considered, actioned and reflected in finalised and amended water resource plans. |
|  | Partnership arrangements in environmental watering activities and with natural resource management groups are proving to be an effective way of embedding First Nations’ knowledge, cultural practices and connection to Country into Basin water management. However, there is scope to do more, including resourcing First Nations to strengthen capacity, and improving how Basin governments work in partnership and share decision‑making. |
|  | Less than 1% of water entitlements in the Basin are held by First Nations people. No water has been purchased under the Aboriginal Water Entitlements Program since it was announced in 2018. The $40 million original program budget will buy less water today than in 2018. |

## 5.1 Some background

### First Nations people’s values, uses and knowledges of water

More than 100,000 First Nations people from over 40 Nations live in the Murray–Darling Basin (MDBA 2023l). As outlined in the Murray–Darling Basin Plan (the Basin Plan), ‘Traditional Owners and their Nations in the Murray–Darling Basin have a deep cultural, social, environmental, spiritual and economic connection to their lands and waters’.[[85]](#footnote-86) Basin health is vital for sustaining Country and connection.

Water energises our country. Water is our driver for bringing everything together to preserve and sustain our country, our Elders, our children and our habitat. (Latji Latji Mumthelang First Peoples, sub. 78, p. 1)

For Aboriginal people the health of the river and the health of people come first. (Dharriwaa Elders Group, sub. 86, p. 3)

First Nations people also have deep knowledge about how to manage water and improve river health, from thousands of years of knowledges about caring for rivers, waterways and wetlands.

We as elders know the right time for water to be delivered and the right amount … (Latji Latji Mumthelang First Peoples, sub. 78, p. 2)

Solutions to the climate crisis must be informed by the knowledge and wisdom of cultures that have survived (and thrived) during significant changes to the climate over the past 60,000 years. (MLDRIN, sub. 92, p. 23)

However, since colonisation, First Nations people have been dispossessed of their lands and waters. This has fundamentally limited the opportunities for First Nations people to determine when, where and how they use water. As the Victorian Government’s *Water is Life – Traditional Owner Access to Water Roadmap*, put it, ‘Australia’s First Nations peoples have been treated as bystanders in the management, allocation, and ownership of water and water landscapes’ (Victorian DELWP 2022b, p. 15). This has significant implications for First Nation people’s economic, emotional, cultural and spiritual wellbeing.

Hartwig et al., commenting on the impacts of ‘water colonialism’ on First Nations people, said:

Many … reflected on past activities relating to their waterways, such as growing up along the river, fishing, celebrating and connecting with those places, its non‑human inhabitants and with other people. However, over‑extraction (particularly upstream), the construction and operation of water infrastructure, and other state‑sanctioned water management policies have caused significant impacts to the health and survival of these water relations and have threatened drinking water supplies. Many interviewees expressed a clear sense of loss for those activities that can no longer take place and described a range of resulting harms that are not being attended to … As access to a healthy and flowing river diminishes, this dispossession affects Traditional Owners’ independence, and abilities to sustain themselves, connect with and pass on customs and practices. (Hartwig et al. 2021, p. 50)

Some participants at the Commission’s First Nations roundtable spoke about the hurt from the damage to Country and the consequences of dispossession (box 5.1).

In addition, Grafton et al. called for truth telling about water injustice.

… ‘truth telling’ about water injustice is a key first step on the pathway towards meaningful change and reconciliation. Transformational change can only come if we avoid post‑truths, prejudices, and superficial judgements and conclusions. The much harder step beyond acknowledging the truths of water injustice is to act in ways that deliver a more just future. (2021, p. 3)

| Box 5.1 – What we heard from some First Nations people – Damage to Country and the need for better balance and communication[[86]](#footnote-87) |
| --- |
| The hurt from the damage to Country   * We all knew that there were beautiful rivers before dispossession. The horse has bolted. It happened when dispossession happened – farmers, miners, overseas water owners came in and took water. * Aboriginal people did not know what the Murray–Darling Basin Plan was. * The water consequences of dispossession are now burdening our community. * Irreversible damage is occurring with banks being degraded and ancestors being exposed. * The hurt from this goes deep. It hits harder when out on Country.   First Nations people are being left behind   * We now live in the context of what’s happened at the referendum. We need to shift to United Nations principles. * First Nations never agreed to the Basin Plan. The Basin Plan does not take into account the views of First Nations. * There needs to be recognition that First Nations come first across the whole Basin Plan.   Achieving a better balance   * Valuable water has been given to irrigators recently – Aboriginal communities need to have water to be relevant in the current water world. What First Nations are being offered is tokenistic. * The Basin Plan needs to look at balance – where can it do that? Environmental, cultural and First Nations.   A need for better communication approaches   * Water is a spiritual thing; it talks to sovereignty. * There is a need to review communication approaches with our people because they’re not working. * Governments don’t do enough to keep track of who has cultural authority, who has a local Aboriginal voice. We find out things too late because there is not enough effort by government. * A forum to bring groups together – government and traditional owners – should be considered. |
|  |

### Requirements in the Basin Plan specific to First Nations people

The Basin Plan has provisions that specifically relate to furthering First Nations people’s interests in, and objectives for, water management. In particular, water resource plans (WRPs) must identify the objectives of First Nations people for managing water resources, and the outcomes that are desired by First Nations people.[[87]](#footnote-88) In doing so, ‘regard must be had to’:

* Indigenous values: the social, spiritual and cultural values of First Nations people that relate to the relevant water resources of the WRP area[[88]](#footnote-89)
* Indigenous uses: the social, spiritual and cultural uses of the relevant water resources of the WRP area by First Nations people.[[89]](#footnote-90)
* the views of First Nations people with respect to cultural flows,[[90]](#footnote-91) and the views of relevant Indigenous organisations on a range of other matters, including native title rights and Indigenous Land Use Agreements.[[91]](#footnote-92)

The Basin Plan also has provisions for First Nations people to provide input into:

* improving the knowledge of water requirements in the Basin relating to the social, spiritual and cultural uses of water resources by Indigenous people[[92]](#footnote-93)
* achieving a heathy and working Basin, including water supplies that are fit for a range of intended purposes – domestic, recreational and cultural uses[[93]](#footnote-94) and to maintain appropriate water quality for environmental, social, cultural and economic activity in the Murray–Darling Basin[[94]](#footnote-95)
* the Basin‑wide environmental watering strategy[[95]](#footnote-96)
* when undertaking environmental watering activities (have regard to Indigenous values, uses, knowledge and experience).[[96]](#footnote-97)

And there is funding provided by governments to support First Nations to participate in Basin Plan implementation and review activities. Two groups – Murray Lower Darling Rivers Indigenous Nations (MLDRIN) and the Northern Murray–Darling Basin Aboriginal Nations (NBAN) – were important in co‑ordinating and facilitating Aboriginal engagement in the earlier period of Basin Plan implementation (and they are explicitly mentioned in the Plan).[[97]](#footnote-98)

The *Water Act 2007* (Cth) and Basin Plan 2012 were also recently amended to better consider First Nations values and uses (box 5.2).

| Box 5.2 – Recent changes to the Water Act and Basin Plan – First Nations values and uses |
| --- |
| Recent amendments to the Water Act and Basin Plan expand:   * the objects of the Water Act (s. 3) to include ensuring ‘that the use and management of Basin water resources takes into account spiritual, cultural, environmental, social and economic matters relevant to Indigenous people, including in relation to their knowledge, values, uses, traditions and customs. * the purpose of the Basin Plan (as defined in s. 20 of the Water Act) to provide for ‘the use and management of Basin water resources that takes into account spiritual, cultural, environmental, social and economic matters relevant to Indigenous people’.   The Murray–Darling Basin Authority (MDBA) must, when reviewing the Basin Plan, consider and report on:   * matters relevant to Indigenous people in relation to the management of Basin water resources including, but not limited to, the extent to which Basin water resources could be managed so as to improve the spiritual, environmental, cultural, social and economic conditions of Indigenous people * the extent to which the Basin Plan, including requirements relating to water resource plans: recognises and protects the interests of Indigenous people; and supports opportunities for Indigenous people to participate in determining and developing priorities and strategies for the development or use of Basin water resources, including opportunities for participation that incorporates free, prior and informed consent (ss. 50 (4)).   The Secretary [of the Department of Water] must produce annual reports that include information:   * provided by the MDBA about how ‘holders of held environmental water … considered Indigenous values and Indigenous uses’ and ‘involved Indigenous people’ * about engagement and other activities undertaken for the purpose of ensuring that the management of Basin water resources takes into account spiritual, cultural, environmental, social and economic matters relevant to Indigenous people’ and ‘any other matter specified by the Minister in writing’ (Division 6).   The MDBA members must include ‘2 Indigenous people recognised in the Indigenous community as having a high level of expertise in Indigenous matters relevant to Basin water resources’ (s177).  The review of the Water Act in 2027 must ‘identify opportunities … to promote the principles set out in the United Nations Declaration on the Rights of Indigenous Peoples’ (ss 253(1)).  Source: *Water Amendment (Restoring Our Rivers) Act 2023* (Cth). |
|  |

There are some First Nations people, however, who do not accept the Basin Plan (box 5.1). MLDRIN noted that the ‘Basin Plan as a whole, and its individual provisions, largely override or ignore Basin Nations’ rights and obligations relating to waters and rivers’ (sub. 92, p. 3).

We stress that Basin Nations’ rights and interests in water and waterways are holistic and distinct, and they are affected by multiple aspects of the plan implementation. Basin Nations’ rights and interests are both *sovereign* and *central* to water management in the Basin. A key message … that because the Basin Plan fails to recognise this to start with, it is impossible for Basin Plan implementation to address Basin Nations’ rights and interests. (MLDRIN, sub. 92, p. 3)

Other First Nations people were more supportive of the Basin Plan. For example, the Latji Latji Mumthelang First Peoples said:

We understand a holistic view of Basin water and hold a position of getting water back on country by any means and in as natural a pattern as possible. We believe the support to do this starts with the Basin Plan. We are fully behind the Basin Plan being delivered … (sub. 78, p. 1)

### All Basin governments have made policy commitments under the National Agreement on Closing the Gap

The policy landscape has changed considerably since the Murray–Darling Basin Plan was introduced in 2012 and since the Commission last reviewed Basin Plan implementation in 2018.

In 2020, all governments, along with the Coalition of Aboriginal and Torres Strait Islander Peak Organisations, signed the *National Agreement on Closing the Gap* (the Agreement). The central pillars of the Agreement are four Priority Reforms.

* Priority Reform 1 – Formal partnerships and shared decision making.
* Priority Reform 2 – Building the Aboriginal and Torres Strait Islander community‑controlled sector.
* Priority Reform 3 – Transforming government organisations so they work better for Aboriginal and Torres Strait Islander people.
* Priority Reform 4 – Improving and sharing access to data and information to enable Aboriginal and Torres Strait Islander communities to make informed decisions.

These reforms require changes to the way governments work with Aboriginal and Torres Strait Islander people across all areas of policy and program delivery, including implementation of the Basin Plan. When signing the Agreement, governments made a commitment to ‘a fundamentally new way of developing and implementing policies and programs that impact on the lives of Aboriginal and Torres Strait Islander people’ and to do so in a way that ‘takes full account of, promotes, and does not diminish in any way, the cultures of Aboriginal and Torres Strait Islander people’ (Australian Governments and Coalition of Aboriginal and Torres Strait Islander Peak Organisations 2020, pp. 2–4).

Performance monitoring and public reporting arrangements to support transparency and accountability for progress against outcomes are also part of the Agreement.

There has also been a shift in recognition of First Nations in the community since the Basin Plan was put in place. As noted by the MDBA:

Since the Basin Plan came into force there has been an important shift in the recognition of First Nations people’s values and uses of water across the Basin. Community expectations and knowledge on these issues has progressed considerably over the last decade and there is much more to be done. (sub. 61, response to information request, p. 5)

Improving outcomes for First Nations people will be one of the key themes for the 2026 Basin Plan Review, along with the need for regulatory changes to facilitate greater involvement of Aboriginal and Torres Strait Islander people in Basin Plan policy setting and decision‑making. The MDBA said ‘we’ll work with First Nations people, supporting them to gather and provide input, including testing policy options’ (MDBA 2023l, p. 9).

## 5.2 Assessing progress: 2019 to 2023

There has been a lot of activity over the past five years aimed at increasing the involvement of Aboriginal and Torres Strait Islander people in water management in the Basin (box 5.3). Basin state governments have improved how they work, engage and partner with First Nations people in the Murray–Darling Basin, particularly in environmental watering activities and WRP development activities (in most Basin states).

### Environmental watering

All Basin state governments are working more with First Nations people to plan and manage environmental watering activities in the Basin (chapter 3).

First Nations people are now more directly involved in key Basin‑wide environmental watering processes –MLDRIN joined the Southern Connected Basin Environmental Watering Committee in 2021, and First Nations people have been represented on the Northern Basin Environmental Watering Group since 2019 (chapter 3). Both these groups coordinate planning and the delivery of water for the environment to enhance cross‑border and multi‑catchment connectivity, drawing on First Nations people’s knowledge and values of river systems.

Other important developments in the area of environmental water since the Commission’s assessment in 2018 include the:

* *2019‑20 First Nations Environmental Water Guidance Project* – thisproject seeks to better integrate First Nations outcomes directly into Basin Plan water management by synthesising the environmental watering priorities of 16 southern Basin Nations (PC 2021c, supporting paper C, p. 45)
* *First Nations Environmental Watering Statement 2021‑22* – sets out southern Basin Traditional Owners’ preferred outcomes from environmental water management and Aboriginal people’s views on the legal, policy and governance settings affecting water management in the southern Basin (MDBA, sub. 61, p. 23)
* *First Nations Environmental Water Partnership Pilot Program* – in the May 2023 Budget, the Commonwealth Environmental Water Holder received $3.5 million to establish this program. The Commonwealth Environmental Water Holder is seeking to embed First Nations people’s knowledge and science into the future science program (Flow‑MER 2.0) to ensure environmental watering is underpinned by the best available knowledge (DCCEEW, sub. 77, p. 18).

There is also better reporting on how the values of First Nations people are considered in the planning and delivery of water for the environment in the Basin, drawing on information from the MDBA, Basin state and territory governments, and First Nations people.

### Water resource plans

As discussed in chapter 4, Basin state and territory governments are responsible for developing WRPs in accordance with the requirements set out in the Basin Plan, including those specific to Aboriginal and Torres Strait Islander people. In doing so, the person or body preparing a WRP ‘may’ identify opportunities to strengthen the protection of Indigenous values and Indigenous uses and, if identified, must specify them in the WRP.[[98]](#footnote-99)

The MDBA is responsible for assessing WRPs against these provisions and are expected to consult with relevant Indigenous organisations when making this assessment.[[99]](#footnote-100) Subject to the outcome of this assessment, the MDBA is also responsible for making a recommendation to the Minister for Water about whether to accredit the WRP.

The Commission’s 2018 assessment found that Basin states had improved their formal processes for engaging Traditional Owners as part of water resource planning development, but warned that compressed timelines for WRP accreditation risked having too little time for effective engagement and having regard to the views of Traditional Owners in preparing water resource plans (PC 2018, p. 209).

In this inquiry, we heard mixed reports about the ways Basin governments have worked with First Nations people when developing WRPs.

A number of participants emphasised that the NSW Government has failed to address key gaps in their WRP processes, including limited or no consultation with all Nations identified in WRPs, a lack of clarity about the scope and purpose of the engagement, and insufficient time for participants to respond or follow up when substantial issues or concerns emerge. For example, the NSW Aboriginal Land Council outlined concerns about the NSW Government’s failure to include input from Aboriginal communities (sub. 101, p. 8) and MLDRIN said:

… some Traditional Owners were unaware that their WRP consultation was supposed to address both surface waters and groundwater relevant to multiple WRPs. Instead, the NSW Government used outcomes from what Nations understood to be surface water‑focused consultation to meet Basin Plan requirements of its groundwater WRPs. (sub. 92, p. 6)

The NSW Government, however, noted that:

Our WRPs are all informed by extensive local consultation with First Nations people on a Nation‑by‑Nation basis, rather than a broader approach by WRP area, aimed at improving efficacy and honouring connection to Country. … We are progressing further engagement with First Nations across the Basin in line with commitments within accredited WRPs. This engagement is commencing in the Border Rivers/Namoi/Gwydir areas first, before extending to all areas of the Basin. (sub. 111, p. 10)

First Nations consultations are published in Consultation Reports, as Schedules to NSW’s accredited WRPs.[[100]](#footnote-101)

The Commission also heard concerns about the narrow scope of the relevant Basin Plan provisions.

… [the] focus is only on the social, spiritual and cultural values and uses (section 10.52(2)) and objectives and strategies (section 10.53(1)(d)). Traditional Owners have expressed deep dissatisfaction that this scope excludes economic or environmental values, uses, and objectives from consultation conversations and legal consideration in water resource planning.   
(MLDRIN, sub. 92, p. 15)

Several participants expressed frustration that WRPs were assessed by the MDBA and accredited by the Australian Minister for Water despite First Nations groups raising significant concerns during the assessment process. For example, the Environmental Defenders Office highlighted that:

… the Authority has endorsed a ‘Nations based’ approach to First Nations engagement. However, when the rubber hit the road in NSW, the substantial and material issues raised in the First Nations assessments as to compliance with the Basin Plan appear to have made little to no difference to the accreditation decisions. (sub. 91, p. 28)

Notwithstanding these concerns, the Commission also heard that there were better outcomes when advice from First Nations people about WRPs was considered and acted on. MLDRIN, for example, said:

Victoria’s responsiveness in addressing gaps in WRPs saw Nations’ procedural rights respected and led to better outcomes and improved relationships with Aboriginal people. Arguably, the relationships and improved processes that were developed between Nations and the Victorian Government during this period have contributed to other ongoing positive outcomes beyond the Basin Plan, such as ensuring a good foundation for more recent work … (sub. 92, pp. 5–6)

In some respects, the frustrations and experiences of First Nations people about the development of WRPs is unsurprising. Prior to the recent Basin Plan amendments, there were no formal requirements for Basin state governments to meaningfully and consistently take account of, and address, the objectives of Aboriginal and Torres Strait Islander people (and the outcomes for water management they would like to see) when developing WRPs. The Basin Plan requirement to ‘have regard to’ these matters can be (and clearly has been, in some cases) interpreted in a minimal way, with limited accountability. This issue is discussed further in section 5.3.

### Engaging and partnering with First Nations people

Basin governments have sought to improve how they engage and partner with First Nations people on Basin Plan issues, beyond environmental watering and WRP consultations, over the last five years. Examples of policies aimed at improving engagement are provided in box 5.3.

| Box 5.3 – Examples of recent policies aimed at improving engagement and partnerships with First Nations people |
| --- |
| The Australian Government’s Department of Climate Change, Energy, the Environment and Water (DCCEEW) recently released a Statement of Commitment to First Nations which has components to deepen engagement with Aboriginal and Torres Strait Islander people. It aims to deliver on the National Agreement on Closing the Gap targets and advance key policy priorities that directly relate to Aboriginal and Torres Strait Islander people, including water. The Statement acknowledges the value of Indigenous knowledges.  Our work will recognise that Indigenous knowledge is critical to living sustainably in Australia. The 65,000 years of knowledge that Aboriginal and Torres Strait Islander peoples hold as custodians of Australia’s land and natural resources is essential to achieving our vision. Traditional knowledge will be used with permission and respect of Indigenous cultural and intellectual property. (DCCEEW 2023k, p. 2).  The 2017 Aboriginal Partnership Action Plan, reviewed and updated in 2022, has become the  Murray–Darling Basin Authority Strategy for Engagement with First Nations (2022–26). The Strategy outlines the MDBA’s objectives for cultural flows, partnerships and collaboration, embedding action and participation, knowledge, research and policy and reconciliation. It also outlines MDBA’s vision to achieve healthy rivers by incorporating First Nations’ science, expertise, knowledge and values in water management (sub. 61, response to information request, p. 27).  An Aboriginal member was also appointed to the MDBA Board (MDBA 2020h, p. xxii) and Aboriginal representation on the Basin Community Committee was increased to more effectively incorporate Aboriginal values and uses in Basin water management.  The Queensland Government allocated $11.7 million over 3 years for a First Nations Water Strategy to support partnerships with First Nations people in water management (QLD DRDMW 2023b). The Strategy follows the passing of the *Path to Treaty Act 2023* (Queensland Government 2023a).  The South Australian Government has committed to strengthening partnerships with First Nations people through several initiatives, including the *First Nations Voice Act 2023* (SA Government 2023c) and the signing of a ‘Statement of Commitment’ to collaborate with First Nations people to manage, protect and restore landscapes, by each of the 9 regional landscape boards (SA Government 2023b). The South Australian Aboriginal Partnerships Program also aims to increase the participation of Aboriginal people, groups and organisations in all levels of landscape management, including environmental watering and wetlands management (SA Government 2023a).  The Victorian Government’s *Water is Life – Traditional Owner Access to Water Roadmap* sets out a pathway for how the Victorian Government intends to return water to Traditional Owners and increase their role in environmental watering (Victorian DELWP 2022b, p. 41). |
|  |

The Commission heard about partnerships between First Nations and governments that were working well, including to deliver environmental water in ways that also achieve cultural benefits. For example, we heard that the *National Cultural Flows Research Project* – a project supported by the MDBA and other Australian Government agencies – has helped to improve knowledge of cultural flows and identify ways of integrating cultural flows into Basin water management.

*The Murray–Darling Basin Indigenous River Rangers Program*, the *First Nations Environmental Water Guidance Project*, and partnership programs implemented by Catchment Management Authorities, were also highlighted. Inquiry participants stated that these programs effectively draw on, and enhance, First Nations people’s knowledges and understanding of river systems and natural resource management, to help design and implement water management practices and policies.

Dharriwaa Elders Group (DEG) River Rangers now provide DEG with a daily observation capability and have turbo‑charged DEG’s evidence and knowledge base. They have observed and reported two Walgett native fish kills in February and August 2023. They are observing Walgett water quality, the disappearance of mussels and other river invertebrates and the triumph of European carp and other invasive species. (sub. 86, p. 4)

Catchment Management Authorities have a lot of skills we don’t have here, hence the importance of partnerships. (Wamba Wamba First peoples representative, pers comm., 27 June 2023)

The Kolety Werkul Indigenous Ranger program is improving the connection with local Traditional Owners. They do fish, fish lavae and turtle monitoring, they put cameras out when the floods came to see the water going up and down. They’ve done GIS mapping training and various other things. The ranger programs mean you’ve got members of the local community that can be engaged by all agencies involved in monitoring. There is no excuse that work can be done without First Nations involvement. (Yarkuwa Indigenous Knowledge Centre, pers. comm., 8 June 2023)

The Senate Select Committee on the Multi‑Jurisdictional Management and Execution of the Murray–Darling Basin Plan also heard from Dr Phil Duncan, then Chair of the Basin Community Committee, about the value of partnerships:

… now the time is for us to be more engaged in repairing our country. We are seeing rivers go on to evolutions and change in flow regimes. We are seeing less and less water going in. If you look at the 150 year research around climate change, I believe that our people have a significant range of knowledge that can help the basin recover and be more sustainable into the future. (Duncan in Australian Government 2021, p. 147)

The knowledges of First Nations people are also being drawn on increasingly via Basin state projects and initiatives. For example:

* The Victorian Department of Environment, Land, Water and Planning is funding 17 Aboriginal water officers in the Basin to deliver projects in partnership with government and Traditional Owner organisations (sub. 74, response to information request, p. 82).
* The Victorian Government has set aside 1.36 gigalitres of additional water savings from the Goulburn Murray Connections project for Traditional Owners in northern Victoria (GMW 2022).
* The NSW Government is establishing Regional Aboriginal Water Committees to provide advice to the Department of Planning and Environment where it affects Aboriginal water rights. The Committees will inform water management policy, projects and programs as they apply to Aboriginal people (sub. 43, response to information request, p. 20).
* The *Queensland Water Act 2000* was amended to allow for recognition of the importance of water to Aboriginal and Torres Strait Islander people by providing for water plans to include cultural outcomes. This builds on existing mechanisms that provide a statutory right to take water for traditional activities or cultural purposes (Queensland Government 2023b).
* The ACT Water Strategy 2014–44 Striking the Balance Implementation Plan Two (2019–23) outlines   
  18 actions, including to: ensure Aboriginal representation on governance bodies; establish an Upper Murrumbidgee Aboriginal Nations Group; empower local communities to share their knowledge of land and water; and investigate arrangements for Indigenous cultural flows.   
  (ACT Government 2019, pp. 18–21).

The ambition set out in these initiatives is encouraging. However, such initiatives do not automatically lead to improved outcomes for First Nations people. Despite increased efforts by Basin governments to engage First Nations people in water planning and management, particularly in environmental watering, the Commission heard concerns about current processes and calls for Basin governments to do more to empower First Nations people in Basin water planning, management and ownership.

## 5.3 Strengthening the role of First Nations people in the Basin Plan

Almost everyone with an interest in the Basin agrees that the Basin Plan needs to do more to deliver on the values and interests of First Nations people (box 5.4).

The Commission also heard that Basin governments’ engagement practices often fall short (especially around WRPs in NSW) and the capacity of First Nations people and organisations to participate in key processes is being stretched.

| Box 5.4 – Calls to do more: recognising the values and delivering on the interests of First Nations people |
| --- |
| Murray–Darling Basin Authority  The deep significance of First Nations’ knowledge passed down over the generations is ever more pressing and more precious as our climate changes. We all need to work harder to provide a greater place for First Nations people in water management. (sub. 61, p. 7)  National Irrigators’ Council (NIC)  … we are very supportive of further involvement of Indigenous Australians in managing the Basin, including but not limited to, addressing cultural flows. … NIC would welcome an enhanced First Nations engagement regime to further improve our connections with Indigenous peoples across the Basin. (sub. 62, p. 26)  National Parks Association of NSW  The independence and views of the numerous Aboriginal Nations with a connection to the Basin and its water should not be compromised. Water carries great cultural, spiritual, environmental, social and economic significance to these people … Despite the National Native Title Council (2014) stating it believed the Water Act was failing in its management objectives for Aboriginal people some ten years ago, not much has changed. (sub. 41, p. 6)  The NSW Aboriginal Land Council  The NSW Government needs to work more closely with existing Aboriginal structures, such as LALCs [Local Aboriginal Land Councils] and Indigenous ranger programs on future water management approaches and to take into account Aboriginal people’s knowledge and wisdom. (sub. 101, pp. 9–10)  Wentworth Group of Concerned Scientists  … . the next Plan needs to address Aboriginal water rights and interests as a matter of urgency. More support is needed to build capacity of Indigenous land and water ranger programs to manage wetland Country. (sub. 81, p. 6)  River Lakes and Coorong Action Groups  We need to celebrate the wisdom of First Nations people in caring for the land and the water for millennia while it has only taken 235 years of settlement to destroy the system. We need to acknowledge the deep connection of First nations people to the land and to their totems and the intrinsic need to protect them. (sub. 15, p. 4) |
|  |

### Engagement is not always meaningful

First Nations people – many of whom have invested a lot of time participating in the Basin Plan and reviews of it – expressed concerns about engagement processes. They said engagement processes were often rushed and tokenistic, and their input rarely influenced decisions. There was a sense that government representatives only engage with First Nations people ‘to tick a box,’ rather than to understand and genuinely consider First Nations perspectives in decision‑making (box 5.5).

| Box 5.5 – Meaningful engagement? What First Nations people said … |
| --- |
| Latji Latji Mumthelang First Peoples  We as First Peoples have not been properly connected to decision makers. There is disconnect between our interests on country and these reaching and being considered by the eventual decision makers above local government departments and authorities. (sub. 78, p. 2)  Werai Land and Water Aboriginal Corporation  We’re not involved in any process as such. We were not consulted. After the fact, after the stuff is done, then they want to speak to us to get us to tick the box and approve what they’ve done. (Taylor in Australian Government 2021, p. 128)  First People of the Millewa Mallee Aboriginal Corporation  You should have various focus groups from each area and then feed this all into decision‑making bodies, so that we get peoples’ ideas to decision makers. (pers. comm., 27 June 2023)  Yarkuwa Indigenous Knowledge Centre  When government do come out so much is already set, so they don’t hear much when they come out … River operators and others from MDBA and NSW pick particular people to meet with rather than connect with local Traditional owners. (pers. comm., 8 June 2023) |
|  |

The Commission also heard that there is little two‑way exchange to understand whether and how input has influenced decisions, or otherwise been worthwhile. This concern was especially prevalent around the development of WRPs. The National Parks Association of NSW, for example, said:

Many of the water resource plans created by the states only give scant reference to Indigenous peoples’ water … States have given inadequate provision to ensure consistent engagement with Indigenous people. (sub. 41, p. 7)

And MLDRIN said:

We’ve had lots of meetings with MDBA since 2019 but our advice is not being considered. We’re being disregarded. [Water Resource] Plans being approved against our advice feels token again. We’re not being listened to. We’ve been duped in this process – we thought this [assessment role] was a good process and we were keen to be part of it. Now we have nothing really to show for it. There’s disregard for us. We’ve never ceded our rights to water and there’s no recognition of that anywhere. We’re pretty disappointed. (sub. 92, p. 14)

Consultation fatigue and frustration is evident across the Basin.

Consultation experiences for some NSW Traditional Owners has been so poor that it has nearly completely undermined their trust in the NSW Government, the MDBA, and any other water related consultation processes more broadly (MLDRIN, sub. 92, p. 14).

Contributing to engagement processes can be particularly difficult for participants if unnecessarily complex and technical language is used.

The language of water management is not always well understood by Indigenous people. Water sector language can be highly technical and results in the alienation of Indigenous knowledge and values. Conversely, cultural values of water are often poorly understood by water managers. (Jackson 2015 in Moggridge and Thompson 2021, p. 7)

First Nations groups are somehow expected to understand complex legal documents. We’re not scholars, it’s all practical. (Barkindji Maraura Elders Environment Team Limited, pers. comm.,  
27 June 2023)

The dominance of the water experts come in with all this jargon and they talk to each other. You have to come down and have a chat like the yarn along the river. (Yarkuwa Indigenous Knowledge Centre, pers. comm., 8 June 2023)

We also heard concerns about consultations on sustainable diversion limit adjustment mechanism (SDLAM) projects. For example, the Millewa Mallee Aboriginal Corporation expressed concern about a cancelled SDLAM project in Victoria and the way this was communicated:

The Murray Floodplain Program by the Victorian Government was amazing before it was scrapped. The whole ecosystem came back to life and it was restored into a living cultural area. We were never told why it was scrapped. (pers. comm., 27 June 2023)

The Yarkuwa Indigenous Knowledge Centre also conveyed:

There’s no knowledge of what’s going on. We have no confidence in the protection of sites and there’s a risk of harm. We went out and identified some things around the weir. We found some sites and they didn’t protect them but just said they’d move the weir. (pers. comm., 8 June 2023)

Related to the issue of meaningful engagement is the way knowledges of First Nations people are recognised and valued in Basin water management. The Basin Plan has a commitment to using ‘best available knowledge’ in water resource management (chapter 6), which includes the knowledge of First Nations people. A number of participants commented that there is scope for Basin governments to better draw on First Nations people’s knowledges and understanding of the river systems and natural resource management (box 5.4).

While Basin governments have improved how they engage with First Nations people in the Murray–Darling Basin over the last five years, there is scope for Basin governments to:

* be more accountable for the outcomes of First Nations engagement processes
* strengthen the role of First Nations people in Basin water management (including in key decision‑making processes)
* demonstrate their commitment to the priority reforms in the *National Agreement on Closing the Gap*.

### First Nations capacity to engage in processes is being stretched

There is a significant and growing pull on First Nations groups and individuals to participate in government processes about the Basin. Participants said that the capacity of First Nations organisations to attend meetings, sit on working groups and write submissions does not match the demands being put on them.

It is imperative that governments … listen to and learn from the ways Indigenous populations wish to manage water … and recognise that the security of long‑term indigenous water management may require some form of support to ensure the governance mechanisms around indigenous water use remain healthy and vibrant. (National Parks Association of NSW, sub. 41, p. 8)

Deep participation by First Nations in regulatory decision making that affects their Country requires resourcing that will facilitate and scaffolds such participation. (Environmental Defenders Office, sub. 91, p. 30)

One of the principles of good water governance (chapter 1) is providing support to groups that are less represented to engage in decision‑making processes. For example, the Organisation for Economic   
Co‑operation and Development’s Principles on Water Governance highlight the importance of ‘paying special attention to under‑represented categories such as youth, the poor, women, Indigenous people’ and ‘encouraging the capacity development of relevant stakeholders’ (OECD 2015, p. 12).

And as noted earlier, the *National Agreement on Closing the Gap* commits governments to ‘building and strengthening structures that empower Aboriginal and Torres Strait Islander people to *share* decision‑making authority with governments’ (Priority Reform 1). Policy partnerships – partnerships created for the purpose of working on discrete policy areas – are a key mechanism identified in the Agreement to help achieve this. Such partnerships will require investment by governments and enactment of power sharing arrangements if decisions are to be made jointly with Aboriginal people (PC 2023, p. 3).

Governments seeking to engage with First Nations people in the Basin have relied heavily on MLDRIN and NBAN. However, the MDBA has ended its contract with NBAN. While MLDRIN has continued to actively engage in consultation processes and has made submissions to several reviews, some participants told the Commission that MLDRIN no longer has broad support by all First Nations.

Basin governments have started to shift their Basin Plan (and other) engagement practices to focus more on individual Nations and smaller groups of Nations. The MDBA noted that:

Some First Nations are indicating to the MDBA they prefer to have a direct involvement with government, and that engagement with individual Nations or smaller groups of affiliated Nations is preferred, rather than engagement through larger coordinating bodies. (sub. 61, p. 24)

Inquiry participants also called on governments to do more to strengthen the capacity of First Nations organisations to engage in key processes:

Experience shows that community consultation and engagement can be improved by resourcing local Aboriginal community‑controlled organisations … to engage their own independent water researchers and advisors … (Dharriwaa Elders Group, sub. 86, p. 11)

The MDBA needs to establish funded partnership arrangements directly with Nations as well as with their preferred peak bodies, such as MLDRIN and NBAN. Basin Nations and their peak bodies need to be set up for genuine and sustained success in working with dominant settler state agencies, including ongoing, sustainable investment that is commensurate with Nation‑determined functions. (MLDRIN, sub. 92, p. 24)

A view articulated by some First Nations participants at the Senate Committee hearings on the Water Amendment (Restoring Our Rivers) Bill 2023 was that non‑Indigenous people’s capacity and abilities also need to be improved. Kate Harriden, Research Fellow, Indigenous Water, Monash University, for example, said:

We spend a lot of time as a nation‑state talking about needing to improve Indigenous people’s capacity … There’s actually an onus on non‑Indigenous people. Particularly post the referendum, it’s so clear that, actually, the non‑Indigenous community has a lot of work to do before there can be these good relationships, and that’s not because of mob. (Senate Environment and Communications Legislation Committee 2023a, p. 13)

A summary of the views of some First Nations people on cultural capacity and shared decision‑making, conveyed at the First Nations roundtable held by the Commission, is in box 5.6.

| Box 5.6 – Cultural capacity and shared decision‑making – what we heard from some First Nations people[[101]](#footnote-102) |
| --- |
| **Cultural capacity**   * Cultural capacity embodies a depth of knowledge in the fields of water quality, water management and wellbeing, which is being consistently overlooked at every tier of government. * Cultural capital is not as valued as farming enterprise and needs to be considered, especially if we want to move any of the Basin Plan forward. * Now governments want to learn from First Nations’ wisdom but they didn’t listen in the first place.   Shared decision‑making   * Can we work together as a collective to improve water quality – for better health and long‑term health of Country and waters to achieve outcomes for future generations? * How will our research ever be used? It hasn’t been to date. * Practical measures need to be implemented to save the Murray–Darling Basin waters and manage water in the interests of Australia, not bureaucrats. |
|  |

### What more can be done?

The Commission sought to identify practical and cost‑effective actions that Basin governments could take to:

* better achieve First Nations people’s objectives and Basin Plan outcomes
* demonstrate their commitment to the priority reforms of the *National Agreement on Closing the Gap*.

#### Greater transparency on how the values and objectives of First Nations people are incorporated in water resource plans

Prior to the recent Basin Plan amendments, there was little accountability on Basin states to meaningfully consider and address the objectives of First Nations people (and their desired outcomes for water management) in making WRPs. This is at odds with governments’ commitments to share decision‑making and work in formal partnerships with Aboriginal and Torres Strait Islander people under the *National Agreement on Closing the Gap*.

The 2023 amendments to the Basin Plan:

* Expand the purpose of the Plan to provide for ‘the use and management of Basin water resources that takes into account spiritual, cultural, environmental, social and economic matters relevant to Indigenous people’.
* Require that the MDBA, in reviewing the Plan [in 2026], consider and report on the extent to which the Plan, including water resource plan requirements: recognises and protects the interests of Indigenous people; and supports opportunities for Indigenous people to participate in determining and developing priorities and strategies for the development or use of Basin water resources (box 5.2).

These are important revisions and place a greater onus on Basin states to ensure water resource plans take into account the interests of First Nations people.

Accountability and transparency on how the values and objectives of First Nations people are incorporated in water resource plans could be further improved by Basin States publicly reporting on:

* the input and advice received from First Nations people and organisations on draft WRPs, and proposed amendments to WRPs
* how this advice is considered, actioned and reflected in submitted and finalised WRPs and amendments.

Such reporting would be a valuable input to the Basin Plan Review, given the requirement to review progress towards recognising and protecting First Nations, and is important for strengthening relationships with First Nations people in the Basin.

#### Public reporting on how governments engage with First Nations people on Basin Plan matters

To date, there has been no comprehensive reporting on whether and how Basin governments engage with First Nations people on Basin Plan implementation, or how insights and views shared by First Nations participants are considered in Basin Plan water management processes and decisions.

This limits any assessment of the scope, effectiveness and outcome of governments’ efforts on engagement with First Nations people. And without public reporting, as noted by some participants, government accountability for engagement with First Nations people on Basin Plan implementation is weak.

… state and territory governments should be held to account for how they consider and action advice from Aboriginal and Torres Strait Islander people, but further consideration is needed on how this is achieved. Approaches should be centered on the principles of self‑determination and free, prior and informed consent, respecting the rights and objectives of Traditional Owners. (Department of Energy, Environment and Climate Action, Victorian Government, sub. 131, p. 3)

Better monitoring and reporting can:

* assist in holding Basin governments to account on how they engage and share decision‑making with First Nations people on water resource plans, environmental watering and other aspects of Basin Plan policy and program development
* highlight gaps in engagement processes and opportunities for collaboration and streamlining
* allow for learnings to be shared and engagement processes to be refined and improved.

Recent changes to the Water Act and Basin Plan require annual reporting about First Nations engagement activities (box 5.2). This new annual reporting should cover all Basin governments and Basin states should provide information on their First Nations engagement activities for the purposes of these reports.

It is also important that First Nations people are directly involved in shaping the forthcoming annual Secretary reports on First Nations engagement activities. The MDBA should work in partnership with First Nations people to develop a framework for monitoring how Basin governments engage with First Nations people on Basin Plan matters. The framework should identify:

* what should be monitored and reported on (for example, what information or data could be used to measure the quantity, quality and/or effectiveness of engagement practices)
* how monitoring and reporting will be undertaken (including processes for ensuring the veracity of reported information). This could include collecting information on what Basin state agencies heard in consultations with First Nations people and their response to the issues raised.
* how engagement outcomes will be documented and published.

The framework should be developed and implemented ahead of the upcoming Basin Plan Evaluation and Basin Plan Review.

#### Invest in partnerships and the capacity of First Nations to have enhanced roles in decision‑making

##### Policy and place‑based partnerships for shared decision‑making

The commitment by Basin governments to a fundamentally new way of developing and implementing policies and programs that impact on the lives of Aboriginal and Torres Strait Islander people has direct implications for how the Basin Plan is to be implemented, evaluated and changed over time.

Formal partnership arrangements between Aboriginal and Torres Strait Islander people and governments at all levels is one aspect of the National Agreement commitments. There is considerable scope for (and potential benefit from) establishing genuine partnership arrangements between Basin governments and First Nations people on water management and water policy matters, including to deliver environmental water in ways that also achieve cultural benefits. As one participant said:

There should be more partnership programs involving Aboriginal water managers and rangers, such as the Nimmie‑Caira project, which is training traditional owners in management of watered sites. (Dr Anne E Jensen, sub. 39, p. 3)

As the National Agreement makes clear, ‘adequate funding is needed to support Aboriginal and Torres Strait Islander parties to be partners with governments in formal partnerships’ (p. 2). In addition, it is important that Basin governments recognise that First Nations people’s knowledge about water management is the cultural and intellectual property of Aboriginal and Torres Strait Islander people, and respect relevant protocols and permissions around use of this knowledge.

##### Enhancing First Nations involvement in Basin decision‑making

It is important to recognise the value of engaging with different Basin Nations, and that peak or representative bodies do not necessarily speak for First Nations people (nor do they intend to). However, a collective body or group/s can be a valuable additional model for individuals and groups to communicate concerns, advocate for change, and respond to the ideas and proposals of others. For governments, engaging with such bodies is established practice with various practical benefits.

While there may be value in establishing a new body, or a number of bodies, to represent First Nations’ interests in Murray–Darling Basin Plan decision‑making, this is a decision for First Nations people living in the Basin. The expertise and knowledges of First Nations people throughout the Basin, including members of existing bodies such as the Committee on Aboriginal and Torres Strait Islander Water Interests and the Basin Community Committee, could be used to help establish any new body. As part of the upcoming Basin Plan Review, the MDBA – in partnership with First Nations people – should consider how best to work with First Nations people in implementing the Basin Plan, given existing references to MLDRIN and NBAN in the Plan.

Government agencies should also be as ‘joined up’ as possible when engaging with First Nations people in the Basin – to create efficiencies and to reduce the need for people to convey their views many times (and the frustration and fatigue this leads to). Effective engagement is further discussed in chapter 9.

##### Early planning of First Nations engagement activities is key

The upcoming Basin Plan Evaluation and Basin Plan Review are opportunities for advancing the interests and objectives of First Nations people in the Murray–Darling Basin. The MDBA said its engagement activities will be guided by the Akwé: Kon Guidelines, to ensure First Nations people are engaged in a respectful manner and with free, prior and informed consent (box 5.7). However, while there is a framework for the Basin Plan Evaluation, it does not include a plan for First Nations engagement or articulate how First Nations objectives and outcomes will be evaluated (MDBA 2022j).

| Box 5.7 – Free, Prior and Informed Consent is central to effective engagement |
| --- |
| In 2007, the United Nations General Assembly adopted the United Declaration on the Rights of Indigenous Peoples, recognising their rights and making specific mention of Free, Prior and Informed Consent (FPIC) as a pre‑requisite for any activity that affects their ancestral lands, territories and natural resources.  FPIC is a principle protected by international human rights standards that state, ‘all peoples have the right to self‑determination’ and – linked to the right to self‑determination – ‘all peoples have the right to freely pursue their economic, social and cultural development’. Backing FPIC are the United Nations Declaration on the Rights of Indigenous Peoples (UNDRIP), the Convention on Biological Diversity and the International Labour Organization Convention 169 that recognises Indigenous peoples’ right to self‑determination within a nation‑state. … United Nations (2007)  The Akwé: Kon Guidelines are voluntary and designed to facilitate the full involvement of Indigenous and local communities in the assessment of the cultural, environmental and social impact of proposed developments on sacred sites and on lands and waters they have traditionally occupied. The guidelines, which represent best practice, were endorsed by the Parties to the Convention, including Australia, in 2004 (Secretariat of the Convention on Biological Diversity 2004). |

To foster meaningful and effective engagement with First Nations people in these forthcoming processes, the MDBA – in partnership with First Nations people – should plan how, when and where it will engage with First Nations people and publicise these plans well in advance. In doing so, the MDBA should articulate the desired outcomes from engagement and ensure all Basin Nations across the Basin are provided genuine opportunities to participate.

|  | Recommendation 5.1  Strengthen the roles of First Nations people in the Basin Plan |
| --- | --- |
| In line with the priority reforms committed to under the National Agreement on Closing the Gap, Basin states should:   * publish the input and advice received from First Nations people and organisations on draft water resource plans * publicly report on how the advice is considered, actioned and reflected in finalised and amended water resource plans.   In addition, the Murray–Darling Basin Authority should:   * in partnership with First Nations people, develop a framework for monitoring and reporting on how Basin governments engage with First Nations people on Basin Plan matters. This should be in place before the 2025 evaluation of the Basin Plan * in partnership with First Nations people, consider how best to work with First Nations people on Basin Plan implementation, given existing references in the Plan to Murray Lower Darling Rivers Indigenous Nations (MLDRIN) and the Northern Murray–Darling Basin Aboriginal Nations (NBAN).   Basin states should provide the Secretary of the Australian Government Department of Water with information about First Nations engagement on Basin Plan water management matters, for the purpose of the Secretary’s annual reports on First Nations engagement.  All Basin governments should:   * actively pursue opportunities to work in formal partnership with First Nations people on the implementation of, and shared decision‑making about, the Basin Plan and provide funding and capacity strengthening support to these partnerships * work in partnership to develop, then make public, their First Nations engagement intentions early, including for the upcoming 2025 Basin Plan Evaluation and 2026 Basin Plan Review. | |
|  | |

## 5.4 First Nations ownership of water in the Basin

### Background

Water ownership is important for realising First Nations people’s cultural, social, economic, spiritual and environmental values and interests. The Basin Plan does not define ‘cultural flows’ but recognises that the following definition is used by NBAN and MLDRIN:

Water entitlements that are legally and beneficially owned by the Indigenous Nations and are of sufficient and adequate quantity to improve the spiritual, cultural, environmental, social and economic conditions of those Indigenous Nations. This is our inherent right. (Australian Government 2012a, p. 174) and (MLDRIN 2007, p. 2)

First Nations’ ownership of water is a national issue, and there is a growing awareness on the part of Australian governments about the importance of providing cultural flows, including in the Basin. Efforts to increase ownership have been made, particularly in Victoria and outside the Basin. However, Aboriginal and Torres Strait Islander people’s ownership of water remains very low. While First Nations people represent about 5% of the Basin population, they hold less than 1% of available Basin water holdings (MLDRIN and NBAN 2021, pp. 13–15).

We heard concerns about declining water entitlements owned by First Nations people.

Our ownership of water is minuscule and has been going backwards. … Aboriginal water holdings between 2009 and 2018 indicate a new wave of dispossession. Almost one‑fifth of Aboriginal water holdings by volume were lost during this time. (The NSW Aboriginal Land Council, sub. 101, p. 7)

And MLDRIN expressed concern about progress made on cultural flows:

No Basin Nation currently holds a cultural flow entitlement nor is there a legal mechanism in place (federal or state based) that enables a cultural flow entitlement to be applied for, let alone attained, by any Nation. Any future iterations of the Basin Plan and WRPs must push all levels of government to invest time, resources, and effort to make the policy and legal reforms needed to make cultural flows possible. (sub. 92, p. 16)

Other participants noted their support for Aboriginal people holding water entitlements for cultural purposes, to support their economic and social participation in, and contribution to, regional communities. This aligns with the national framework for cultural flows, developed as part of the *National Cultural Flows Research Project.*

The *National Agreement on Closing the Gap* includes new outcome areas, targets and indicators that support the cultural wellbeing of Aboriginal and Torres Strait Islander people in several areas, including land and waters. There is a provisional target for First Nations ownership of national water entitlements in inland waters of 3% (NNTC 2023). The Joint Council on Closing the Gap indicated it expects to consider the inland waters target again in 2024 (2023, p. 2).

### Little progress made on the Aboriginal Water Entitlements Program

The *Aboriginal Water Entitlements Program* (AWEP) – while not part of the Basin Plan – aims to support Murray–Darling Basin First Nations communities’ investment in cultural and economic water entitlements and associated water planning activities.

The AWEP commenced in 2018 with $40 million to support Basin First Nations to purchase cultural and economic water entitlements. On 27 November 2023, the Australian Government Minister for the Environment and Water announced that the funding for the AWEP would increase to $100 million (Plibersek and Hanson-Young 2023, p. 2).

To date, no AWEP money has been spent on water purchases. Some of the reported challenges implementing the program include ‘administrative changes[[102]](#footnote-103) and diverse perspectives on how the funding should be allocated, including how to address First Nations values, interests and uses’ (Senate Environment and Communications Legislation Committee 2023b, p. 107).

As highlighted by a number of inquiry participants, the original $40 million budget will buy less water today than in 2018. The Environmental Defenders Office, for example, said:

The Commonwealth Government made a commitment to return $40m worth of water rights to First Nations across the Basin in 2018 and yet this is still to be achieved. Meanwhile, the price of water has increased such that the real value of the proposed acquisition has materially decreased. (sub. 91, p. 30)

And First Nations people have missed out on the cultural and economic benefits of water ownership.[[103]](#footnote-104)

DCCEEW, while acknowledging that the program has had implementation challenges, and delivery of the program has taken too long, noted that ‘the government is committed to ensuring that the delivery of the AWEP supports self‑determination of First Nations peoples’ (sub. 127, p. 9). The department is currently working with First Nations people on governance models to deliver the program (there has been extensive engagement on this issue in the past).

The mechanism for the First Nations water holder arrangement is yet to be determined as First Nations peoples need to be engaged about how models would work, and how these can support the principles of self‑determination … The department will work with the Committee for Aboriginal and Torres Strait Islander Water Interests, the Coalition of Peaks, the Indigenous Land and Sea Corporation, National Indigenous Australians Agency and other stakeholders to engage with First Nation people. This engagement will help to develop a fit‑for‑purpose model for First Nation people to own, access and manage water in Australia. (DCCEEW, sub. 77, p. 26)

DCCEEW plans to deliver the AWEP by 2024. The key steps and timing are:

* develop purchasing principles and interim governance arrangements with Basin First Nations peoples for water entitlements in the Basin – July to November 2023
* convene a Basin‑wide First Nations Gathering to present options for water entitlement portfolios and interim governance arrangements to Basin First Nation representatives – November 2023
* implement the purchasing framework and commence the purchase phase of the *Aboriginal Water Entitlements Program* – January to June 2024 (DCCEEW, sub. 127, p. 8).

|  | Finding 5.1  Limited progress made on the Aboriginal Water Entitlements Program |
| --- | --- |
| The Australian Government has made little progress on the Aboriginal Water Entitlements Program since the program was announced in 2018. Given the increase in water entitlement prices over that period, the $40 million original program budget will buy less water today than it would have in 2018. | |
|  | |

# Bringing new knowledge into the Basin Plan framework

|  |  |
| --- | --- |
| Key points | |
|  | An adaptive management approach to managing Murray–Darling Basin water resources, as established under the Murray–Darling Basin Plan (the Basin Plan), requires relevant knowledge to be continually improved and the management of the Basin’s water resources linked to this knowledge.  The required regular reviews and revisions of the water management framework and plans establish opportunities to apply new knowledge to Basin water management.  However, there is evidence that the water management framework is not updated as fully as it should be to reflect best available knowledge. |
|  | Climate change and its impacts should be considered in the 2026 review of the Plan. The Murray–Darling Basin Authority (MDBA) advises that it will be considered.  In the 2026 Basin Plan review, the MDBA should consider and report on how climate change has impacted, and is projected to impact, the Basin’s water resources. This work should draw on the best available climate projections.  The MDBA should also report on how climate change science has informed any proposed amendments to the Basin Plan, including to the environmentally sustainable level of take.  The framework for evaluating the Basin Plan and water resource plans should include indicators and targets specifically related to the resilience of water‑dependent ecosystems to climate change. |
|  | Some decisions made about the Basin Plan and ongoing management of Basin water resources are not transparent and it can be unclear what information is used to inform these decisions. This lack of transparency affects trust in the Basin Plan and government agencies implementing it, as well as the underpinning knowledge base.  All data, modelling outcomes and scientific and socio‑economic research used in Basin Plan‑related decisions should be published. |
|  | More coordination of knowledge generation, and sharing among researchers and policy makers, would improve the efficiency of research investment and better support water management decisions.  Greater consistency in climate change modelling approaches and application is a key area for improvement. |

Achieving the outcomes of the Murray–Darling Basin Plan (the Basin Plan) depends on the Plan and its supporting management activities being informed by a sound knowledge base. The *Water Act 2007* (Cth) requires the Basin Plan to be developed ‘on the basis of the best available scientific knowledge and socio‑economic analysis’.[[104]](#footnote-105) The Basin Plan requires the best available knowledge, or information, be used for:

* developing water resource plans
* the application of environmental water
* prioritising assets for environmental watering
* the assessment of river inflows to manage critical human water needs
* monitoring and evaluation.[[105]](#footnote-106)

Establishing a sustainable long‑term adaptive management framework for Basin water resources is one of the objectives of the Basin Plan, which the Plan defines to include ‘linking knowledge (including local knowledge), management, evaluation and feedback over a period of time [and] … improving knowledge’.[[106]](#footnote-107) To this end, the Basin Plan requires various elements of the water management framework be regularly reviewed or evaluated. Environmental watering plans, long‑term watering plans, water quality targets and socio‑economic impacts of the Basin Plan are required to be reviewed at least every five years.

This chapter assesses the extent to which the Basin Plan framework provides opportunities for adaptive management and how new knowledge can be further embedded in the Basin Plan framework (section 6.1). The way knowledge is generated and applied in practice is discussed in section 6.2.

## The Basin Plan framework has an adaptive management approach

An adaptive management approach to managing Basin water resources requires knowledge relevant to the Plan be continually improved and the management of the Basin’s water resources to be linked with this knowledge. Relevant knowledge includes:

* results of scientific research
* First Nations’ knowledges
* community insights and experience
* monitoring data
* findings of reviews and evaluations (including reviews of socio‑economic conditions).

Since the development of the Basin Plan, the relevant knowledge base has improved considerably, particularly in the areas of climate change and ecological water requirements. The question is how well does the management framework established under the Basin Plan allow for newly generated knowledge to be incorporated into Basin water management activities.

While a number of participants commented on the importance of having access to the most up‑to‑date evidence, some were of the view that the Basin Plan is not as adaptive as it could be and/or updated information is not incorporated in the Plan in a timely way (box 6.1). Improved accountability could encourage water agencies to apply more effective adaptive management processes (chapter 9).

| Box 6.1 – New knowledge and the Basin Plan: what participants said … |
| --- |
| Participants commented on the importance of relying on the best available knowledge.  Renmark Irrigation Trust  The ‘best available science’ will be important in the ongoing management of the available water resources in order to maximise the health of our riverine ecosystem and to maintain the social, economic, environmental balance for the long term. (sub. 24, p. 7)  Temba Orchards  We must be making our decisions based on evidence and best available science, as is demanded by the Water Act. (sub. 87, p. 1)  Environmental Defenders Office  Government decision‑making with respect to water resources must be based on demonstrated best available scientific knowledge. This must necessarily incorporate climate change projections. The scientific information underpinning decision‑making must be accessible, intelligible and peer reviewed. (sub. 91, p. 28)  Murray Irrigation  The expectation that the Plan will commit to the best available science is an important principle as communities have a right to expect that threshold levels of take and water quality targets are based upon a sound understanding of the biophysical processes. (sub. 65, p. 37)  But some questioned how well new knowledge is used.  Murray Valley Private Diverters  The Basin Plan is not adaptive and politicians and the MDBA [Murray–Darling Basin Authority] have not enabled meaningful improvements based on updated information to be incorporated. (sub. 95, p. 20)  National Farmers’ Federation  The implementation of the Plan does not adequately reflect a commitment to the best available scientific knowledge. Insufficient evaluation and a lack of adjustments based on scientific findings indicate a failure to incorporate scientific knowledge effectively. (sub. 46, p. 20)  Institute for Water Futures and Institute for Climate, Energy and Disaster Solutions  The requirement for commitment to the best available scientific knowledge is broadly commendable, and the Murray–Darling Basin Authority … has invested in significant programs, such as the Water and Environment Research Program … to ensure relevant and accessible science. However, it is important to review the kind of science that is preferred and privileged in this context, and determine whether more innovative and diverse approaches to ‘best available scientific knowledge’ are needed. (sub. 35, p. 7) |
|  |

### The first comprehensive Basin Plan review will be in 2026

The first full review of the Basin Plan – in 2026 – will be 14 years after the Basin Plan was put in place. The long time between initial drafting and review means new knowledge and ideas are not integrated at this level of the management framework.

Some parts of the Basin Plan are out of date and not considered adequate in today’s context. Climate change and First Nations’ interests are two such areas and the Murray Darling Basin–Authority (MDBA) has identified these areas as key themes of focus for the 2026 review of the Basin Plan (MDBA 2023l; Wyborn et al. 2023). The need to better reflect the current state of understanding of climate change and adequately account for the associated risks is discussed in this chapter. First Nations’ interests and knowledge, and how Basin Plan implementation can put into effect current best practice and government commitments to First Nations engagement, are discussed in chapter 5.

Amendments to the Basin Plan can be made before the scheduled 10 yearly review.[[107]](#footnote-108) Under the Water Act, the MDBA may, after conducting prescribed consultation, prepare an amendment to the Basin Plan for consideration by the Minister. The requirements for proposing an amendment are sufficient to discourage frequent use which may undermine the certainty of the plan, and the MDBA does not have processes in place to systematically identify circumstances that would warrant initiating an amendment to the Basin Plan. And, to this point, there does not appear to have been a situation that required the MDBA to use their powers in this area.

While reviewing the Basin Plan earlier in its life span may have meant these shortcomings were remedied earlier, more generally, increasing the frequency of reviews would reduce certainty provided by the Plan, which in turn could undermine trust. Full reviews of the Basin Plan are also expensive[[108]](#footnote-109) and time consuming for all governments involved and the wider community. The nature of the content of the Basin Plan and the slow dynamic of developments in this space mean that more frequent updates may not be necessary.

### There are other opportunities for adaptive management

#### Water resource plans

Other instruments in the Basin management framework also allow for adaptive management. Water resource plans (WRPs), which establish how Basin states will allocate and manage water in the river system at a local level (chapter 4), must reflect best available information to be accredited. And as new information becomes available, especially information relevant to a local area, there is scope to revise WRPs through a re‑accreditation process. Advances in, and updates to, hydrological modelling should be reflected in WRPs.

However, as discussed in chapter 4, the process to have initial WRPs accredited has been onerous for Basin states and the MDBA. While no WRPs have been re‑accredited as at December 2023, it is expected that, unless there are changes to the process, re‑accreditation will be similarly difficult. The ACT Government, for example, said:

The WRP is a static policy document of the Australian Government. Without changes to its structure, and improved administrative processes for amendment and accreditation, the WRP will become outdated and serve to limit progressive policy implementation. (sub. 85, response to information request, p. 5)

While WRPs need to be sufficiently stable and enduring to provide certainty and trust in water management arrangements, an overly burdensome amendment and re‑accreditation process could act as a disincentive to updating WRPs with new information. Chapter 4 (section 4.2) discusses this issue further.

#### Environmental water planning and management

Adaptive management is particularly important for environmental watering activities as much remains to be learnt about the ecology of the Basin. Implementing new knowledge as it comes to light enables the best use of environmental water to achieve optimal environmental outcomes (MDBA 2021e; Thurgate et al. 2019). The 2021 Review of the Environmental Watering Plan[[109]](#footnote-110) identified opportunities to improve implementation of environmental watering without legislative change, including addressing knowledge gaps and continued investment in adaptive management (MDBA 2021e).

The environmental watering framework, including the environmental watering strategy, long‑term watering plans and annual watering priorities, applies knowledge about environmental conditions and watering techniques to environmental water management. These documents are reviewed and updated either annually or every five years, but can also be revised earlier if required.

The Basin‑wide environmental watering strategy was reviewed, revised and updated in 2019 (five years after the initial strategy was drafted) to reflect changes in policy, new scientific knowledge and updated information about the condition of some Basin ecosystems (MDBA 2020d). At the time of the review, the MDBA noted the need for further updates earlier than the next five‑year review to address issues such as climate change and to reflect the findings of the 2020 Basin Plan Evaluation. The planned update for 2022, however, was not conducted (chapter 3). As it stands, material changes to the strategy have not been made despite deficiencies and the need for updates identified. Without these updates, the strategy does not support maximising environmental benefits from environmental watering as required under the Basin Plan.

The Commonwealth Environmental Water Holder (CEWH) states that its water use is adaptively managed as conditions unfold, using different scenarios and responding to water availability. It also monitors results and feeds findings back into future planning activities (CEWH, sub. 69). The Inspector‑General of Water Compliance (2022d, pp. 13, 18) found that the CEWH ‘relies strongly on productive working relationships with Basin State delivery partners’ and has ‘a positive culture of continuous improvement’ by responding to the findings of reviews.

State environmental water holders also have adaptive management approaches to planning and delivering environmental water flows to respond to seasonal weather conditions, water availability and environmental conditions. Watering plans are updated annually and use scenarios to plan for actions under different conditions (NSW DPE 2019; SA DEW 2023a; VEWH 2019a). Water delivery activities by river operators throughout the Basin are managed daily based on operating rules, science, monitoring and modelling (MDBA 2023f).

### Summing up

Successfully adopting an adaptive management approach to managing Basin water resources requires both generating advances in knowledge as well as timely opportunities to update the water management framework to apply the knowledge. Different elements of the Basin Plan framework can be updated at varying timeframes.

There is, however, evidence that not all aspects of the water management framework are satisfactorily updated through the review processes to reflect the best available knowledge. One example of this is the Basin‑wide environmental watering strategy.

### Further accounting for climate change in the Basin Plan

The climate in the Murray–Darling Basin is changing and is expected to become hotter and drier in the future, with more frequent and severe droughts and floods, and greater climate variability (box 6.2). The Basin Plan was designed to rebalance the consumptive and environmental use of water and enable the Basin to better adapt to a changing climate. Whether it does so successfully is a key measure of the Plan’s success.

A number of participants argued that the Basin Plan already accounts for climate change. For example, some emphasised that water allocations are adjusted each year to respond to changes in water availability (Renmark Irrigation Trust, sub. 24, p. 5). Others said a significant and sufficient amount of water had already been recovered for the environment – and either more was not needed, or it would be unfair for farmers to bear a greater share of the risk of climate change (for example, Murray Irrigation Limited, sub. 65, p. 24).

| Box 6.2 – Climate change in the Murray–Darling Basin |
| --- |
| Between 1910 and 2019, the Murray–Darling Basin experienced an average temperature increase of approximately 1.4oC, and there has been an increase in the incidence of extreme daily heat events (BOM 2020). Average annual inflows to the River Murray over the last two decades (2000–2020) are 39% less than that from 1900 to 2000 (MDBA 2020h, p. 21). However, the 2020–2022 period was significantly wetter with widespread and prolonged flooding, particularly in the second half of 2022. And since 1900 there has been highly variable rainfall from year to year and from decade to decade posing significant challenges for water management in the Basin (Bureau of Meteorology, sub. 17, p. 4).  Studies suggest a future characterised by hotter and drier conditions in the Basin, with increased frequency and severity of floods and droughts (BOM 2020; Prosser et al. 2021; Zhang et al. 2020). The median projection for 2046–2075, relative to 1981–2010, for a high global warming scenario is a 20% decline in streamflow across the Basin (Chiew et al. 2022).  Climate change affects water resource availability and management in the Basin and environmental outcomes. There are also concerns that climate change poses a significant and disproportionate burden on First Nations communities, the health of Country, and cultural values (Wensing et al. 2023, p. 12). Chapter 5 discusses First Nations’ values, knowledges and their involvement in Basin Plan implementation. |

Some argued that the Basin Plan was not well equipped to respond to climate change, with many focusing on whether it allows enough water to be recovered for the environment. The Wentworth Group of Concerned Scientists, for example, said the current water recovery target does not take into account climate change or its impacts on water availability and the condition of wetlands (sub. 81, p. 2). The Commissioner for the Murray River argued that without more water for the environment, climate change is likely to lead to irreversible ecological degradation (sub. 47, p. 14). And the Healthy Rivers Lower Murray Group said:

A major re‑set and re‑commitment is needed to get the Basin Plan back on track to achieve a sustainable level of take. This needs to happen before the next phase of incorporating the impacts of climate change on future water availability, predicted to reduce by 30‑50% in the next few decades. (sub. 37, p. 1)

Others said climate change needed to be better considered when recovering water for the environment. The River Lakes and Coorong Action Group, for example, said:

So far the Plan has not delivered sufficient water for ecosystem health. … There needs to be recognition that environmental water, or water for river health, is the most important water, maintaining a sustainable source for every user. … The impact of climate change must be considered and responsibility taken for not including allowances for a possible 30‑40% reduction in inflows over the Basin in the original Plan. … Climate change must be accounted for with flexibility in the volume of environmental water needed to sustain a healthy system. All consumers will have to manage with reduced allocations to maintain river health. (sub. 15, pp. 2–6)

Reporting on the environmental flow requirements in the changing climatic context, the Wentworth Group of Concerned Scientists said:

With changes in climate and declining water availability, it may not be possible to achieve every water requirement in the Basin. Governments need to be transparent about what we are trying to achieve, what we are failing to protect, and how we manage the consequences. (WGCS 2023, p. 1)

The variability of climate change can pose challenges to decision making about environmental watering. The CEWH, for example, said:

Under climate change, a range of threats are likely to arise more frequently. This will put pressure on environmental water managers like the CEWH to address issues and emergencies beyond what was contemplated at the time of the Basin Plan’s creation, while also constraining its ability to do so. (sub. 69, p. 2)

The MDBA recognises the importance of assessing climate risks to the expected environmental outcomes and water management strategies (MDBA 2020d, 2023j). It has also identified ‘adapting to climate challenges and increasing resilience’ as one of the six priority areas for the future and has made recommendations and commitments to enhancing climate resilience and adaptation in the Basin (MDBA 2020h, p. 118). The MDBA, in its 2020 evaluation of the Basin Plan, said:

While there are mechanisms embedded within the Basin Plan and water resource plans to respond to the implications of climate change, these instruments need to be continuously monitored and adapted to keep pace with the challenges of climate change. (MDBA 2020h, p. 120)

Climate change will be a focus for the next Basin Plan Review. The MDBA’s ‘Roadmap to the 2026 Basin Plan Review’ notes that its:

… understanding of the impacts of climate change on the management and resilience of river environments and water users has improved significantly since the Basin Plan was developed and up to date climate data and science needs to be incorporated in the Basin Plan’s strategies and activities. The Review will explore how best to plan for an uncertain future, and what actions we can take to help the Basin adapt to a changing climate. (MDBA 2023l, p. 11)

In October 2022, the Government announced $22 million to update science to ensure the impacts of climate change are accounted for in managing Basin water resources (DCCEEW 2022e).

Although the importance of climate change to the future of the Basin is now widely recognised, as discussed below, the Commission considers that climate change should be more explicitly embedded in the Basin Plan and resilience to climate change should be more thoroughly measured and monitored.

It should, however, be noted that the Basin Plan is an adaptation strategy, with the instrument confined to water management, and is not designed to address *all* impacts of climate change. Climate change will affect communities, agriculture, business and infrastructure in ways that are outside the scope of the Plan to manage. This is reflected in definitions of climate change resilience that refer to the capacity of communities, economies and environmental systems to cope (for example, definitions from the Intergovernmental Panel on Climate Change and the Australian Government in its National Climate Resilience and Adaptation Strategy 2021–2025). The MDBA recognised that:

There are many actions that will increase the Basin’s resilience to climate change but are beyond the remit of the Authority and the Basin Plan, and indeed the remit of water management alone. (sub. 61, p. 2)

Policies and programs related to climate change resilience more broadly include Australia’s National Climate Resilience and Adaptation Strategy 2021–2025, and the national climate risk assessment and national adaptation plan currently being developed by the Australian Government (DCCEEW 2023a).

#### Climate change science and the Basin Plan

The Basin Plan was intended to help the Basin adapt to climate change and a number of its features are focused specifically on climate change (box 6.3). However, neither the Water Act nor the Basin Plan explicitly refer to climate change projections, nor do they describe how this science should be integrated into Basin water management arrangements.

| Box 6.3 – References to climate change in the Water Act and Basin Plan |
| --- |
| The Basin Plan must be prepared giving effect to Australia’s obligations under a variety of international environmental agreements, including the United Nations Framework Convention on Climate Change and the Ramsar Convention (s21 of the Water Act).  The Basin Plan must identify ‘the risks to the condition, or continued availability, of the Basin water resources’, including risks to the availability of Basin water resources that arise from the effects of climate change (s22 of the Water Act).  The MDBA and the Minister for Water, in exercising certain powers and performing certain functions – which include preparing, reviewing and amending the Basin Plan – must ‘act on the basis of the best available scientific knowledge and socio‑economic analysis’ (s21(4) of the Water Act).  The Plan also sets out objectives and outcomes for the environment, which include protecting and restoring water‑dependent ecosystems and ensuring they are resilient to climate change and other risks and threats (s5.03). Related targets are set out in Schedule 7. |
|  |

In our interim report, we sought participants’ views about whether the Water Act should be amended to make clear and explicit that the best available science about the impact of climate change on water availability, including climate projections, is part of the scientific knowledge on which the Plan should be based and reviewed. Several participants said the Act should be amended with some arguing that the amendments should be made as a matter of urgency to inform the review of the Basin Plan in 2026 (box 6.4).

| Box 6.4 – Support for amending the Water Act to embed the best available climate change scientific knowledge in the Basin Plan framework |
| --- |
| The Lifeblood Alliance (LBA)  LBA has consistently argued that the impacts of climate change on water availability should be included in the Water Act and Basin Plan since 2010. We therefore support changes to the Water Act to make this explicit. Any change needs to happen now so that it can guide the review of the Basin Plan in 2026 and the development of Basin Plan 2. (sub. 119, p. 9)  Inland Rivers Network  It is imperative that climate change science is embedded into the Basin Plan framework. This has been argued since before the Basin Plan was adopted in 2012. These amendments to the Water Act need to happen now to inform the review of the Basin Plan in 2026 and the development of Basin Plan 2. (sub. 109, p. 5)  National Parks Association of NSW  The impacts of climate change on water availability should be included in the Water Act and Basin Plan. Any change to the Water Act to make this explicit are supported. (sub. 121, p. 4)  The Australian Academy of Technological Science and Engineering (ATSE)  ATSE agrees that the Water Act 2007, which enables the Basin Plan, should be amended to explicitly include climate science in the scientific knowledge upon which the Plan is based. Climate change will exacerbate the Basin’s environmental challenges. Grounding the Plan in the best available scientific evidence is crucial for restoring the health of the Basin and preserving it for the use of future generations. (sub. 135, p. 1)  Barrie MacMillan  Climate change science should be embedded into the Basin Plan framework, including updated climate projections and the impact on water availability, to ensure that the MDBA cannot choose to ignore current scientific knowledge in the future, is obligated to implement appropriate risk management practices in setting [the Environmentally Sustainable Level of Take and Sustainable Diversion Limits] in the future and to encourage research into efficient use of water. (sub. 125, p. 3)  Healthy Rivers Lower Murray  It is absolutely critical that the impacts of climate change be factored into the Basin Plan. The implementation of the Plan to date has failed to effectively address the fundamental issue of overextraction that was identified in 2007. The predicted effect of climate change is that there will be even less water available in the future, so the Water Act needs to ensure that this unpalatable factor of not enough water is addressed effectively and built into the ‘environmentally sustainable level of take’. (sub. 106, p. 4)  The NSW Department of Planning and Environment  Climate change science should be further embedded in the Basin Plan with greater consistency in climate change modelling approaches across Basin States as a key area for improvement. (sub. 111, p. 10) |
|  |

While acknowledging the importance of climate change science, the Rice Growers Association emphasised that science alone is insufficient for managing reduced water availability.

As we learned during the Millenium Drought, management of reduced water availability requires good, real‑time decision‑making. Science on its own does not provide for this. … Policy options and operational responses that take full advantage of the expected more frequent and severe floods will also be critical. (sub. 105, p. 6)

There is some disagreement about whether future climate scenarios were adequately considered in the making and implementation of the Basin Plan, particularly in setting the sustainable level of take. The South Australian Royal Commission, for example, was highly critical of the MDBA for not considering projections, claiming it ignored advice given by CSIRO in 2009 to incorporate climate change projections into its modelling for the determination of the Environmentally Sustainable Level of Take and the Basin‑wide sustainable diversion limit (SDL). The MDBA disagreed with these findings, arguing that when the Plan was developed there was scientific uncertainty about the impact of climate change on water availability and it was difficult to anticipate exactly how global changes to the climate would play out at smaller scales such as across the Murray–Darling Basin (MDBA 2019a, pp. 13, 16). There is much less disagreement now about whether projections *should* be considered in the design and implementation of the Plan.

A substantial amount of work is underway looking at how climate change science can be better embedded in the Basin Plan. For example, in November 2023, the MDBA commissioned CSIRO to develop basin‑scale hydroclimate projections for the Murray‑Darling Basin Sustainable Yields 2 Project. The projections will be used by the MDBA and Basin states to assess future water resources across the Basin and form part of the Basin plan review (CSIRO, sub. 113, p. 4). An interjurisdictional Strategic Hydroclimate Working Group has been established to provide advice on developing and applying Basin scale hydroclimate information (MDBA, sub. 126, p. 9).

Several participants argued that climate modelling and projections should be considered in the 2026 Basin Plan Review (Beasley, sub. 47, p. 15; Beer, sub. 38, p. 19; Central NSW Joint Organisation, sub. 31, p. 8; Lifeblood Alliance, sub. 52, p. 10; Peerson et al., sub. 35, p. 4). The MDBA has said it will explore ways to better integrate climate change in this review (MDBA 2023l) and the Water Act has recently been amended to require the MDBA to consider and report on ‘the management of climate change risks’ (*Water Amendment* *(Restoring Our Rivers) Act 2023* (Cth)). In doing this work, the MDBA should consider the best available climate projections and how these affect the Basin Plan.

|  | Recommendation 6.1  Climate projections and the Basin Plan |
| --- | --- |
| In its 2026 review of the Basin Plan, the Murray–Darling Basin Authority should consider and report on:   * how climate change has impacted, and is projected to impact, the Basin’s water resources, and * how climate change science has informed any proposed amendments to the Basin Plan, including to the environmentally sustainable level of take. | |
|  | |

#### Climate change resilience needs to be more measurable

The Basin Plan includes ‘overall environmental objectives’ for the water‑dependent ecosystems of the Murray–Darling Basin – namely, to ‘protect and restore’ the ecosystems and ecosystem functions and to ensure they are ‘resilient to climate change and other risks and threats’.[[110]](#footnote-111) The MDBA is required to monitor and report every five years on progress against these objectives.

The Basin Plan does not specify what is meant by ‘climate change resilience’, and while targets to assess progress against these environmental objectives are set out in Schedule 7 of the Plan, they are general and aggregated, rather than specifically focused on climate change resilience, and difficult to measure. The targets relate to flow regimes; hydrologic connectivity; improvements in river, floodplain and wetland types; the condition of the Coorong and Lower Lakes and Murray Mouth; native water‑dependent vegetation; native water‑dependent species, including birds, fish and macroinvertebrates; and the community structure of water‑dependent ecosystems. This lack of specificity makes it difficult to understand how progress towards climate change resilience is measured and whether progress is being made at all.

The Plan also requires the MDBA to have regard to certain strategies when undertaking its functions, including strategies to improve knowledge of the impact of climate change on water requirements and water resources.[[111]](#footnote-112) The strategies are clearly ‘high‑level’ and have been criticised for being somewhat ‘minimal’ (Owens 2022, p. 23) and even ‘whimsical’ (SA Government 2019, p. 253).

The Basin Plan would be improved if there was more clarity about how objectives related to climate change are measured and assessed. Several participants supported such a reform (Barrie MacMillan, sub. 125; Inland Rivers Network, sub. 109; Lifeblood Alliance, sub. 119; National Irrigators’ Council, sub. 130). A clear definition of climate change resilience and more detailed targets and related indicators, some tailored to specific ecosystems, would be significant improvements. This could be a challenging task, in part because of differing levels of climate hazard, exposures, and adaptive capacities across the Basin. However, without some specific indicators or measures of climate change resilience, it is difficult to rigorously assess progress and make necessary changes in response. Other factors also affect the broader resilience of the Basin and its communities. As the NSW Farmers Association (sub. 123) said, factors such as removing water from agricultural production also affect resilience.

Incorporating advancements in science into evaluation methods is important for ensuring the Basin Plan delivers on its water management objectives to adapt to climate change (Department of Climate Change, Energy, the Environment and Water, sub. 127). There are examples of quantitative climate change resilience measures, for instance, the Economist Intelligence Unit developed a Climate Change Resilience Index that can be compared across different locations and time periods (EIU 2019). The index used indicators such as loss of land, crop yields, tourism and labour productivity due to extreme climatic events.

|  | Recommendation 6.2  Specific measures or targets for evaluating climate change resilience |
| --- | --- |
| The Murray–Darling Basin Authority should set out how it evaluates whether water‑dependent ecosystems are resilient to climate change, including by specifying which targets are relevant to climate change resilience and how progress against these targets is monitored. When reviewing the Basin Plan in 2026, the Murray–Darling Basin Authority should also consider whether some of this information should be integrated into the Basin Plan. | |
|  | |

## Processes for generating and using knowledge

Knowledge generation activities[[112]](#footnote-113) are undertaken by a variety of bodies, including government research institutions, universities and the private sector. These activities are funded by Australian, state and territory governments and research corporations.

Since 2018, the Australian Government has made significant investments in the generation of knowledge relevant to the Murray–Darling Basin Plan, including via the following programs.

* The MDBA manages the Murray–Darling Water and Environment Research Program, the Basin Condition Monitoring Program, the Sustainable Rivers Audit, the Sustainable Yields project, the Integrated River modelling uplift program and the River Reflections Conference (MDBA, sub. 61, response to information request).
* The MDBA developed a climate workplan for 2021 to 2026 which includes filling climate change knowledge gaps and sharing information with communities, industry and Basin governments (MDBA 2023j).
* The CEWH’s key science program is the Flow Monitoring, Evaluation and Research program (FLOW‑MER). The CEWH also undertake short‑term intervention monitoring projects and monitoring programs for the Living Murray and for state governments (sub. 69).
* As part of the National Environmental Science Program, CSIRO is developing methods for projecting hydrological metrics which will support science and modelling for national climate projections. CSIRO is also collaborating on methods to quantify evapotranspiration (CSIRO 2020).

Basin states are also making investments.

* The NSW Government has developed a new climate data and modelling framework to inform regional water strategies (NSW DPIE 2020a).
* The Victorian Government updated their guidelines for assessing the impact of climate change on water availability in Victoria drawing on the findings of the first phase of the Victorian Water and Climate Initiative (Victorian DEECA 2023).
* The Queensland Government is investing in seven new water modelling projects to improve their capacity to model water resources. This includes a project to improve Queensland’s ability to integrate First Nations’ cultural knowledge, values, and land and water management skills into water modelling and management practices (Queensland DES 2023).
* In South Australia, the Healthy Coorong, Healthy Basin program includes scientific trials and investigations to fill knowledge gaps and provide a scientific evidence‑base to inform management actions to improve the long‑term health of the Coorong (SA DEW 2023b).
* The ACT Government commenced a project in 2022 to develop a model that incorporates climate projections to assess vulnerability of ACT water resources (ACT Government, sub. 85, response to information request).
* The Department of Climate Change, Energy, the Environment and Water has ‘engaged Professor Mary O’Kane AC to conduct a review to advise and make recommendations that will enable the Commonwealth to ensure water science and research investments are strategically aligned, and appropriate to water policy’ (sub. 127, p. 18). The review (expected to be completed in early 2024) was commissioned with the intent to support robust evidence‑based water policy, planning, decision making and investment.

Through the inquiry process, we did not hear significant calls for an increase in the volume or scope of water‑related research being undertaken. However, submissions in response to the interim report noted a couple of areas where further research would be beneficial.

* CSIRO (sub. 113) noted that there is a knowledge gap around modelling hydrological connectivity of the Basin (on which it is currently undertaking some research). It also highlighted the importance of maintaining knowledge of groundwater systems, and their interaction with surface water, for managing the Basin’s water resources.
* Wheeler et al. (sub. 104) argued that more research is needed on the economic benefits of water recovery for First Nations and downstream communities. They also pointed to the need for:
  + an independent and comprehensive water audit using remote‑sensing data (and other relevant data) to assess the impacts of water recovery and the Basin Plan on relevant inflows and outflows
  + a proper assessment of structural adjustment and regional diversification funds.

### Greater transparency is needed around how knowledge is used in decision making

Despite these investments in knowledge generation and application, some decision‑making processes lack transparency so it is unclear if and how new knowledge is used. And without clear, accessible and understandable explanations of what information is used to inform key decisions (and what other factors are considered when making decisions), decision makers are unlikely to gain the trust of the community. The NSW Government, for example, commented that:

Greater accountability and transparent use of best available science is central to the credibility of decision‑making by governments and to the credibility of any reform agenda. Clear evidence supporting how and why decisions are made is important – but equally, ensuring that this evidence is available and can be understood by customers, stakeholders, and the broader community. (sub. 43, p. 17)

A noteworthy example of a decision taken that lacked transparency was the setting of SDLs under the Basin Plan. The reasoning, modelling data and assumptions used to underpin the final SDLs were not made public in any form, accessible or otherwise. The level at which SDLs were set, and the process by which they were determined, has been an issue for the life of the plan and the evidence underpinning SDLs has been consistently questioned (Rural and Regional Affairs and Transport References Committee 2013; SA Government 2019). This lack of transparency has had wide ranging effects on community confidence in the Basin Plan, and trust in science and government agencies.

Enhanced transparency about the factors considered in decision making, and improved access to the supporting information, can have a number of positive effects: the community is assured that the best available knowledge is being considered; scientific claims can be verified; alternative or better information can be identified and shared; and it can spark constructive discussion and debate around the best course of action, potentially leading to improved outcomes. This is important for knowledge of socioeconomic conditions and impacts as well as physical conditions. Chapter 2 discusses the importance of high‑quality and transparent socioeconomic analysis in the development and design of adjustment assistance.

As SDLs are such a fundamental aspect of the Basin Plan, building support for the SDLs through the 2026 review period will be essential. When SDLs are reassessed in 2026 it is critical that the MDBA publish the information that supports the SDL decisions to ensure the controversy surrounding the initial SDLs is not repeated. The Commission notes that MDBA has committed to this transparency for the 2026 Basin Plan Review (MDBA, sub. 126).

One way to improve transparency, and demonstrate what information is considered by decision makers across the Basin Plan framework, is to routinely publish all data, modelling outputs and government commissioned scientific research that is used when making decisions about water management in the Basin. Ensuring the information is accessible and understandable for all interested parties is equally important. This may require different information products to be produced for different audiences.

Since 2018 there have been some improvements to the publication of information.

* The MDBA has committed to publishing data and reports from two of their key science programs: Murray–Darling Water and Environment Research Program and the Basin Conditioning Monitoring Program (MDBA 2022f; MDWERP 2022).
* The MDBA is currently undertaking the Integrated River Modelling Uplift, a program to integrate 24 separate river models by 2024. The program will develop a public‑facing data portal which will help improve public understanding of hydrologic modelling scenarios and results (MDBA 2023q).
* In 2021, the Bureau of Meteorology released the Murray–Darling Basin Water Information Portal. The portal brings together information about water storages, river flows, water allocations and water trading information for Basin regions. The portal was designed to meet the needs of members of the Basin community (BOM 2023).
* The CEWH are currently redeveloping their website to better meet the needs of users. They publish highlights of monitoring and research findings on the FLOW‑MER website and all monitoring and science reports on data.gov.au (sub. 69).
* The NSW Government launched the Open Data Framework to support commitments to transparency made in the 2021 NSW Water Strategy. Climate and hydrological modelling data and outputs will be included in the data published (NSW DPE 2022e).
* The Queensland Government’s Rural Water Futures program was established in 2020 to provide ‘better access to high quality water data, more visible and consistent water management decisions, and improved customer experience’ (QLD DRDMW 2021, p. 1).

But more could be done. The National Farmers’ Federation observed that:

The communication of scientific knowledge within the Plan has been inadequate. The information provided to the public lacks clarity and accessibility, hindering the understanding and engagement of stakeholders. There is a need for improved communication channels that effectively convey scientific findings, their implications, and the rationale behind decision‑making processes. (sub. 46, p. 20)

|  | Recommendation 6.3  Publishing material used for decisions |
| --- | --- |
| Government agencies should publish, including in regular scheduled reports, the data, modelling outputs and government‑commissioned research that informs their decisions about water management in the Basin. This should include any decisions related to resetting sustainable diversion limits. | |
|  | |

### Coordination of research efforts and knowledge sharing

Knowledge generation activities should be undertaken in a coordinated and strategic way to ensure the best possible information is available to support decision makers’ needs (current and future) and investments in knowledge generation are cost effective. Strategic coordination of knowledge building across agencies and policy or program areas can also ensure efforts are aligned, future focused and support the overall objectives of water policy. While some water knowledge needs are specific to a particular location or region, others are shared across jurisdictions. Coordination of knowledge generation efforts and information sharing helps to reduce duplication of effort, generate additional research activity through pooling of resources and build consensus on common issues (PC 2021b).

Some participants highlighted a lack of strategic coordination of knowledge sharing. The NSW Government, for example, called for the MDBA to undertake a coordinating role.

The MDBA should focus on a coordinating role working with state agencies to access the best available information, analytics, and communications. (sub. 43, p. 17)

Without effective coordination, there is not only a risk of duplication or that decision makers will not consider all available information, but there is also a risk that messaging from different jurisdictions results in confusion in the wider community. Diversity in approaches to knowledge generation is valued and can be facilitated within a coordinated approach. The National Parks Association of NSW noted that a coordinated approach to reporting should ensure ‘Commonwealth statements do not, unless evidence based, create uncertainty in state‑based modelling’ (sub. 121, p. 4).

The Commission acknowledges that coordinating Basin governments’ knowledge generation can be a challenging task, however, it has been done successfully in the past. Previously dedicated bodies or initiatives established to coordinate a strategic approach to water research have included Land and Water Australia, the National Water Commission and most recently the Basin Wide Knowledge Platform. These programs ended, and no similar initiative is currently in place.

Knowledge sharing between Basin states currently occurs through discussions at the Basin Officials Committee and informal networking. At the project scale, end user advisory groups review each project under the Murray–Darling Water and Environment Research Program and include representatives from each Basin state. These advisory groups provide an opportunity to share and discuss research outcomes of specific projects and ensure research is translatable to government policy needs (MDBA 2021a). Program‑level co‑operation is also occurring, such as through the Integrated River Modelling Uplift program where MDBA is working to improve how individual regional river models ‘talk’ to each other and improving approaches to sharing water data and modelling information (MDBA 2023q).

The lack of a dedicated body or role focused on overseeing and coordinating knowledge generation across the Basin is a gap in the Basin management framework. A dedicated role or office for knowledge coordination could:

* identify water‑related knowledge gaps with a strategic, future‑focus
* signpost priorities for knowledge generation for use by academics, non‑profit organisations and government agencies
* share information between jurisdictions and water agencies
* aid in the establishment of relationships or links among knowledge generators and with policy makers.

This role will provide a valuable contribution to implementation of the Basin Plan. As noted in the Commission’s report on the National Water Initiative, coordination of knowledge generation activities across the nation is also a desirable outcome (PC 2021b). The knowledge coordination role could cover both Basin Plan and national water interests. It could be housed under the Department of Climate Change, Energy, the Environment and Water or, if established, the National Water Commission.

|  | Recommendation 6.4  Strategic coordination of knowledge generation and sharing activities |
| --- | --- |
| The Australian Government should establish a role for overseeing and coordinating water‑related knowledge generation and knowledge sharing across the Murray–Darling Basin. | |
|  | |

#### Consistency in climate change modelling approaches and application

Basin states use different climate models and risk assessment methods when developing their water resource plans and water sharing plans, and the results are communicated in different ways. These models and methods inform, for example, plan responses to extreme events, such as extended periods of drought. The MDBA said:

There has been extensive work undertaken by each jurisdiction to develop and apply high quality climate change information. There are systematic differences underlying each approach and significant structural differences in how climate model projections are applied. (sub. 61, p. 21)

Using different climate models and risk assessment methods across the Basin presents a number of challenges. Aside from the question of whether some models and methods are better than others, using different models can make it difficult to compare outputs. Different models may use different combinations of equations, approximations, and assumptions, which means they are likely to produce different results for the same scenario. There is scientific evidence that different models can produce a range of future climate conditions for a specific geographic region (Sauchyn et al. 2022). More specifically, it can make it difficult to:

* compare climate risks and vulnerabilities across the Basin
* compare climate change projections
* monitor and evaluate climate change impacts
* track trends and progress
* assess various risk management measures.

Such differences can also make it more difficult to clearly communicate the effects of climate change on water resources. Prosser et al., for example, said:

The availability of multiple climate projection products or datasets, as well as the different methods that can be used to develop hydrological projections, can add to the confusion and challenge in interpreting the projections. (Prosser et al. 2021, p. 4)

The Commission also heard that some Basin agencies appear to make little use of climate change modelling in their water management. The National Parks Association of NSW said:

It is widely acknowledged that at least four of the NSW’s 13 water‑sharing plans did not take the Millennium Drought into consideration when calculating water availability. … this caused over‑allocation and serious deficiencies in water security during an intense drought, particularly in the Northern Basin River systems. (sub. 41, p. 5)

Similarly, the Nature Conservation Council of New South Wales said:

Climate predictions are not used when extraction limits and available water determinations are calculated. (sub. 50, p. 7)

The SA Government acknowledges that while future climate and water availability may not reflect historical trends, their water allocation limits and principles have predominantly relied on historical data. Additionally, the SA Government emphasised the need for Basin‑wide climate projections, which are currently unavailable, posing challenges for water management planners to integrate climate change considerations (SA Government, pers. comm., 25 September 2023).

The Bureau of Meteorology said it would be beneficial if Basin states, when developing WRPs and water sharing plans, considered using common assumptions or at a minimum communicated their assumptions in a consistent manner (Bureau of Meteorology, pers. comm., 24 July 2023). This would foster a more cohesive understanding of climate change impacts on water resources and lead to informed decisions that account for the shared challenges posed by climate change across different regions. The NSW Government also said:

It is critical that the development and application of fit for purpose hydroclimate information, consistent with best practice, informs Basin Plan implementation and related water policy and planning needs. Currently, there is no agreed tool or plausible future climate scenarios between Basin jurisdictions and the MDBA. (sub. 43, p. 16)

It is not practical or desirable for all Basin states to be required to use the same model or assessment method. Such a change would add administrative and transactional costs and may make it difficult for states to adapt and take advantage of new developments in modelling and methodology. Differences in geographical features across states and catchments may also present challenges. However, there would be advantages to Basin states agreeing upon key assumptions and principles for future climate models and assessment methods – for example, a standard about using the historical water flows and climate conditions to compare model predictions. There are examples of such standardisation in climate modelling. For instance, the Intergovernmental Panel on Climate Change develops a set of emission scenarios to apply in different climate models (Hausfather 2019).

The Commission understands the MDBA is currently working with Basin states to understand differences in climate models and collaborate on clear messaging. As part of this work, they could also seek to agree on certain assumptions and principles for the models and assessment methods.

This would help ensure the models and methods are fit‑for‑purpose, produce results that can be compared across the Basin, and inform decision‑making, including decisions about environmental watering. It may also enable the MDBA and Basin states to synthesise results from the various models and better communicate the most likely climatic scenarios and potential impacts on water resource availability and management.

Summing up, the use of different climate models and risk assessment methods across the Basin present multiple challenges. For example, it makes it difficult to compare climate risks and projections across the Basin, track trends and progress, and make informed decisions about water management. It also makes it difficult to clearly communicate the effects of climate change on the Basin. Greater cooperation and collaboration across the Basin may help meet these challenges.

# Water quality and critical human water needs

|  |  |
| --- | --- |
| Key points | |
|  | The Murray–Darling Basin Plan (the Basin Plan) sets water quality objectives and targets and requires Basin states to include water quality management plans in their water resource plans. Water resource plans are also required to describe how water resources will be managed during ‘extreme events’, in part to ensure critical human water needs are met.  Ensuring fit‑for‑purpose water quality in the Murray–Darling Basin relies on the full implementation of the Basin Plan. With most water resource and water quality plans still outstanding in New South Wales, water quality and critical human water needs are at greater risk in that state. |
|  | Water quality targets and objectives need to be reviewed in the Murray–Darling Basin Authority’s 2026 review of the Basin Plan. National water quality guidelines are being updated and there is an opportunity to question whether targets in the Basin Plan are set at the right geographic and temporal scale. |
|  | There are long‑standing concerns about water quality and critical human water needs in the northern Basin. The NSW Government has a number of programs to manage these problems, but there are calls for the Basin Plan to do more.  Several towns in western New South Wales, such as Walgett, Brewarrina and Bourke, have had limited access to (or limited long‑term supplies of) safe drinking water for some time – not only during ‘extreme events’. |
|  | The Basin Plan Review in 2026 should examine how the Basin Plan can play a greater role in improving water quality and securing critical human water needs in the northern Basin.  The Review should consider whether arrangements in the southern Basin could be adapted and applied to the northern Basin, and the role of related water planning instruments in improving outcomes in this region.  The Review should also explore other options, such as further restrictions on extractions and more clearly demarcated roles and responsibilities. |

This chapter sets out the framework in the Murray–Darling Basin Plan (the Basin Plan) for managing water quality and meeting critical human water needs, summarises Basin governments’ progress on implementing these arrangements, and considers how the arrangements could be improved, particularly in the northern Basin.

## Water quality

### The framework

The Basin Plan seeks to ensure that water quality is appropriate for environmental, social, cultural and economic activity.[[113]](#footnote-114) It does this by setting objectives and targets and requiring Basin states to include local targets, objectives and actions in catchment‑level water quality management plans (WQM plans). There are targets and objectives for salinity levels, dissolved oxygen (blackwater events), blue green algae, and for specific types of water use, such as cultural, recreational and consumptive water use.[[114]](#footnote-115) The Basin Plan also includes an objective to discharge an average of 2 million tonnes of salt from the River Murray system into the Southern Ocean each water accounting period.[[115]](#footnote-116)

Basin governments use the targets to identify areas experiencing water quality problems and inform water management decisions. Meeting the targets is not mandatory; rather, the targets help identify and manage risks (MDBA, sub. 61, p. 11) and assess whether environmental values are being achieved (NSW DPIE 2020b, p. 2). Basin governments also use the targets to inform the assessment and development of state water planning instruments, such as the Victorian Waterway Management Strategy (Victorian Government, sub. 74, response to information request, p. 6).

River operators and managers are required to take into account water quality targets when making decisions related to flows. The water quality benefits of environmental watering are discussed in chapter 3.

#### Monitoring and evaluation

The Murray–Darling Basin Authority (MDBA) monitors and reports on water quality outcomes on a regular basis. For example, summaries of water quality threats by type and location are provided on the MDBA website and information about water quality is included in their mid‑year and end‑of‑year Basin Plan Report Cards (MDBA 2023a, p. 16). The MDBA also reports each year on salinity levels at five sites[[116]](#footnote-117) and overall salt export performance for the entire Basin[[117]](#footnote-118) (sub. 61, response to information request, p. 7).

The MDBA, Basin states and the Commonwealth Environmental Water Holder also report annually on how water quality targets are being considered when managing flows (MDBA, sub. 61, response to information request, p. 7).

Basin states must report on water quality outcomes every five years.[[118]](#footnote-119) The most recent reports, which covered the period between 2014 and 2019[[119]](#footnote-120), found that water quality objectives were generally being met, although some targets were not. Notable instances of targets not being met are outlined in box 7.1.

| Box 7.1 – Basin state government reporting on water quality |
| --- |
| The Basin Plan requires Basin state governments to report on water quality every five years.  New South Wales, Victoria and South Australia released reporting in 2020 that detailed water quality measurements against targets set in water quality management plans (WQM plans). The ACT provided a summary of water quality outcomes as part of the Murray–Darling Basin Authority’s annual reporting (MDBA 2020a, pp. 5–6). Queensland reported that water management processes complied with water quality objectives, but it did not present water quality measurements against targets (QLD DNRM 2020, p. 15).  New South Wales  The NSW Government reported that several significant poor water quality events occurred between 2016 and 2019, including blackwater and fish death events and blue green algal blooms (NSW DPIE 2020b, pp. 105–116).  While water quality was found to be ‘fair’ or ‘good’ for most water resource plan areas in NSW, many still exhibited declining water quality over the five‑year period.  Importantly, it was reported that targets in the Barwon‑Darling area were ‘inappropriate’ (NSW DPIE 2020b, p. 76), as targets set in the Plan are such that the Darling River will always be classed as having poor water quality (NSW DPIE 2020b, p. iv). This reporting echoed findings in the Commission’s 2018 review of Basin Plan implementation, which found that the salinity target at Burtundy in the Lower Darling was often not met during periods of low flow (discussed below). The MDBA’s 2020 review of water quality targets concluded that further investigation was still needed to determine whether the salinity target at Burtundy needed to be redefined, such as whether the observed levels posed risks to Basin Plan objectives, and if changes to water management were needed to reduce salinity levels (MDBA 2020g, pp. 30–33).  Victoria  The Victorian Government reported that it had ‘actively delivered on its water quality requirements’ (Victorian DELWP 2020, p. 3). Reporting on dissolved oxygen levels showed that almost all sites in the north‑east of the state measured above target levels of saturation (the desired outcome), while there were ‘more incidences of samples not attaining the target’ in the north west of the state (Victorian DELWP 2020, p. 12).  Dissolved oxygen levels below target risk the ability of waterways to support aquatic life.  Salinity in the Ovens, Kiewa and Wimmera Rivers was maintained below target values over the reporting period, while targets were exceeded for at least one year at five other sites (Victorian DELWP 2020, p. 16).  South Australia  In South Australia, water quality reporting covers a broader range of measures than in other states.  Water quality targets for maintaining flows, irrigation water and recreational water were rarely exceeded, which meant water sampled was of an acceptable quality to allow these uses of water. During the 2006 to 2020 reporting period, dissolved oxygen levels fell below targets in some locations. However, there were more widespread examples of dissolved oxygen levels falling below target in 2010‑11 and 2016‑17. High flow events during these years meant that multiple locations exhibited hypoxic blackwater conditions, dangerous for aquatic life (SA DEW 2020, p. 13).  There were minimal exceedances of salinity targets in the River Murray, and some minimal exceedance of salinity in Lake Alexandrina in 2011, 2018 and 2019 (SA DEW 2020, p. 14). Total phosphorus levels were recorded above targets on occasion during the monitoring period, with significant exceedances measured in 2010 and 2013 for all sites within the River Murray (SA DEW 2020, p. 16). From 2016 to 2020, phosphorus continued to be recorded above target levels. Higher total phosphorus levels impact food webs and can reduce the availability of food resources for native fish and birds.  Australian Capital Territory  Water Quality reporting published by the Murray–Darling Basin Authority summarised findings from ACT’s State of the Environment report. This report found that samples met water quality guidelines for most measures, however, there were examples of turbidity exceeding guideline levels (MDBA 2020a, p. 5). The ACT’s Catchment Health Indicator Program assessed water quality as excellent in 35% of reaches, and good in 62% of reaches (MDBA 2020a, p. 5).  Results for recreational water were not as favourable. Nearly every monitored site experienced closures due to exceedance of enterococci guidelines, and there were closures at some sites due to blue‑green algae occurrences (MDBA 2020a, p. 6).  Queensland  Rather than focusing on water quality outcomes against targets, the Queensland reports outlined the risks to water quality, accredited water management measures used to address these risks, and the implementation status of these measures (QLD DNRM 2020, pp. 2–15). Queensland reported progress against all three types of water quality targets and noted that all measures were ‘either ongoing or completed, thus demonstrating progress towards the water quality targets’ (QLD DNRM 2020, p. 15). |

### Water quality management plans

Water resource plans must include WQM plans, which must set out targets and identify risks and causes of water quality degradation. WQM plans must also include measures to help meet water quality objectives, including measures related to land‑use. Examples of measures include the use of salt interception schemes and regulations around the use of intensive livestock operations (such as feedlots), which can pollute watercourses. As outlined in chapter 3, Basin governments are undertaking natural resource management works and activities in part to improve water quality in the Basin.

There should be 33 water resource plans (WRPs) in place across the Basin, but 10 plans remain outstanding in New South Wales (chapter 4). In its 2020 evaluation, the MDBA stated ‘the Basin Plan’s contribution to ensuring fit‑for‑purpose water quality in the Basin relies on full implementation of the Basin Plan’ (MDBA 2020h, p. 68). This includes having all 33 WRPs in place. As discussed later in this chapter, the absence of WRPs is a particular concern for the Lower Darling.

#### Targets and objectives need to be updated

Water quality targets and objectives will be considered in the MDBA’s 2026 Review of the Basin Plan. The MDBA will need to consider updated national guidelines and whether water quality targets are specific enough and set at the right geographic and temporal scale.

#### Updated national guidelines

National water quality guidelines, which are reflected in targets and objectives in the Basin Plan,[[120]](#footnote-121) are currently being reviewed. The Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZ Guidelines), which are part of the National Water Quality Management Strategy (NWQMS), are being revised through the Water Quality Guidelines Improvement Program (DCCEEW, sub. 77, p. 14). The Department of Climate Change, Energy, the Environment and Water (DCCEEW) submitted:

Incorporating the ANZ Guidelines and NWQMS into the upcoming review of the Basin Plan will ensure it continues to reflect best practice in water management. It will also be a practical example of how water quality and broader water management issues are integrated to address quantity and quality outcomes. (sub. 77, p. 15)

Changes to the ANZ Guidelines will need to be reflected in the Basin Plan and therefore considered by the MDBA in its upcoming review of the Basin Plan.

#### Changes to specific targets

In a 2020 review of Basin Plan water quality targets, the MDBA found that most targets were working well, were supported by Basin states and were ‘instrumental in driving change in key management areas of the Basin, such as salinity’.

When applied well, they provide an opportunity to engage with an understanding of the risk posed by water quality stressors and the potential need for change. … Targets should continue to be applied as guideline values triggering action or risk mitigation, rather than enforceable limits leading to regulatory response. (MDBA 2020g, pp. 57–58)

However, the MDBA also recommended improvements to some water quality targets and objectives, including the objectives about salt export, cultural use, and raw water for treatment for human consumption (MDBA 2020g, pp. 3–6). It also recommended building a ‘shared understanding’ of water quality targets and a risk‑based approach to selecting and implementing targets.

The Commission also raised concerns in 2018 about some water quality targets, including the salt export target and the Burtundy salinity target, and noted that there can be a conflict between the salt export objective and salinity targets (PC 2018, pp. 224–225). The MDBA review also concluded that both targets should be further investigated (MDBA 2020g, p. 56).

In its submission to this inquiry, the MDBA said that water quality targets and objectives are currently being reviewed and this work will inform its 2026 Basin Plan Review (sub. 61, response to information request, pp. 6–7).

#### Targets need to be set at the right scale

There are significant differences in the types of water quality threats and risks seen in different valleys and river reaches across the Basin, and within some of the same water resource plan areas. For example, surface water systems can:

* be heavily regulated and used for irrigated agriculture
* include large storages and interconnected infrastructure that supply urban areas, or
* include unregulated rivers with high conservation value.

This raises a question about whether the Basin Plan and WQM plans sufficiently account for these differences. For example, the MDBA has suggested the targets for deoxygenated water in the Basin Plan may be too broad (MDBA 2020g, p. 35). There is considerable natural variation in deoxygenation in the Basin, and a uniform target value does not take this into account. Aquatic life can be severely impacted by localised deoxygenation (box 7.2).

The MDBA’s 2020 review found that some water quality targets in the Basin Plan need defined locations to better reflect local conditions (MDBA 2020g, pp. 3, 44). Basin states observed that they ‘generally preferred to consider the management of water quality issues at the sub‑catchment scale’, and suggested that the scale of water quality targets were sometimes ‘too broad for management of water quality issues’ (MDBA 2020g, p. 23).

Ensuring water quality targets are set at the right scale and there is effective monitoring and adaptive water management within WQM plans will be important considerations for the MDBA’s Review of the Basin Plan.

| Box 7.2 – Fish deaths as the result of localised poor water quality |
| --- |
| Deoxygenated blackwater has resulted in several significant fish death events over the past five years, including in the Darling River near Menindee in late 2018 to early 2019 and again in early 2023.  The events in 2018‑19, which were the subject of an independent review, are estimated to have resulted in hundreds of thousands of fish deaths (some estimates suggest over one million fish deaths) (Vertessy et al. 2019, p. 8). The review found that high flow events in 2012 and 2016 led to high numbers of fish spawning in the Menindee Lakes, and these events were followed by low flows and hot conditions by the end of 2018, which restricted oxygenated water to the surface of the lakes only. These conditions, along with restriction of fish movement due to weirs, meant that when temperatures dropped and hypoxic water spread, fish were unable to escape and died in large numbers (Vertessy et al. 2019, p. 10).  A number of recommendations were made in the review, including reducing extraction during low flows, maintaining connectivity along the Barwon‑Darling River, and changing operating procedures in the Menindee Lakes in order to minimise the likelihood of lakes being at very low levels prior to summer. Importantly, it was recommended that New South Wales and Queensland adopt an ‘active event‑based management approach’ to providing flows through the Barwon–Darling system (Vertessy et al. 2019, p. 13).  An independent review of the 2023 event in Menindee presented similar findings and recommendations. Low levels of dissolved oxygen, high biomass and poor water quality were all found to cause the death of millions of fish (NSW Chief Scientist & Engineer 2023, p. 1). The review noted that ‘mass fish deaths are symptomatic of degradation of the broader river ecosystem over many years’ (NSW Chief Scientist & Engineer 2023, p. 14). Some of the recommendations were similar to the previous review, with recommended long‑term strategies including the restoration of flow regimes and connectivity across the catchment. Shorter‑term recommendations included modifying the nature of water releases to maximise desired benefits and looking into pumping, oxygenation and fish passage infrastructure to enable movement and refuge in selected areas (NSW Chief Scientist & Engineer 2023, pp. 2–3). |
|  |

## Critical human water needs

The Basin Plan is required to give critical human water needs (CHWN) the highest priority. There must be water to meet ‘core human consumption’ needs (that is, drinking water) and to meet other needs that, if unmet, ‘would cause prohibitively high social, economic or national security costs’.[[121]](#footnote-122) These provisions ‘were forged during the Millennium drought and reflect the lessons of that extreme dry period’ (MDBA, sub. 61, p. 12).

The provisions in the Basin Plan about CHWN for the southern Basin are more detailed than those for the northern Basin.

### Arrangements for the southern Basin – in place but untested

For communities that depend on the River Murray System, the Basin Plan sets out the amount of water for consumptive use and conveyance required to meet CHWN.[[122]](#footnote-123) It also sets out water quality and salinity trigger points for when water becomes unsuitable for meeting CHWN, at which point an emergency response is required.

There is a three‑tier system that allows action to be taken in certain circumstances. Tier 1 represents normal water availability and therefore normal water sharing arrangements as outlined in Basin state water management plans. Tier 2 arrangements are triggered under very low water availability conditions and tier 3 is triggered under extremely low water availability conditions. Tier 2 and 3 water sharing arrangements occur in extreme conditions, such as the Millennium Drought, and set out requirements such as conveyance reserves. The Basin Plan sets triggers for moving between tiers and the MDBA is responsible for declaring Tier 2 or Tier 3 water sharing arrangements. Basin states, the MDBA and DCCEEW are required to report on the implementation of these emergency responses.[[123]](#footnote-124)

The MDBA said that these arrangements are working effectively but have not been tested by a severe drought (sub. 61, p. 12). A 2020 review of urban water in the Murray–Darling Basin also noted that communities that rely on the River Murray generally view the CHWN rules with confidence (Marsden Jacob Associates nd, p. 30)

In 2018, the Commission reported that the arrangements for meeting CHWN in communities in the River Murray system appeared to be operating effectively – the relevant provisions in the Basin Plan were ‘robust’ and did not need to be changed (PC 2018, p. 240). On this inquiry we did not hear any evidence to suggest this view should be revised, though some participants raised concerns specific to the upper Murrumbidgee area (box 7.3).

| Box 7.3 – Water quality concerns for the upper Murrumbidgee River |
| --- |
| Some inquiry participants raised concerns about poor water quality and critical human water needs (CHWN) outcomes in the upper Murrumbidgee catchment area. While the area does fall within the Murray–Darling Basin, ‘management arrangements for the [Murrumbidgee] river are largely directed by the operations of the snowy hydro scheme’ (UMCN, sub. 140, attachment, p. 1).  The ACT Government highlighted that:  … in 2019, the perennial Murrumbidgee River ceased to flow at the ACT border, impacting critical human water needs. Annually, the water quality of summer river flows entering the ACT do not meet human health guidelines for enterococci bacteria … The operation of Tantangara Dam by Snowy Hydro, climate impacts, and cross‑border water management arrangements upstream of the ACT border are unfortunately compromising the health and function of the upper Murrumbidgee River (sub. 85, p. 4)  The Upper Murrumbidgee Catchment Network said that CHWN ‘are not prioritised for towns such as Cooma and the ACT’ and that the Basin Plan ‘should be doing more to ensure CHWN for this region’ (sub. 140, pp. 2–3). However, the Network also noted that the complexity of interactions between the Plan and Snowy Hydro arrangements were part of the reason why the upper Murrumbidgee were not being captured in water reform and that a review of the Snowy Hydro operating arrangements for environmental flows was needed.  The Australian River Restoration Centre also stated that CHWN are not prioritised in the upper Murrumbidgee region with the NSW Murrumbidgee Water Resource Plan (WRP) not accredited, noting that the ACT WRP ‘is not able to influence any flows it relies on from NSW’, and ‘outdated’ environmental water management does not do enough to support basic ecological functions (ARRC, sub. 142, p. 2).  The Upper Murrumbidgee Demonstration Reach said there is a need for better water management in the area. It raised concerns about extraction of environmental flows and the upper Murrumbidgee River ‘falling through the cracks’ due to Snowy Hydro operations, which limits ‘remedial measures’ (sub, 143, pp. 1–2).  The *Water Amendment (Restoring Our Rivers) Act 2023* amends the *Water Act 2007* (Cth) and Basin Plan to more clearly define the upper Murrumbidgee region and ensure the Basin Plan better covers the area. An annual reporting requirement on water releases from the Snowy Hydro scheme into the area has been legislated. Funding has also been secured for contingency reserves in the area as well as investment in monitoring and assessment of water quality in the river (Pocock 2023). |
|  |

### Extreme events

WRPs – within and outside the River Murray System – must set out how water resources will be managed, including to meet CHWN, during extreme events.[[124]](#footnote-125) The MDBA said that accredited WRPs have ‘fully incorporated the Basin Plan’s critical human water needs requirements into Basin state water management practices’ (sub. 61, p. 16).

Where WRPs have not been finalised and accredited, the effectiveness of the Basin Plan’s arrangements for meeting CHWN cannot be evaluated because the provisions are not in place. As discussed below, this is of particular concern in the northern Basin.

## The northern Basin

There are long‑standing concerns about water quality and CHWN in various reaches of the Barwon‑Darling system.[[125]](#footnote-126) The Commission heard about these concerns while visiting areas of regional NSW, including Menindee and Bourke. The issue was also raised in a number of submissions.[[126]](#footnote-127)

Access to safe drinking water in the northern Basin is inadequate

The Dharriwaa Elders Group in Walgett NSW argued that CHWN are not given sufficient priority in some areas outside of the context of extreme events. The Group also said that extreme events are not well defined in the Basin Plan and critical human needs ‘must be more clearly defined and given a high priority in water management’ (sub. 86, p. 6).

Other participants said that the experiences of towns like Walgett show that arrangements to meet CHWN in the northern Basin have failed.

* The Wentworth Group of Concerned Scientists said that the arrangements were ‘inadequate’ and that this was ‘most evident in the northern Basin where water quality in towns such as Walgett and Wilcannia has been compromised for some time’ (sub. 81, p. 3).
* Slattery & Johnson pointed out that several towns in Western NSW have had no safe drinking water for the last decade (not just during ‘extreme events’) and that these towns had large Aboriginal populations (sub. 90, p. 16).
* The Environmental Defenders Office (EDO) said the failure to provide safe drinking water in Walgett showed there should be ‘more rigorous’ provision for CHWN for the entire Basin (sub. 91, p. 22). And outside the River Murray System, ‘there is no assurance of conveyance water, or any other form of base flows, for delivering CHWNs’ and CHWN provisions are undermined by ‘complex and inconsistent water management rules and practices’ (EDO, sub. 91, p. 20). The EDO also commented that these pressures would only increase with climate change.

The recently developed NSW Western Regional Water Strategy highlights that poor water quality has been a long‑term concern for the region:

Water quality is generally poor during periods of low or no flow in the Barwon‑Darling and Lower Darling. Poor water quality also occurs after droughts when flows return and during floods – debris and dissolved material from previously dry river channels and floodplains then begin to accumulate … Poor water quality affects aquatic organisms, is a risk to human health and stock, impacts the amenity of waterways and affects Aboriginal people’s ability to practice culture on or near waterways. (NSW DPE 2022f, p. 10)

A 2019 review of the NSW Barwon‑Darling water sharing plan by the Natural Resources Commission found ‘an ecosystem in crisis’ and that the plan had not effectively prioritised the protection of the water source and dependent ecosystems (NRC (NSW) 2019, p. 1). Specifically, it found that the ‘risk of decreasing water quality and increasing algal blooms has elevated under the Plan rules’ (NSW NRC 2019, p. 4).

### Competing water management priorities can impact water quality

Instruments other than the Basin Plan and water sharing plans also affect water quality outcomes in the Basin. For example, the Murray–Darling Basin Agreement (chapters 1 and 9) sets out rules for managing water in the Menindee Lakes. The MDBA cannot direct water to be released from the Menindee Lakes to meet downstream demand when the volume of water in the lakes falls below 480 GL, and until the volume of water in the lakes next rises above 640 GL.

An independent assessment of fish deaths in 2018‑19 found that ‘environmental outcomes downstream of the Menindee Lakes were constrained by the need to adhere to sharing arrangements of the Murray–Darling Basin Agreement’ (Vertessy et al. 2019, p. 58). More generally, the Inspector‑General of Water Compliance has highlighted the sometimes‑competing demands[[127]](#footnote-128) of the Agreement and the Basin Plan and the difficulties this causes for river operators (IGWC 2022d, p. 2).[[128]](#footnote-129)

Under the current *Objectives and outcomes for river operations in the River Murray System* (2023b), when the MDBA is unable to achieve one or more of the objectives because of a conflict, the matter must be referred to the Basin Officials Committee (after first seeking advice from the Water Liaison Working Group and then the River Murray Operations Committee). The Basin Officials Committee may then approve the MDBA to prioritise one or more conflicting objectives or undertake river operations other than specified in the objectives and outcomes document (2023b, p. 16).

Basin governments must all agree on changes to the MDB Agreement, including those concerning management policies at the Menindee Lakes. The NSW government has stated that it is working with other Basin jurisdictions to agree on such changes (NSW DPE 2023c, p. 6).

|  | Finding 7.1  Poor water quality and critical human water needs in the northern Basin |
| --- | --- |
| Some communities in the northern Basin live with a precarious supply of safe drinking water. The current arrangements in the Basin Plan, even if implemented, will not ensure these needs are met. | |
|  | |

### What is being done about poor water quality and CHWN outcomes?

In 2018, the Commission found that Basin communities were justifiably concerned about water quality and the management of CHWN in the Lower Darling and the development of the water resource plan for the New South Wales Murray and Lower Darling was the process to resolve this concern (PC 2018, p. 231). This plan was submitted to the MDBA in August 2023 (having previously been submitted and withdrawn) and is being assessed for accreditation (as of December 2023). Where WRPs are not in place, the Basin Plan’s arrangements for water quality and CHWN cannot be fully implemented. The need to finalise the WRP for the Lower Darling is pressing, particularly given the prospect of another drought.

The NSW Government acknowledged community concerns about poor water quality along the Barwon–Darling and Lower–Darling (Baaka) River and said these issues are ‘likely to continue and intensify’ in future droughts (sub. 43, p. 10). It pointed to a number of programs and strategies it has in place to address these concerns.

* The NSW Government has set up an Independent Connectivity Expert Panel to look at triggers in New South Wales WSPs to better improve connectivity and protect CHWN in the northern Basin. A draft report will be released in early 2024 and a final report later in 2024. The findings of the final report will be used to inform amendments to be made to WSPs by 30 June 2025 (NSW Government, sub. 111, p. 11).
* The ‘Extreme Events Policy’ provides a framework for making decisions during extreme events and ‘establishes the principles by which water resources will be managed’. The recently updated policy (NSW DPE 2023a) explicitly discusses CHWN (NSW Government, sub. 43, p. 10).
* Regional water strategies set out a long‑term road map to improve water security, water quality and flood management for regional towns and communities and improve the health and integrity of environmental systems and assets (NSW DPE 2022f, p. 11)
* The North‑West Flow Plan recognises the importance of inflows from the main Barwon‑Darling tributary valleys in maintaining sufficient water quality and quantity for people and the environment in the Barwon‑Darling River (NSW DPE 2022a).

The NSW Government also outlined actions to improve emergency event protocols in their response to the 2023 Independent Review of the fish deaths event at Menindee. The Chief Scientist’s review of the event highlighted the emergency management framework as ‘dysfunctional and not well understood at the local level’ (NSW Chief Scientist & Engineer 2023, p. 70). Subsequently, the NSW Government updated emergency response actions to include temporary extraction restrictions on low priority licences during drier conditions, with the NSW Environment Protection Authority to develop an interim response plan before the end of 2023. This plan will dictate responses until a ‘Mass Fish Death Sub‑Plan’ is finalised by the NSW Government. Longer term actions have also been outlined, including investment in engagement staff, fish passage and data infrastructure, and a review of water management rules in Menindee (NSW DPE 2023c, pp. 4–5).

However, some participants questioned whether the NSW Government was doing enough. For example, the Central NSW Joint Organisation suggested the aspirations of some policies were not being realised ‘on the ground’ and ‘better policy and protocols’ were needed ‘in a new climate future to ensure water for critical human needs are met as the highest priority’ (sub. 31, pp. 5–7).

Should the Basin Plan do more?

It is clear that more needs to be done to improve water quality and secure CHWN in the northern Basin. Given the transboundary nature of water management in the northern Basin, the Basin Plan is an appropriate instrument to help address CHWN in the area.

Currently, the Basin Plan does not regulate in detail how CHWN should be met in the northern Basin. The Basin Plan and the Water Act cover CHWN in the River Murray System, because the issue was ‘inextricably linked with the shared management of the River Murray System including its infrastructure, and therefore also with the operation of the [MDB] Agreement’ (Australian Government 2012b). In the northern Basin, there is no shared regulating infrastructure, however New South Wales and Queensland have intergovernmental agreements for the Paroo and Border Rivers for water sharing and management[[129]](#footnote-130).

There are some good reasons for state governments to drive policy about CHWN and remain responsible for meeting these needs. For example, state governments are better placed to account for local conditions and considerations. The Coleambally Irrigation Co‑operative warned against a ‘prescriptive’ approach and said that CHWN issues ‘should be addressed catchment‑by‑catchment and entrenched in state planning frameworks’ (sub. 21, p. 6). The Commission’s 2020 review of the National Water Initiative concluded that ensuring access to a ‘basic level of service’ was the responsibility of state and territory governments.

A renewed National Water Initiative should include a commitment by State and Territory Governments to each develop a definition of, and to ensure access to, a basic level of water services for all Australians. At a minimum, this would include safe and reliable drinking water. (PC 2021c, p. 175)

The NSW Government said CHWN provisions ‘could be reviewed to improve clarity and relevance for water resources beyond the River Murray’ and pointed to the need for ‘ongoing support and engagement with the Commonwealth’ to deal with some of these issues (sub. 43, pp. 9–10). However, it also emphasised that CHWN was largely a state matter and greater regulation via the Basin Plan was ‘unlikely to be justified’ (sub. 111, p. 11).

Others argued that the Basin Plan should do more to ensure CHWN are met (box 7.4). The ACT Government suggested that addressing CHWN was one of several issues that were not unique to the Basin but that would ‘benefit from national policy direction, through the renewed National Water Initiative, and coordinated through a national policy agency’ (sub. 85, p. 8). As discussed below, a number of other participants suggested ways the Basin Plan and other intergovernmental agreements and arrangements might be improved to meet these needs.

| Box 7.4 – What participants said about how the Basin Plan could improve water quality and better secure critical human water needs |
| --- |
| CSIRO suggested that ‘hydrological connectivity’ was ‘integral to a healthy Murray–Darling Basin’ (sub. 113, p. 5).  The Inspector‑General of Water Compliance noted that:  … the critical human water needs framework is currently geographically limited, fails to clearly assign roles and responsibilities, and does not treat the Basin as an interconnected system. Extending the regulation of critical human water needs to the northern Basin could usefully be supported by also strengthening the existing framework. … However, there is a risk of the Basin States’ regulatory frameworks and Basin Plan becoming disjointed in relation to critical human water needs. (sub. 133, pp. 6–7)  The Wentworth Group of Concerned Scientists called for Basin‑wide criteria for town water supply and quality, and a ‘systematic assessment of the drivers of poor water quality’ which would ‘consider the potential impacts of upstream irrigation water use, domestic water quality, including the rules governing irrigation water allocations, carryover, and drought reserves in storage dams’ (sub. 81, p. 3).  The Environmental Defenders Office recommended improvements to the reporting and compliance arrangements and said that the Murray‑Darling Basin Authority or the Inspector‑General of Water Compliance should be given a ‘substantial compliance and oversight role in relation to the delivery of water for CHWNs’ (sub. 91, p. 24).  A number of participants stressed the importance of water for food security and some said the definition of CHWN could be expanded to reflect this. The National Irrigators Council, for example, said:  … Human needs should always remain the highest focus, but that should be extended to include some form of food security and availability. (sub. 62, p. 25).  While noting the CHWN provisions in the Basin Plan are ‘generally adequate’, the Department of Climate Change, Energy, the Environment and Water observed that upcoming reviews could consider whether they can be improved to ‘provide certainty across a range of climate change scenarios’ (sub. 77, p. 16).  The Murray‑Darling Basin Authority said the framework for supporting CHWN was ‘limited and focused on the southern Basin’, suggested a ‘set of objectives supported by investment and innovation may be needed to manage this direct risk to social and economic outcomes under climate change’ (MDBA 2020h, p. 122). |
|  |

A number of inquiry participants said the 2026 Basin Plan Review should consider changes to the Plan to improve CHWN in the northern Basin.[[130]](#footnote-131) The Commission agrees that there is scope for the Basin Plan to play a greater role in improving water quality and the arrangements for meeting critical human water needs in the northern Basin. Designing new arrangements will require consultation with Basin governments, communities and experts and should be an important matter for the MDBA to review in its 2026 Basin Plan Review (as acknowledged by the MDBA, sub. 126, pp. 7–8 and the DCCEEW sub. 127, pp. 18–19).

#### Options to better meet CHWN should be considered in Basin Plan review

Participants raised a number of options for improving water quality and CHWN arrangements[[131]](#footnote-132), and noted that the absence of waterway connectivity, base flow and conveyance reserves were major challenges. Some of the options proposed involved increased investment in complementary measures, while others were about changes to water rules or governance.

* **Complimentary measures:** Adding additional environmental indicators, such as for erosion, weeds and pests (Australian Dairy Industry Council, sub. 117, p. 3), carp control (NIC, sub. 130, p. 5), and investment in irrigation efficiency programs (DCCEEW, sub. 127, p. 19).
* **Changes to water rules**:
  + Additional restrictions on extraction, changes to SDLs, and further water recovery[[132]](#footnote-133) – although these options were also strongly opposed by some irrigation groups and others.[[133]](#footnote-134)
  + Review of volumes of water set aside during drought for conveyance needs and consumptive use in WRPs, town supply deliverability and environmental outcomes (CEWH, sub. 116, pp. 4–5).
  + Considering Planned Environmental Water management options for water quality issues beyond the use of Held Environmental Water policy approaches (CEWH, sub. 69, p. 23).
  + Better protection of environmental water from extraction through the northern Basin.
* **Governance:** Better integration of Commonwealth and Basin state frameworks (IGWC, sub. 133, p. 7) and clearer governance and policy direction for responses to extreme events (CEWH, sub. 116, p. 4).

The Commonwealth Environmental Water Holder warned against assuming that environmental water could be repurposed to meet CHWN.

The prospect of more frequent extreme cease‑to‑flow events necessarily requires a review of fundamental policy settings. Opportunities include clearer governance and a hierarchy of measures, rather than the ad hoc reliance on environmental water to respond to emergency situations. (sub. 116, p. 54)

Another option that should be considered is adapting the ‘three‑tier’ arrangements for the southern Basin and applying them to the north, with specific triggers and actions. This could be done through amending chapter 11 of the Basin Plan and the relevant WRPs.

Greater cooperation between Basin states, particularly New South Wales and Queensland, will be necessary, and not only during extreme events. The connectivity of water systems in the northern Basin – and the fact that water quality and CHWN in parts of NSW depend (in part) on water management arrangements in Queensland – underscores the need for intergovernmental cooperation and a greater role for the Basin Plan.

|  | Recommendation 7.1  The Basin Plan should play a greater role in improving water quality and securing critical human water needs in the northern Basin |
| --- | --- |
| Improving water quality and meeting critical human water needs in the northern Basin should be a key priority for the 2026 Basin Plan Review. Noting the connectivity of water systems in the northern Basin, the review should consider:   * how the Basin Plan can contribute to improving water quality and securing critical human water needs in the northern Basin * whether arrangements for the southern Basin can be adapted for the northern Basin * whether changes should be made to other instruments and agreements, including the Murray–Darling Basin Agreement and state water sharing plans. | |
|  | |

# Trading rules

|  |  |
| --- | --- |
| Key points | |
|  | The Murray–Darling Basin Plan seeks to support and improve the operation of water markets in the Basin. Water markets provide a mechanism through which users can adapt to changes in the availability of water, promoting the efficient allocation of water, and they enable water to be purchased for the environment. |
|  | Recent reviews have found that water markets in the Murray–Darling Basin need reform, including in the areas of insider trading, price reporting, water announcements, rule‑making processes, and institutional and governance arrangements.  Basin governments have committed to a roadmap for reform and the *Water Amendment (Restoring Our Rivers) Act 2023* implements a number of the recommended changes. |
|  | The trading rules in the Murray–Darling Basin Plan are one part of the framework governing water markets. They seek to limit restrictions on trade, improve transparency and access to market information, and maintain market integrity and confidence. |
|  | The implementation of the trading rules has been challenging and the water market itself has changed significantly since the trading rules came into effect in 2014. The trading rules have not been comprehensively reviewed since they were made and, given the experience and pressures of the last nine years, the rules should now be reviewed. |
|  | The Murray–Darling Basin Authority (MDBA) should ask the Australian Competition and Consumer Commission (ACCC) to conduct a comprehensive review of the trading rules, including those about trade restrictions, and consider how the rules can be effectively monitored and enforced.  The *Water Act 2007* (Cth) should also be amended to enable the ACCC to provide advice to the MDBA about the rules on its own initiative, to make water market policy more adaptive. The ACCC should notify the MDBA before preparing any such advice. |

## Trading rules support water markets

The Murray–Darling Basin Plan (the Basin Plan) relies on water markets – for example, to enable water rights to be purchased for the environment – and aims to support and improve their operation. The Basin Plan seeks to facilitate the operation of an efficient and effective water market (so water reaches its most productive use), minimise transaction costs on trade, and provide protection for the environment and the interests of third parties.[[134]](#footnote-135)

The Australian Competition and Consumer Commission (ACCC) described the Basin’s water markets as a ‘core element of the Basin Plan’s design’, noting that the markets ‘support the delivery of the plan’s objectives to reset the balance between consumptive and environmental water holdings’. And under a ‘cap and trade’ system, with sustainable diversion limits capping consumptive water, ‘markets are the tool that allow water to move to where its economic value is highest’ (sub. 26, p. 3).

Water markets are also important for helping industries and communities in the Basin adapt to a drier and more volatile climate.

### The purpose of the trading rules

One mechanism to achieve the Basin Plan’s objectives for water markets is the trading rules of the Basin Plan. The rules provide a common framework for the trading of water rights across the Basin. They seek to:

* limit restrictions on trade
* improve transparency and access to market information
* maintain market integrity and confidence.[[135]](#footnote-136)

The trading rules also seek to contribute to the market and trading objectives and principles in the Water Act[[136]](#footnote-137) and reflect, at the Basin level, one of the objectives of the Intergovernmental Agreement on a National Water Initiative – the ‘progressive removal of barriers to trade in water and meeting other requirements to facilitate the broadening and deepening of the water market, with an open trading market to be in place’.[[137]](#footnote-138) Under the National Water Initiative, Australian states and territories agreed that their water market and trading arrangements should:

* facilitate efficient water markets and opportunities for trading within and between states
* minimise transaction costs on trades
* enable the appropriate mix of water products to develop based on access entitlements which can be traded
* recognise and protect the needs of the environment
* provide appropriate protection of third‑party interests.[[138]](#footnote-139)

The trading rules in the Basin Plan are prepared by the Murray–Darling Basin Authority (MDBA) on the advice of the ACCC and are enforced by the Inspector‑General of Water Compliance (IGWC).

The trading rules are only one part of the framework governing water markets in the Basin. Most of the rules governing water trade in the Basin are made by Basin state governments. Basin states are responsible for approving trades and enforcing state trading rules, although state rules must be consistent with the Basin Plan.

The Basin Plan water trading rules are also intended to complement other related instruments, such as the water market rules and the water charge rules. The water market rules ‘provide protections for irrigators who want to permanently transform their irrigation right into a statutory entitlement to water’ (ACCC 2023b). The water charge rules ‘provide price transparency for infrastructure and related services’ in the Basin (ACCC 2023a). These rules are enforced by the ACCC and are not part of the Basin Plan.

Reflecting on the effect of the Basin Plan trading rules since they were made in 2014, the ACCC said the rules had:

… led to improvements in the information available to water users on trade arrangements and restrictions, and to the removal of some distortionary trade restrictions, including volumetric limits and thresholds on water ownership by non‑water users. (sub. 26, p. 5)

On water markets more generally, the Productivity Commission in its 2021 assessment of the implementation of the National Water Initiative found that since 2017 there has been ‘continued progress in a number of jurisdictions in removing trade restrictions and other barriers to trade’ (PC 2021a, p. 57). However, there remain issues with restrictions and distortionary arrangements in some Basin markets and challenges enforcing some of the rules (ACCC sub. 26, p. 5).

### Compliance

In relation to the water trading rules, the IGWC’s regulatory policy states that action will be triggered when:

* restrictions are placed on trades inconsistently with the Basin Plan
* information is not provided about water delivery rights and irrigation rights
* trade approval authorities do not disclose interests in a trade
* information about water access rights is not provided, is inadequate or is not managed in accordance with the Basin Plan
* trading prices are not made available in accordance with the Basin Plan or [relevant information] is inadequate. (IGWC 2023g, p. 8)

The IGWC 2022‑23 workplan states that trade enforcement is a priority for the agency, in particular price‑reporting, trade disclosures, trade accounting and compliance (IGWC 2022a). The IGWC has conducted two audits on the water trading rules. One looked at interstate trade in the Northern Basin (IGWC 2022b) and the other at compliance with disclosure obligations by Victoria’s largest rural water provider, Goulburn‑Murray Water (IGWC 2022c). Both audits found ‘process and system failures’ in relation to Basin Plan obligations (sub. 75, p. 18).

The IGWC has expressed frustration with some of the rules it enforces, including rules about reporting trade prices. Asked at a Senate Estimates hearing in May 2023 about illegal water trading practices, the Inspector‑General said his office had closed multiple investigations in part because the legislation had ‘more get out of jail clauses and opportunities than a Monopoly board’ (Grant 2023, p. 7). As discussed below, this legislation is being amended.

In October 2023, the IGWC released a report (IGWC 2023f) following an investigation into compliance with the trading prices reporting requirements in section 12.48 of the Basin Plan. The IGWC found that the scope of the section was too narrow and that it was too easy to rely on the ‘reasonable excuse’ exemption. It also found there was limited access to good data for IGWC investigators. The IGWC expressed support for water market reforms to address these issues (IGWC 2023f, p. 10).

## Recent reviews of Basin water markets

The framework governing water markets in the Basin was recently the subject of two significant reviews – one by the ACCC (ACCC 2021) and another by Daryl Quinlivan, who was tasked with testing the ACCC’s recommendations with Basin states and other stakeholders and developing a roadmap for reform (Quinlivan 2022).[[139]](#footnote-140)

### A call for decisive and comprehensive reform

The 2021 report on Basin water markets by the ACCC found that many water users ‘do not trust that the markets and key institutions are fair or working to the benefit of water users’ and that ‘decisive and comprehensive reform’ was needed (ACCC 2021, pp. 2, 3).

The final report made recommendations about:

* market integrity and conduct – including about market conduct and integrity legislation, a code for water market intermediaries, and insider trading obligations
* trade processing and water market information – including on data standards, trade approval service standards, water announcements, a repository for water market data, a hub for trade approvals, and a market information platform
* market architecture – transparency of allocation decisions, metering and monitoring, and mechanisms for delivery of environmental water
* governance – the institutional architecture and processes for rule‑making.

In its submission to this inquiry, the ACCC emphasised the importance of implementing reforms to fill gaps in the governance of water markets, including by establishing an ‘independent expert body responsible for advising on market design and assessing whether Basin water markets are operating efficiently’ (ACCC, sub. 26, p. 3).

### A roadmap for water market reform

In October 2022, the *Water Market Reform: Final Roadmap Report* (Quinlivan 2022) was released, and the Australian Government and the Murray–Darling Basin Ministerial Council agreed in principle to implement all of its recommendations (MDBA 2022k).

The Restoring Our Rivers Act implements a number of the recommendations, including by establishing stronger insider trading rules, prohibiting market manipulation, and introducing a code of conduct (to be prescribed by regulations) for market intermediaries – the Water Markets Intermediaries Code. Conduct provisions will be regulated by the ACCC.

Some of these changes affect the trading rules in the Basin Plan. The Act removes some rules from the Plan and places them, in a modified form, in the Water Act – specifically, the rules about reporting trade prices, making water announcements, and insider trading (originally in sections 12.48 to 12.52 of the Basin Plan). The Act also implements the roadmap’s recommendation about tagged water entitlements, removing an exemption from trade restrictions that applied to these entitlements. This makes ‘grandfathered tagged entitlements’ subject to the same restrictions as other water allocation trades.

The Act also gives new functions and powers to the Bureau of Meteorology. This includes issuing water markets data standards and collecting, publishing and providing advice about water markets information. The IGWC will have the role of enforcing compliance with the new data standards.

The Bureau of Meteorology is also developing a water data hub and a website with Basin‑wide near real‑time water market information, including pre‑trade bids and offers. The Bureau said the changes will ‘build transparency, integrity, and confidence’ in the Basin’s water market (sub. 17, p. 13).

The Australian Government has not announced when the remainder of the Quinlivan recommendations will be implemented. Some of the reforms are complex and will take time to implement and some could be progressed with later legislative responses to the review of Schedule D of the Murray–Darling Basin Agreement or the reviews of the Water Act and Basin Plan (Quinlivan 2022, pp. 92–93).[[140]](#footnote-141)

### Water market institutions

Both the ACCC and Quinlivan reports found shortfalls in the governance of water markets in the Basin. The ACCC found that fragmented institutional arrangements were impeding Basin water markets (ACCC 2021, p. 547). This concern was echoed in the Quinlivan report, which said the governance of Basin water markets was ‘highly fragmented’, with numerous government agencies having a role and sharing responsibilities, causing duplication and confusion among market participants (Quinlivan 2022, p. 11).

In part to address these concerns about governance, the ACCC recommended that a new national water markets agency be established. Quinlivan found little support from stakeholders for this proposal, and instead recommended that new water market functions be allocated among existing Commonwealth agencies and the proposed new National Water Commission (Quinlivan 2022, pp. 12, 16).

The ACCC has since said these proposed arrangements would substantially improve water market governance, but ‘uncertainty remains on the establishment, timing and functions of the National Water Commission’ (ACCC sub. 26, p. 4).

The Restoring Our Rivers Act implements some, but not all, of the institutional changes recommended in the Quinlivan report. The Act does not establish a National Water Commission. In a submission to a Senate inquiry, Professors Wheeler, Grafton, Quiggin and Connor express support for many of the proposed changes to water market laws, but suggest the governance arrangements will remain fragmented, arguing that there remains ‘a strong argument for a reestablished and revamped National Water Commission’.[[141]](#footnote-142)

## Review of trading rules

### Rules not reviewed since 2014

The trading rules in the Basin Plan have not been comprehensively reviewed since they came into effect in 2014. Such a review was not in the scope of the recent work of the ACCC or Quinlivan.

If a review were needed, this would be a task for the ACCC; under the Water Act, the MDBA must obtain advice from the ACCC before proposing amendments to the rules (s 42(2)). The ACCC said that the rules need a ‘thorough evaluation’ and suggested that its advice be sought soon, to ensure that it has time to consult widely and that the advice can inform the MDBA’s 2026 review of the Basin Plan (sub. 26, p. 6).

The ACCC noted several developments in Basin water markets that highlight the need for a review:

… there have been significant changes to the volume and location of trade, the participants in the market, Basin State trade administration practices, the evolution of environmental watering arrangements and the impacts of changing climate patterns. The ACCC inquiry found that trade is facilitating significant changes in patterns of water use in the Southern Connected Basin. These patterns are posing increasing challenges to river operators, who are also faced with changing system conditions on a number of fronts. (sub. 26, p. 5)

The Inspector‑General said that the process and system failures of certain trading rules obligations that it identified in recent audits will not be addressed by the current reforms.

The majority of the Basin Plan water trading rules will remain largely unchanged under the water market reform process. Ongoing compliance, enforcement and review of the Basin Plan water trading rules will be required to ensure they support Basin Plan outcomes. (sub. 75, p. 18)

The ACCC suggested that the recent audits of the IGWC also highlight the need for the trading rules to be reviewed. For example, it said one audit ‘identified discrepancies in water trade and sustainable diversion limit accounting’:

The audit identified water being traded from one state but not appearing in an account in the other state, incorrect volumes being recorded in water accounts, and manual adjustments being made by the authorities without documented explanations.

The 2026 review of the Basin Plan, including the Basin Plan water trading rules should help ensure that these rules are effective and can be enforced. (sub. 26, pp. 7–8)

The need for a review was supported by most participants who commented on the matter.[[142]](#footnote-143) Although the Department of Climate Change, Energy, the Environment and Water suggested a review was not necessary because the ACCC and Quinlivan had already provided ‘two comprehensive review processes of water trading in the Basin’ (sub. 127, p. 14), these reviews did not comprehensively review the trading rules.

Some participants emphasised that such a review should consider the environmental and socio‑economic impacts of trade (Inland Rivers Network, sub. 109, Lifeblood Alliance, sub. 119). For example, Inland Rivers Network said:

It is essential that the review must consider the impacts of trade on the environment, including the impacts of Inter Valley Transfers and large movements of trade to areas where it is difficult to supply water orders. Socio‑economic effects of water trading can also be very substantial and have been wrongly attributed to the purchase of and use of environmental water. (sub. 109, p. 4)

And the NSW Farmers' Association said that it was important for the review to:

… examine how conditions like trading zones, or limited parcel size, could be utilised to protect the principles of the National Water Initiative. It will also be critical to assess the feasibility of rationalising trading rules and regulations across all levels of government, all states and all valleys. (sub. 123, p. 8)

Murray Irrigation opposed the review and emphasised the role of the MDBA and the need for a ‘process for costs and benefits to be specified using a suitable consultant and transparent process’ (sub. 118, p. 5).

The ACCC would only be providing advice to the MDBA about the trading rules – consistent with the ACCC’s existing role under the Water Act. It would remain for the MDBA to consider the advice and propose any changes to the trading rules. Any review would also need to be conducted transparently and with appropriate consultation.

Reflecting on its own upcoming work, the MDBA said the 2026 Basin Plan Review provided an opportunity to consider ‘the ecological and river management implications of trade, how water trade and transfer rules are used to maximise the environmental outcomes of held environmental water and the role of Basin water markets as a climate adaptation mechanism’ (sub. 126, p. 8). These are also matters the ACCC should consider in a review of the trading rules.

The MDBA should ask the ACCC to conduct a detailed review of the trading rules, to be completed prior to the 2026 review of the Basin Plan. The review should consider, among other things, whether the current trading rules are operating effectively or need to be clarified or otherwise amended, and whether new rules are needed. It should also consider whether the rules should be changed in light of the Australian Government’s commitment to implement the roadmap for water markets and, as discussed below, give particular attention to the effectiveness of the rules about trade restrictions.

Some participants suggested a review should wait, given other reforms to water market laws are in train. However, the review will take time and the results should inform the 2026 review of the Basin Plan.

#### The review should consider trade restrictions

The rules that seek to remove unnecessary trade restrictions may need particular attention in a review. Removing restrictions on trade is one of the main objectives of the trading rules, consistent with the National Water Initiative. Most restrictions are simply prohibited, but some are permitted when they would be ‘necessary’ for one of the reasons set out in the Plan. The Plan provides that a restriction may be necessary because of:

* the existence of a physical constraint
* the need to address hydrologic connections and water supply considerations
* the need to protect the needs of the environment
* the level of hydraulic connectivity.[[143]](#footnote-144)

These restrictions are described in the Basin Plan at a relatively high level of generality. The terms ‘hydrologic connections’ and ‘water supply considerations’ are defined in the Basin Plan, but otherwise little further guidance is provided about which restrictions might be considered necessary.

A complete list of trade restrictions is not available, but in 2018 the MDBA reported that there were over 1500 restrictions on surface water trade. It is understood that these largely remain in place.

If a Basin state imposes certain restrictions, it must notify the Inspector‑General and give reasons for its decision.[[144]](#footnote-145) It may also ask the Inspector‑General for a declaration that the restriction is necessary.[[145]](#footnote-146) If such a request is made, the Inspector‑General must publish the declaration and supporting reasons.[[146]](#footnote-147)

In 2018, the Commission recommended that the MDBA (which was then responsible for compliance with the Basin Plan trading rules) prepare a framework for assessing trade restrictions (PC 2018). This was intended to help expedite the MDBA’s review of trade restrictions, which it had identified as a difficult and time‑consuming exercise. Relevant matters to consider when deciding whether a restriction should be assessed might include:

* the volume of the affected entitlement
* whether a complaint has been received about the restriction
* whether the restriction appears on its face to be necessary – that is, consistent with the Basin Plan.

An assessment framework could also help ensure decisions about restrictions are principled and consistent, help others understand how and why these decisions are made, and increase transparency and accountability around these decisions.

The MDBA and Basin governments agreed with the 2018 recommendation and indicated that work on the framework was underway, but no framework has been publicly released. Related reforms recommended by the Commission in 2018 include publishing the reasons given by Basin states for restrictions on trade and publishing compliance determinations and supporting assessments.

In a review of the trading rules, the ACCC could consider whether unnecessary trade restrictions are still in place, and if they are, how they might be identified by the regulator and removed, both now and in the future. The review could also consider whether a framework for assessing trade restrictions is needed, or whether the trading rules themselves should be amended to provide greater clarity about which trade restrictions are necessary. It would not be for the ACCC to review all the state restrictions; as it said, its expertise is in ‘markets and regulation rather than the science related to hydrology and environmental management’ (sub. 107, p. 2).

This is not to suggest that there is no place for restrictions on water trade. As noted above, the Basin Plan recognises that some restrictions are necessary to manage hydrological constraints and protect the environment. And in any event, formal trade barriers are not the only obstacle: trade can be inhibited in other ways, such as poor market transparency (PC 2021a, p. 57), which recent reforms seek to address.

#### Ongoing advice from the ACCC

There is a related question about when, more generally, the ACCC should provide advice about the trading rules. The Water Act suggests that the ACCC’s advice must be sought by the MDBA, rather than be provided on the ACCC’s own initiative. However, it is not clear that a request from the MDBA should be a necessary step, particularly if other agencies, such as the IGWC and the ACCC, play a role in the trading rules and are in a good position to know when changes to the rules might need to be considered.

Allowing the ACCC to provide advice about the rules on its own initiative could also ensure the agency maintains an ongoing interest in the effective operation of the rules and has the resources to perform this function. It could also mean that the rules can be more readily changed, when necessary, consistent with an adaptive water market framework. The ACCC noted that:

An ongoing power to instigate advice on its own initiative would have the benefit of allowing the ACCC to provide timely and well‑considered advice to the MDBA. It would make water market policy more adaptive by allowing the ACCC to identify and respond to issues related to water markets and the Basin Plan water trading rules as they arise. It would also allow the ACCC to plan for adequate public consultation and support the ACCC’s independence from other government agencies. (sub. 107, pp. 2–3)

As discussed above, the MDBA would still decide whether the rules should be amended in light of the advice.

|  | Recommendation 8.1  A comprehensive review of trading rules in the Basin Plan |
| --- | --- |
| The Murray–Darling Basin Authority (MDBA) should ask the Australian Competition and Consumer Commission (ACCC) to conduct a comprehensive review of the Basin Plan trading rules. The review should consider, among other things, how unnecessary trade restrictions should be identified and removed.  The *Water Act 2007* (Cth) should be amended to enable the ACCC to provide advice to the MDBA about the trading rules on its own initiative. The ACCC should notify the MDBA before preparing any such advice. | |

# Governance and engagement

|  |  |
| --- | --- |
| Key points | |
|  | Implementing the Murray–Darling Basin Plan (the Basin Plan) – and achieving its objectives – requires robust, transparent governance arrangements, appropriate monitoring, reporting and evaluation processes and genuine community engagement. The transboundary nature of the Murray–Darling Basin means governance and institutional arrangements for water management are inherently complex. |
|  | There have been some positive developments in the governance arrangements supporting Basin Plan implementation since 2018.  The Inspector‑General of Water Compliance was established as the Basin Plan Regulator.  The Basin Officials Committee adopted a new structure and modest transparency improvements.  Basin governments have improved how they engage, including by establishing more direct, local relationships, but there is further room for improvement. |
|  | Strong accountability mechanisms are central to effective Basin Plan implementation, but despite some modest improvements since 2018, arrangements have proved too weak.  Accountability for implementing the Basin Plan would be increased by ensuring consistent and effective regulatory oversight of intergovernmental funding agreements. |
|  | Greater transparency around the actions and decisions of Basin governments would strengthen accountabilities and help foster community confidence.  The activities and decisions of the Basin Officials Committee should be made much more transparent.  The Murray–Darling Basin Authority is working on a new monitoring strategy. It should take the opportunity to streamline and improve reporting arrangements. Ahead of the 2026 Review of the Plan, the  Murray–Darling Basin Authority should conduct a stocktake of monitoring and reporting arrangements and assess how this aligns with what is required to evaluate the Plan. |
|  | Communities want more meaningful opportunities to participate in Basin Plan processes and decisions.  Basin governments rarely provide participants with feedback on the outcomes of Basin Plan engagement processes, including how community feedback was used or influenced decisions.  Permanent, local engagement mechanisms can be an effective way of seeking and responding to participants views, help foster community understanding of policy processes, and build trust.  More coordinated, joined‑up engagement efforts by Basin governments could reduce costs and allow for a more holistic consideration of some issues, including those that are affected by other Australian and state and territory government instruments. |

The success of the Murray–Darling Basin Plan (the Basin Plan) depends on effective institutional and governance arrangements for implementing the Basin Plan, appropriate monitoring, reporting and evaluation processes and meaningful community engagement. This chapter examines these arrangements and identifies changes to improve the efficiency and effectiveness of Basin Plan implementation.

An overview of existing arrangements, and key developments since the Commission’s last assessment in 2018, are discussed in section 9.1. Section 9.2 assesses how Basin Plan accountability mechanisms could be strengthened. Section 9.3 focuses on information and transparency arrangements, including monitoring, reporting and evaluation processes. Section 9.4 examines community engagement practices and identifies opportunities for improvement.

## An overview of arrangements

Governance and institutional arrangements for implementing the Basin Plan are complex. To some extent, this reflects the multijurisdictional nature of water and natural resources management in the Basin.

The *Water Act 2007* (Cth) and the Basin Plan 2012[[147]](#footnote-148) establish the legal basis for Basin management arrangements and assign the Australian Government a significant and ongoing role. However, Basin states are constitutionally responsible for water management in accordance with their respective laws. Basin states also share Basin water resources (and the management of them) in accordance with the Murray–Darling Basin Agreement (2008) (MDB Agreement, box 9.1).

### Roles and responsibilities

The Australian Government and Basin states share responsibility for implementing the Basin Plan and for managing the Basin’s water resources (figure 9.1).

The Australian Government has played a central role in resetting the balance through establishing Sustainable Diversion Limits (SDLs), recovering water to ‘Bridge the Gap’ to SDLs and investing in the SDL adjustment measures. It also has a role in environmental water management, facilitating water trading, monitoring, evaluation and reporting and ensuring compliance with the Basin Plan.

The Basin states, in addition to implementing state‑based water management arrangements (including water resource planning and environmental water management), facilitate water trading and support Aboriginal and Torres Strait Islander values and uses. They are also responsible for ensuring critical human water needs are met, managing water quality and salinity, some aspects of monitoring, reporting and evaluation and implementing the SDL adjustment mechanism.

The Basin Officials Committee (BOC) is the peak body of Basin government officials established under the Water Act to provide advice to decision‑makers on all Murray–Darling Basin matters. It has representatives from the Australian and Basin state governments. The chair of the BOC is appointed by the Australian Government and must be a senior Australian Government official.[[148]](#footnote-149)

Figure 9.1 – Current institutional settings and decision‑making arrangements

Current institutional settings and decision-making arrangements 
A diagram of the institutional settings and decision-making arrangements for the Basin Plan and the Murray Darling Basin Agreement. 

Sources: Basin Plan 2012 (Cth); Water Act 2007 (Cth).

The BOC has dual roles, with responsibilities under both the Basin Plan and the MDB Agreement:

* Under the Basin Plan and the Water Act, BOC advises the Murray–Darling Basin Authority (MDBA) on matters referred to it by the MDBA and on engagement with the Basin states on amendments to the Basin Plan. [[149]](#footnote-150) It also facilitates cooperation and coordination between the Australian Government, the MDBA and the Basin states in managing water resources. And the BOC has operated as a key decision‑maker for some components of the SDL adjustment mechanism program (for example, the SDL adjustment mechanism amendment notifications (chapter 2)) (DCCEEW, sub. 77, p. 11).[[150]](#footnote-151)
* Under the MDB Agreement, the BOC advises the Ministerial Council on the management of the southern Basin’s water and other natural resources. BOC implements Ministerial Council decisions, including on Basin state water shares. BOC also exercises responsibility for high‑level decision‑making regarding river operations and directs the MDBA on MDB Agreement functions. It approves the MDBA’s operating plan and budget for these functions.

The MDBA also has roles and responsibilities under the Basin Plan and the MDB Agreement.

* Under the Basin Plan, the MDBA as an independent authority advises the Australian Government on amendments to the Basin Plan. The MDBA is also responsible for periodically evaluating the Plan, conducting the ten‑yearly Basin Plan Review, and several monitoring and reporting functions.
* Under the MDB Agreement, the MDBA is a service provider, funded by Basin states. The MDBA is responsible for calculating how much water is in the River Murray and notifying New South Wales, South Australia and Victoria of their water share. It is also responsible for delivering River Murray operations, including delivering water to entitlement holders, water management, and the construction, maintenance and management of water infrastructure assets.

| Box 9.1 – The Murray–Darling Basin Agreement  The Murray–Darling Basin Agreement (the MDB Agreement) is a long‑standing agreement between the Australian Government and Basin states for sharing water in the southern Basin and for operating the regulated River Murray system.  The MDB Agreement has a consensus decision‑making model, with each party holding an effective veto. Over time, in addition to operating the regulated River Murray system, jurisdictions have collectively made several significant water and natural resource management reforms, including:   * managing salinity, with the first strategy agreed in 1985 * capping water extractions across the Basin in 1995 * improving environmental flows in the River Murray through The *Living Murray* program, which recovered 500 GL of water for the environment and built environmental works along the River Murray * establishing the framework for southern Basin interstate water trading.   Key elements of the MDB Agreement include provisioning water for system demands (conveyance water) to keep the system running, as well as ensuring that critical human water needs can be met and maintaining water in reserve to meet the following year’s system needs. The MDB Agreement provides for the MDBA to manage the River Murray and to deliver state water entitlements. The MDBA also manages the maintenance and operations of infrastructure (such as dams, weirs and locks) on behalf of Basin governments. Each Basin state contributes funding for managing the regulated River Murray system based on its level of water use. The MDB Agreement also defines the agreed approach between Basin states for how available water resources are shared and outlines supporting water accounting arrangements.  The Basin Plan and MDB Agreement are separate instruments that operate in parallel, with neither instrument having primacy over the other.  Sources: Murray Darling Basin Agreement (2008); *Water Act 2007* (Cth). |
| --- |
|  |

The Basin Community Committee (BCC) is an advisory committee responsible for advising the MDBA about the performance of its Basin Plan functions, including advising on engaging the community in amending the Basin Plan and on community matters relating to the Basin water resources as well as any other matters referred to it by the MDBA.[[151]](#footnote-152) Under the MDB Agreement, the BCC advises the Ministerial Council. The Committee is made up of a chair and 16 members, of which two must be Indigenous Australians and eight must be water users or water user representatives. BCC members are nominated by the Ministerial Council and appointed by the MDBA.

The Inspector‑General of Water Compliance (IGWC) is a statutory office holder responsible for providing independent oversight, monitoring, compliance, and enforcement functions for the Water Act and the Basin Plan. Under the Water Act, the IGWC monitors and oversees the performance of Basin governments and their water agencies. This includes monitoring of commitments and intergovernmental agreements specified in section 215C(3) of the Water Act. Other functions of the IGWC include enforcing compliance with the Water Act, conducting inquiries into agency performance under the Water Act and engaging with the Australian public on Basin water management.[[152]](#footnote-153)

### Funding arrangements

The Australian Government, through the Department of Climate Change, Energy, the Environment and Water (DCCEEW), funds implementation of the Basin Plan. Some of this funding is spent by the Australian Government; and some is provided to Basin states to implement the Basin Plan through the Federal Financial Relations Framework. The Australian Government makes financial contributions to Basin states and in return the Basin states have agreed to implement certain outcomes (such as water efficiency programs, environmental initiatives or infrastructure improvements). For example:

* the Australian Government committed $174 million through the National Partnership Agreement on Implementing Water Reform in the Murray–Darling Basin (NPA) (COAG 2014) which expired 30 June 2020
* under the Federation Funding Agreement – Environment Schedule on Implementing Water Reform in the Murray–Darling Basin (2021‑22 to 2023‑24) (the FFA) the Australian Government committed up to $60 million in payments to Basin state governments to support Basin Plan implementation. This agreement expires 30 June 2024 (CFFR 2021).

Under the FFA, Basin states are required to report annually to the Australian Government on progress against milestones and key performance indicators listed within the FFA. DCCEEW assesses Basin state performance against key performance indicators to determine payments. The NPA was also subject to annual milestone and key performance indicators reporting.

The Australian Government funds the MDBA’s roles under the Basin Plan. Basin states provide the majority of the funding to the MDBA to operate the River Murray system and to support the management of river assets, structures and other joint programs. These costs are shared between the Basin states based on periodic assessments of the relative benefit that each jurisdiction derives from these joint activities (Buckley 2014). For natural resource management programs, after allowing for contributions from Queensland and the Australian Capital Territory, the balance of costs is shared equally between the Australian Government, New South Wales, Victoria and South Australia (Buckley 2014).

### Reporting and evaluation requirements

Schedule 12 of the Basin Plan outlines a range of matters that the MDBA, the Commonwealth Environmental Water Holder (the CEWH), the DCCEEW and Basin states are required to report against (table 9.1). The IGWC has also taken on some reporting. Some matters are reported annually – these are predominantly related to the implementation of, and compliance with, different elements of the Basin Plan. Other elements, more focused on the outcomes of the Basin Plan, are reported five yearly.

The Basin Plan also prescribes a program for evaluating its effectiveness. The MDBA reports annually on the effectiveness of the Basin Plan, conducts an evaluation every five years (the latest in 2020) and is scheduled to review the Basin Plan in 2026.

Table 9.1 – Matters to be reported (Schedule 12 of the Basin Plan)

|  |  |
| --- | --- |
| Matters to be reported on an annual basis | Reporter |
| The effectiveness of the management of risks to Basin water resources | Basin states, MDBA |
| The transition to long‑term average sustainable diversion limits | DCCEEW |
| The extent to which local knowledge and solutions inform the implementation of the Basin Plan | Basin states, MDBA, CEWH |
| The identification of environmental water and the monitoring of its use | Basin states, MDBA, CEWH |
| The implementation of the environmental management framework | Basin states, MDBA, CEWH |
| The implementation, where necessary, of the emergency response process for critical human water needs | Basin states, MDBA, DCCEEW |
| The implementation of the water quality and salinity management plan | Basin states, MDBA, CEWH |
| The implementation of water trading rules | Basin states, MDBA |
| Compliance with water resource plans | Basin states |
| The prioritisation of critical human water needs | Basin states |
| The accountability and transparency of arrangements for water sharing | Basin states |
| Matters to be reported on a five‑yearly basis | Reporter |
| The transparency and effectiveness of the management of the Basin water resources | MDBA |
| The protection and restoration of water‑dependent ecosystems and ecosystem functions in the Murray–Darling Basin, including for the purposes of strengthening their resilience in a changing climate | MDBA |
| The extent to which the Basin Plan has affected social, economic and environmental outcomes in the Murray–Darling Basin | MDBA, DCCEEW |
| The achievement of environmental outcomes at a Basin scale | MDBA, CEWH |
| The achievement of environmental outcomes at an asset scale | Basin states |
| The fitness for purpose of the Basin water resources | MDBA |
| Progress towards the water quality targets | Basin states, MDBA |
| The facilitation, by efficient and effective water markets, of tradeable water rights reaching their most productive use | MDBA |
| The certainty of access to Basin water resources | MDBA |
| The efficiency and effectiveness of the operation of water resource plans, including in providing a robust framework under a changing climate | Basin states, MDBA |

### Key developments since 2018

There have been some important developments to the governance arrangements and engagement processes supporting Basin Plan implementation since the Commission’s last assessment in 2018.

#### A dedicated Basin Plan regulator was established

In August 2021, the IGWC was established to provide independent oversight, monitoring, compliance and enforcement of the Basin Plan and parts of the Water Act. The establishment of the IGWC follows the Commission’s 2018 recommendation to establish a Basin Plan Regulator and transfer the MDBA’s regulatory functions to it (PC 2018, p. 364).

While it is too early to assess the effectiveness of the IGWC, its performance and activity to date suggests it has been an important and positive change that is providing greater transparency and accountability around compliance (for example, in relation to metering and measurement as explored in chapter 4). Many participants to this inquiry were positive about the establishment of the IGWC and its performance. The National Irrigators Council, for example, said it:

… supported the introduction of the IGWC and has welcomed its contribution to the Basin Plan through a number of inquiries and reports delivered to date. The tough cop on the beat helps build confidence in the system and its participants. Further work is needed on this front, but progress is being made. (sub. 62, p. 19)

And the ACT Government stated ‘the IGWC was a positive division of responsibilities to address conflicting functions previously held by the MDBA’ (sub. 85, p. 7) and that:

the status of Basin Plan implementation and water recovery reaffirms the importance of the independent oversight role of the IGWC to strengthen accountability in any future redesign of Basin Plan implementation. (sub. 85, p. 3)

However, some participants questioned the administrative arrangements for the IGWC. Following the transfer of the compliance function from the MDBA to the IGWC, the Office of Water Compliance that supports the IGWC is now located in the DCCEEW. Some participants suggested this arrangement could lead to regulatory capture and a loss of independence (Chipperfield, sub. 85, p. 4). Healthy Rivers Lower Murray observed that:

The office of the Inspector‑General needs to be truly independent, with powers to investigate all serious breaches, whether failure to deliver projects, water theft or other actions undermining the security of the Basin Plan. (sub. 37, p. 1).

Others reported concerns about potential duplication of the role of the IGWC and Basin state authorities (such as the Natural Resources Access Regulator in New South Wales) on compliance monitoring (Gwydir Valley Irrigators Association sub. 89; Namoi Water, sub. 94). The New South Wales Government also noted the importance of making sure that the roles and responsibilities of the IGWC and the Natural Resources Access Regulator are clearly communicated to water users to avoid confusion (sub. 43, pp. 13–14). The IGWC advised the Commission that it was aware of this issue and that it continues to communicate to stakeholders about the distinction between the two agency’s roles, including through its community engagement.

Risks to the IGWC’s independence (actual or perceived) – and any duplication or overlap in regulatory responsibilities – should be monitored and assessed as the IGWC matures. Potential efficiency benefits aside, locating the Office of Water Compliance within the DCCEEW, an agency which the IGWC oversees, does not align with principles of good governance (chapter 1).

The Australian Government announced an independent review of the IGWC in September this year (Plibersek 2023b). The review is looking at whether the IGWC has the relevant powers to carry out its functions. The review’s interim report released in October 2023 identified potential duplication and independence as issues that it will consider (Harris 2023, p. 7,10). The final report is due in January 2024.

#### Reforms to the BOC’s committee structure

In 2018, Basin governments commissioned the *Review of the Murray–Darling Basin joint governance arrangements* (the Claydon Review). Released 18 March 2019, the Claydon Review assessed the BOC’s committee and governance arrangements and identified opportunities for improving them (box 9.2).

| Box 9.2 – Review of the Murray–Darling Basin joint governance arrangements |
| --- |
| On 18 March 2019, Mr Greg Claydon delivered his *Review of the Murray–Darling Basin Joint Governance Arrangements Final Report* (the Claydon Review). The Claydon Review examined the decision‑making processes that support the delivery of water reforms and Basin water management. The Claydon Review found the current arrangements to be complex and that:  The existing governance arrangements are unwieldy, there are too many committees adversely affecting coordination and streamlined decision‑making (Claydon 2019, p. 2).  The Claydon Review also found that the Basin Officials Committee (BOC) was not operating effectively and was neither managing or considering strategic directions or strategic risks. The Claydon Review noted a lack of role clarity and responsibility:  All external stakeholders contacted were confused as to who has what roles and responsibilities, and ‘who is in charge?’, or ‘is there no‑one in charge?’ They were especially concerned about the lack of engagement with the high‑level committees and transparency in their decision‑making. (Claydon 2019, p. 2)  The Claydon Review also noted that some committees were past their ‘use‑by dates’ and this was harming coordination and decision‑making. There was also a strong need for effective collaboration, coordination and cooperation among Basin governments.  To support a shift from an operational to strategic focus and a more programmatic and ‘board‑like’ approach, the Claydon Review supported an independent Chair for the BOC. The BOC’s stakeholder engagement was found to be poor and transparency lacking around the forum and its decision‑making. The Claydon Review also noted cultural issues among members such as a lack of collegiality, courtesy and common purpose that were adversely impacting the BOC’s effectiveness.  The Claydon Review recommended several options for reform to the BOC ranging from ‘light‑touch’ to more comprehensive ‘renovations’ of the BOC and joint governance arrangements.  Source: Claydon (2019) |
|  |

In December 2019, the Ministerial Council endorsed the BOC’s response to the Claydon Review and committed to ten actions to improve the BOC’s effectiveness, strategic focus and to foster joint stewardship. These actions included:

* clarifying the role of the BOC in decision‑making
* adopting a board‑like approach to BOC functions and meetings
* reviewing BOC chairing arrangements by 30 June 2020
* improving communication and stakeholder engagement
* restructuring board committees.

It is difficult to assess the implementation status of many of these actions based on publicly available information. However, the DCCEEW advised that these recommendations were completed or implemented as part of business‑as‑usual BOC settings (pers. comm, September 2023).

There is now more transparency around aspects of the BOC’s operations. BOC proceedings are more transparent – since 11 June 2021, 12 meeting communiqués have been published by the BOC on the MDBA website. Prior to this, none appear to have been published. There is also information on the BOC’s committee structure on the BOC website. The BOC also holds at least one regional meeting each year during the River Reflections Conferences.

The DCCEEW informed the Commission that engagement between the BOC and BCC includes a joint BOC and BCC meeting annually, as well as BOC Chair attendance at several BCC meetings each year. In 2021, the BCC developed in consultation with the BOC, draft principles for BOC transparency which were published by the BCC (BCC 2023). The BCC has continued to stress with BOC the importance of these transparency principles to Basin communities (BCC 2023).

There are further opportunities to improve the transparency of BOC processes, and to elevate community voices in Basin Plan decision‑making, as discussed later in this chapter (sections 9.3 and 9.4).

#### Greater centralisation of Australian Government water functions under the responsibility of the DCCEEW’s water division

In May 2023, the Australian Government centralised several water agencies and functions within the DCCEEW.

* The CEWH’s environmental water and statutory functions were integrated into the DCCEEW’s water division.
* The water infrastructure function was transferred from the Australian Government Department of Infrastructure, Transport, Regional Development, Communications and the Arts to the DCCEEW’s water division.

And, as already noted, while the statutory position remains independent, the IGWC is supported by staff from the Office of Water Compliance, which is now housed in the DCCEEW.

These changes may potentially reduce institutional complexity and increase the DCCEEW’s ability to drive reforms by having greater control over water functions. However, centralisation of water functions can also introduce risks, including reduced role clarity and accountability, and real or perceived conflicts of interest.

#### Basin governments are engaging more …

There have been some improvements to engagement practices over the last five years.

Some agencies have strengthened their local connections and increased investment in direct relationships with Basin organisations and communities. For example, the CEWH has partnered with various basin organisations (such as the Australian Landscape Trust) to foster collaboration on infrastructure and resource management to improve environmental watering outcomes (CEWH 2020).

The CEWH also works with the Department of Environment and Water in South Australia to assess potential uses of environmental water, and to design the watering strategy (CEWH 2021). The CEWH’s Local Engagement Officers (LEOs) are also well regarded for building on‑ground connections between community and the agency (chapter 3). Heather Builth of the First People of the Millewa Mallee, for example, said:

LEOs are a great idea, get people living and participating in the area. (pers. comm., 27 June 2023)

Several participants commended the positive impact of the LEO program and the IGWC has called for its expansion (IGWC 2022, p. 17).

The MDBA has also tried to improve community connection and engagement across the Basin, including by:

* undertaking ‘listening tours’ (involving senior MDBA officials and representatives from the DCCEEW, the CEWH, and Basin states) to provide an opportunity for community members to meet with a range of decision‑makers at a single event
* establishing a dedicated engagement team to support specific initiatives. For example, the   
  Barmah‑Millewa Feasibility Study included dedicated workshops and online forums to help ensure local views and knowledge were captured and considered in the decision‑making process
* hosting the annual River Reflections conference in a regional centre each year to discuss water management challenges and opportunities.

These initiatives are complemented by the MDBA regionalisation process which commenced in 2017 (MDBA 2020e). Key elements of this process include establishing Regional Engagement Officers (REOs) to build community relationships in the Basin, and locating MDBA staff in regional offices in Griffith, Mildura and Murray Bridge. In 2021, the MDBA achieved its 2019 goal of having one third of staff regionally based (MDBA 2021a).

However, several participants commented that although they know the MDBA has a representative in town, their presence and impact is not strongly felt. As discussed in section 9.4, effective community engagement should advance partnerships and actively involve communities in decision‑making – a local presence in communities is important but it is not enough.

The DCCEEW has also implemented various programs aimed at working collaboratively with communities to deliver the Basin Plan. These include:

* a ‘Have your say’ page on the DCCEEW website to receive submissions from the community on Basin Plan implementation
* hosting over ten water recovery and water reform community engagements in the Basin since 2018
* targeted information sessions in six Basin catchments covering remaining water recovery targets.

The Commission heard that Basin states have also taken steps to improve how they engage with Basin communities (box 9.3). Notwithstanding these efforts to improve engagement practices, concerns about the quality and value of Basin Plan‑related engagement processes remain (discussed in section 9.4).

|  |
| --- |
| Box 9.3 – Basin state initiatives to improve community engagement  Basin states have invested in several new community engagement activities in recent years.   * The Victorian Department of Energy, Environment and Climate Action established a consultative committee in April 2022 as part of their Constraints Measures Program feasibility study (Victorian Government, sub. 74, response to information request, p. 35). * The NSW Department of Planning and Environment established a monthly webinar Water Engagement Roundup which provides updates on consultation and engagement activities on Department led water policy and programs (New South Wales Government, sub. 43, response to information request, p. 23). * The ACT Environment, Planning and Sustainable Development Directorate provided funding for the Upper Murrumbidgee Waterwatch program, including platypus monitoring and a regional Frogwatch program. |
|  |

#### … and have increased online water information sources

Several online water information portals have been put in place by Basin government water agencies since 2018 to improve data accessibility. The Bureau of Meteorology (BOM) now provides near real‑time water information by combining information from various state water agencies, the MDBA and the CEWH. In 2020, the NSW Government launched an online portal *WaterInsights* which contains daily river reports, meteorology information and various graphs and maps designed to assist community members make informed decisions around their commercial water usage.

The usability and accessibility of some existing information sources have also improved. The BOM added features to the Murray–Darling Basin Water Information Portal, including data on groundwater levels and groundwater trade as well as more interactive river diagrams for major Basin catchments.

### More significant changes to governance arrangements and engagement practices are needed

While there have been some modest positive developments in governance arrangements and engagement practices since 2018, there remains significant scope to strengthen the arrangements supporting Basin Plan implementation.

It has been known for some time that the Basin Plan will not be delivered by 30 June 2024 – in the past five years alone, over 30 reports and reviews have documented the lack of progress, highlighted significant delivery risks, and made recommendations aimed at getting the Basin Plan on track. However, this reporting has not resulted in action by Basin governments to deliver the Basin Plan, despite Basin governments frequently committing and recommitting to implementing the Basin Plan in full.

Some inquiry participants argued that this ‘talk without action’ has eroded confidence and trust in the Basin Plan and the institutions responsible for delivering it. For example, a licence holder from Bourke, said:

Community trust and confidence in water management are completely eroded as the Bourke community keeps asking for tangible action, however, they are met with a raft of summits, conferences, and working parties obsessed with review annotation and not practical outcomes. (Mervyn John Gordon, sub. 19, p. 2)

The Australian Dairy Industry Council also remarked:

The result of … inaction over many years is that communities feel over‑consulted yet unheard, and that there is a high level of cynicism about participation in future consultations. The same questions are asked, and the same recommendations are made time and time again. (sub. 64, p. 4)

Implementing the Basin Plan – and achieving its outcomes and objectives – relies on dedicated effort and timely action by all Basin governments. However, as recent history shows, it is difficult to persuade or incentivise Basin Plan parties to deliver on their commitments and operate in a collaborative way.

There are several relatively simple, low‑cost changes that could improve the prospects of delivering the Basin Plan in an efficient and timely way. These changes complement the recommendations made in earlier chapters of this report.

* Accountability for implementing the Basin Plan would be strengthened by ensuring there is consistent and effective regulatory oversight of these intergovernmental funding agreements (section 9.2).
* Open and transparent decision‑making aids accountability, and information on Basin Plan processes and outcomes builds the public’s trust and confidence in the Basin Plan. While a lot of information is published, it is disparate and difficult to navigate, and governments are not always transparent about the reasons for their decisions or the evidence on which decisions are based (section 9.3).
* Meaningful engagement with industry and local communities on Basin Plan implementation can improve outcomes and is central to the public’s understanding of, and trust in, the Basin Plan. Engagement processes that are well‑coordinated (among government agencies), have a local and enduring presence in Basin communities, and facilitate genuine exchange, are more effective than one‑way, siloed engagement processes (section 9.4).

## Accountability mechanisms under the Basin Plan

Mechanisms that hold Basin institutions to account for their various roles and responsibilities are critical for effective implementation of the Basin Plan, and the achievement of its objectives.

However, progress to date demonstrates that accountability arrangements under the Basin Plan are often weak or ineffective. Basin governments have failed to deliver the SDL adjustment mechanism as agreed (chapter 2), develop water resource plans on time (chapter 4), and prepare long‑term environmental watering plans (chapter 3).

Clear roles and responsibilities, coupled with independent oversight of how effectively institutions are exercising their responsibilities, are fundamental to accountability. Where taxpayer funds are used to fund Basin Plan activities, there must be mechanisms in place to hold the funding body and the recipient to account. There is scope to improve in each of these areas. Greater transparency around the actions and decisions of Basin governments can also strengthen accountability, as discussed in section 9.3.

### Roles and responsibilities should be clear and coherent

As pointed out by some participants, the roles and responsibilities for Basin Plan implementation across Basin governments are complex and can be confusing. Many participants called for greater clarity and coherence of roles and responsibilities. A foundational principle for good water governance is clarity of roles and responsibilities (chapter 1). Role clarity supports clear expectations and accountabilities which promotes public trust and confidence.

Where roles and responsibilities are unclear, it can lead to important activities and decisions being overlooked (or duplicated), increased coordination costs and reduced accountability (by making it easier to shift blame and avoid responsibility). It can also make it difficult to raise concerns (if there is confusion about which agency is responsible for the issue) and reduce the effectiveness of engagement activities.

Many participants called for greater clarity and coherence of roles and responsibilities (box 9.4). Most concerns raised were general in nature and focused mainly on the number of bodies involved in implementing the Basin Plan than on examples of functions being unnecessarily duplicated, not performed or lacking coherence.

The roles and responsibilities for Basin Plan implementation across Basin governments are complex and can be confusing, but this complex institutional landscape is not necessarily unjustified. The Basin Plan is a significant policy endeavour and involves actions, decisions, investments and processes by the Australian Government, one territory and four state governments. While some Basin Plan activities and roles are best suited to distinct government agencies, other roles need to be shared among several agencies. Basin governments are also responsible for many water and natural resource management functions that are adjacent to – but separate from – the Basin Plan. In this context, a relatively crowded institutional landscape is an inherent feature of the Basin Plan framework.

| Box 9.4 – Participants commented on the lack of clarity around the roles and responsibilities of Basin institutions |
| --- |
| We heard from participants to this inquiry about ‘unclear or disputed responsibilities among governments and government agencies’ (Slattery and Johnson, sub. 90, p. 2) and that it is difficult ‘to navigate and find simple explanations for the various aspects of the Basin Plan’ (Renmark Irrigation Trust, sub. 24, p. 6).  Some participants suggested the complexity and lack of role clarity is resulting in blame shifting (Louise Burge, sub. 98, p. 5), and reducing the effectiveness of community engagement (Murray Irrigation Limited, sub. 65, p. 30).  Many called for greater clarity on roles and responsibilities. The NSW Government, for example, said:  Further improvements could be made to clarify roles and responsibilities as it relates to implementation of the Basin Plan as there are a lot of entities especially in the government‑owned water sector, across all tiers of government, with various overlapping roles and accountabilities and differing arrangements between States. (sub. 43, p. 13)  Others were concerned about coherence and collaboration. The ACT Government suggested an ‘independent functional review of the Commonwealth institutional and governance arrangements for the future Basin Plan implementation and water policy reforms’ (sub. 85, p. 8).[[153]](#footnote-154) And the Central NSW Joint Organisation, a regional collaboration of councils, suggested the complex institutional arrangements would benefit from more effective collaboration between the Basin governments and agencies that enables ‘a fully integrated, whole of catchment approach’ that ‘moves beyond the silos of the past’ (sub. 31, p. 7). |
|  |

That said, the reality is that it has not always been clear who is responsible for leading implementation of the Basin Plan: the Australian Government or Basin states. And the absence of clear leadership has meant key implementation risks have not been managed effectively. As discussed in chapter 2, it is important that the Australian Government exercises leadership to deliver key elements of the Basin Plan and is accountable for its decisions to avoid a future stalemate.

#### Overlapping governance instruments exacerbate the challenge

A further driver of institutional and governance complexity around the Basin Plan is the number of laws, plans, agreements, policies and other instruments that govern Basin water management. In addition to the Plan itself, there is the Water Act, the MDB Agreement, water resource plans, and other state‑based water management instruments (such as water sharing plans).

One major cause of the complexity of the Basin Plan’s governance arrangements is that Basin governments are responsible for implementing both the Basin Plan and the Murray–Darling Basin Agreement. There are overlaps between the two. Before the Basin Plan was made, the Murray–Darling Basin Agreement had been the single, overarching instrument for the collective management of the Basin.

The IGWC submitted that the separate instruments guiding water management in the Basin do not always align well.

[An] unresolved conflict that exists between the Basin Plan, with its focus on environmental requirements, and the [MDB] Agreement, which focuses on water delivery for the southern states and irrigation. This conflict is exemplified by the lack of clear and transparent processes for prioritising needs when there are competing demands for water delivery. (sub. 75, p. 22)

Multiple governance instruments, each operating simultaneously over the same geographical area, may be necessary to reflect the complexity of the Basin and its cross‑jurisdictional management arrangements, but this does not necessarily promote coherent governance arrangements.

There is the risk that overlapping instruments work against each other, due to different focuses, policy objectives or incentive regimes, leading to inefficient decision‑making processes, unclear roles and responsibilities, and undermining trust and confidence in the overall arrangements (for example, the interaction between the Basin Plan and the MDB Agreement). This can further exacerbate the difficulty people face establishing ‘who is responsible for what’ in the Basin. Despite the role of the Basin Plan as the central instrument for setting the parameters of water management, the MDB Agreement has not been reviewed to identify what its relation should be to the Basin Plan.

Such a review might provide an opportunity to consider where the two instruments complement each other and how that complementarity might work in practice. It would also provide a chance to review the current operating rules for the River Murray – which were designed for delivering irrigation water orders efficiently – in order to maximise the benefits from environmental water and constraints easing. The Basin Plan has been in place for 11 years. A review of the MDB Agreement is overdue.

Clear and coherent governance arrangements for the Basin Plan, while important, will be insufficient for realising the Basin Plan’s objectives. Effective coordination between the implementation of the Basin Plan, and the operation of other Australian and state government instruments that affect the Basin (such as those relating to natural resource management, town water service delivery and planning arrangements) is also needed. As chapter 3 explores, greater coordination of land and water management activities at the Basin scale will be needed to fully realise the Basin Plan’s objectives.

Based on the views submitted to this inquiry, there is scope to improve community understanding of the specific roles and responsibilities of each Basin government agency involved in Basin Plan implementation. Governance arrangements may also benefit from a more coherent and holistic framework that clearly – and transparently – articulates how key governance instruments work together and explains how conflicts among instruments are managed when they arise. Further, given governance and institutional complexity can lead to a confusing monitoring and reporting environment, and a high volume of fragmented engagement processes, there is a case for clarifying and streamlining these arrangements. These issues are discussed in sections 9.3 and 9.4 respectively.

### Funding agreements need to set the right incentives …

The Basin Plan is underpinned by a series of intergovernmental funding agreements. A review by the IGWC identified 40 agreements in relation to water and Basin Plan deliverables with 58 schedules and 774 milestones covering $1.84 billion in payments (IGWC, sub. 75, p. 8). Implementing the Basin Plan cost‑effectively and on time relies on the parties to these agreements meeting their commitments.

Under the new agreement,[[154]](#footnote-155) in exchange for extending the deadline for the SDL adjustment mechanism, Basin states will ‘provide additional assurances and accountabilities’. At the time of this report, the full details of these strengthened accountability arrangements, and their potential effectiveness, were not public.

The Commission’s 2018 assessment of the Basin Plan found that there were weaknesses in the design of the (now expired) NPA that reduced its usefulness to hold Basin states to account for meeting their commitments. The weaknesses included milestones that were poorly defined; no option for partial payments; key information relevant to progress was not publicly released and assessments against milestones were not released in a timely manner (PC 2018, p. 55). The Commission recommended that any future funding agreements should ensure:

* the roles of the Australian Government and Basin state governments are clearly identified
* specific performance milestones are identified, and that clear responsibility is assigned for the delivery of each milestone
* where milestones are linked to payments, that these payments are disaggregated with a payment per milestone to provide a genuine incentive for implementation
* reporting on the progress of Basin governments in meeting milestones is timely
* independent assessment of the progress of Basin governments is undertaken
* advice provided by relevant agencies (such as the MDBA or the CEWH) is used to inform assessments of progress and is published in full (PC 2018, p. 326).

A 2020 review of the NPA by ARTD Consultants also found that there were opportunities to improve future intergovernmental funding agreements, including ensuring that milestones and key performance indicators clearly prescribe outputs and outcomes. (DAFF 2020, p. vi, vii).

Since 2018, reforms to the Federal Financial Relations Framework have addressed some of these concerns. Standardised processes and documentation for funding agreements have increased the identification of roles and responsibilities and disaggregation of milestone payments has improved. That said, some agreements still contain key performance indicators or milestones that are poorly defined and outputs and outcomes that could be more clearly prescribed (for example, Implementing Water Reform in the Murray–Darling Basin Agreement (Implementing Water Reform Agreement).[[155]](#footnote-156)

While some agreements have clear reporting arrangements, there is scope to improve the reporting, including around what measured outcomes were achieved and evidence on their cost‑effectiveness, in line with Principle 8 of the Federal Financial Agreement Principles (CFFR 2020). As discussed in chapter 2, with the proposed extension of timelines for delivering the Basin Plan, there is an opportunity to improve future funding agreements to ensure they incentivise parties to deliver on their commitments.

### … and be subject to adequate oversight

There are gaps in the current oversight and compliance arrangements for intergovernmental agreements that cover financial arrangements between the Australian Government and Basin states for Basin Plan implementation.

Through its oversight function, the IGWC provides the public with the assurance that agencies are doing what they say they are doing, which drives transparency and accountability and promotes trust and confidence in the Basin Plan and its institutions. Oversight and performance monitoring can also show where implementation is being done well and where there are opportunities for improvement.

The IGWC stated it has oversight of only nine of the 40 intergovernmental agreements relevant to Basin Plan implementation (sub. 75, p. 23). The nine agreements are listed in s. 215C of the Water Act (some of the listed agreements have expired). An example of an agreement that is currently *not* in the jurisdiction of the IGWC is the Implementing Water Reform Agreement, which builds on the already completed National Partnership Agreement on Implementing Water Reform in the Murray–Darling Basin.

The rationale for providing IGWC with oversight of some, but not all intergovernmental agreements, is not clear. The explanatory memorandum for the Bill that established the IGWC does not detail why some agreements are listed in the Water Act and not others. The Australian Minister for Water can prescribe additional agreements under regulation, but this option has not been used. The inconsistency means some intergovernmental funding agreements are only subject to broader government accountability arrangements (such as the Australian National Audit Office oversight and accountability arrangements under the Federal Financial Relations Framework). This creates a mismatch where some agreements are within the remit of the IGWC while others are not, without a good basis for the difference in treatment.

Based on the principles of consistency and clarity, the IGWC’s oversight and compliance role would be made more effective if it had jurisdiction over all intergovernmental funding agreements, unless there is a clear rationale for not doing so.

Participants to this inquiry supported providing the IGWC with the power to monitor and oversee any new intergovernmental funding agreements.[[156]](#footnote-157) In addition to providing consistent treatment and improving the effectiveness of the IGWC’s oversight arrangements, the NSW Farmers’ Association stated this could help to improve community trust and confidence in the Basin Plan and Basin governments through greater transparency and assurance (sub. 123, p. 8).

There may be good reasons why certain intergovernmental agreements are not suited to being overseen by the IGWC (for example, where they have expired, the financial outlay is small, or there is minimal connection to the IGWC’s functions), but these have not been made public.

The remit and expertise of the IGWC makes it well placed to provide regulatory oversight of more intergovernmental funding agreements relating to Basin Plan implementation. Given the importance of independent oversight, and the work program the IGWC has established in this area, the Australian Government Minister for Water should prescribe by regulation additional intergovernmental agreements over which the IGWC should have oversight.

|  | Recommendation 9.1  Extending oversight of intergovernmental funding agreements relevant to Basin Plan implementation |
| --- | --- |
| The Australian Government Minister for Water should prescribe by regulation additional intergovernmental funding agreements that the Inspector‑General of Water Compliance (IGWC) should oversee.  The Australian Government Department of Climate Change, Energy, the Environment and Water should consult with Basin state governments, the IGWC and other interested parties to determine which new and existing agreements should be prescribed and make public the rationale for including or excluding each agreement in the IGWC’s remit. | |
|  | |

## Information and transparency

Transparent information is central to accountability, and it can give taxpayers and the broader community confidence that the Murray–Darling Basin is being managed effectively and efficiently.

However, the Commission heard that many participants find it difficult to navigate and use the information available on Basin Plan funding, decision‑making processes and outcomes. And some participants said they would like different types of information, including information about key processes and decision‑making forums.

### It is difficult to access information

While there is a lot of information available on the Basin Plan, it can be difficult to access, navigate, understand and interpret. Participants commented on the lack of a single source of truth for Basin information but noted the difficulties in establishing one. The Lifeblood Alliance, for example, said the ‘plethora of voices and giggababble’ would make it hard to establish a single voice (sub. 52, p. 12). And the NSW Irrigators Council cautioned against creating multiple ‘single sources of truth’ within the Basin (sub. 110, p. 19).

The fragmented nature of Basin water management information can lead to can inconsistencies between information sources.

* The ACT Government noted that the amount of water used in the Basin during 2018‑19 – as reported by four separate Australian Government agencies (MDBA, BOM, Australian Bureau of Statistics, Australian Bureau of Agricultural and Resource Economics and Sciences) – ranged from 4176 GL to 7484 GL (ACT Government, sub. 85, p. 7).
* Similar problems were observed with water storage information provided via the NSW Water Insights portal and the BOM water storage interactive maps (information is updated at different times, resulting in significantly different storage levels for the same catchments).

This issue of fragmentation is made worse by the complex institutional landscape around the Basin Plan. The IGWC Community Sentiment Research also found that – with at least six Australian Government agencies having a direct role in water management in the Basin, and many more at the state and territory level – there is confusion when identifying which agency is responsible for publishing particular information (sub. 75, p. 5).

| Box 9.5 – Participants said accessing information on the Basin Plan is not easy |
| --- |
| The Inland Rivers Network (sub. 82, p. 2) called for improved transparency and regulation around the investment of public money in Basin Plan implementation.  The Inspector‑General of Water Compliance described the information on funding and costs as ‘opaque’, in part because of the number of changes to Basin Plan‑related programs over time and said ‘it would be almost impossible for a member of the public to digest and comprehend the movements and program changes’ (sub. 75, p. 7).  Information about SDL adjustment mechanism projects is another area where information is difficult for community members to access. Leeton Shire Council said:  … getting updates on the SDLAM projects has proved challenging at both the national and state level, even for local Councils. These projects have huge consequences for communities and there is absolutely no excuse for secrecy or a lack of transparency. (sub. 72, p. 2)  Several participants emphasised the importance of making all information used in decision‑making publicly available, to promote good decision‑making and to help hold decision‑makers to account. The Australian Conservation Foundation, for example, said:  Information used to manage the water in the basin needs to be freely available if management is to improve and public trust restored and maintained. (sub. 88, p. 2)  And the Australian Dairy Industry Council said:  Given the number of organisations, both state and federal, involved in decision making on policy, operations and programs, improving transparency is imperative to ensure community confidence in decision making. (sub. 117, p. 3)  Participants were also frustrated with a lack of accurate scientific information about the outcomes achieved using water that has been recovered for the environment (Central Murray Environmental Floodplains Group, sub. 6, Northern Victorian Irrigators, sub. 7).  Others commented that the lack of a ‘publicly accessible, single set of water accounts for the Basin’ hinders accountability for achieving Basin Plan objectives (Wentworth Group of Concerned Scientists, sub. 81, p. 4). |
|  |

Tracing where taxpayer money is spent on implementing the Basin Plan (and the outcomes achieved from the spending) is also not easy. Information on the Basin Plan’s costs, benefits and outcomes is difficult to find. The Basin Plan evaluation is an important opportunity to provide transparency about the costs and benefits of the Basin Plan (discussed below). There is also scope for agencies to improve their public reporting to provide the Australian community with greater clarity around implementation funding (for example, funding for the new agreement has not been disclosed), costs and what has been achieved.

Poor transparency around whether and how decision‑making in the Basin is informed by good information is also impairing the effectiveness of arrangements. The IGWC’s 2022 Annual Community Sentiment Survey found that many respondents considered:

… water management decisions were not transparent, and that political motives or mismanagement were affecting the public perception of water management across the Basin. (sub. 75, p. 6)

Information on key decisions and processes, such as the SDL adjustment mechanism projects, has been difficult for communities to access. Improving transparency around Basin decision‑making and management can help to show where and how decision‑making in the Basin is informed by good information. This can help to promote trust and confidence in the Basin Plan and its institutions. Chapter 6 explores how knowledge and information can inform decision‑making, including transparency around this.

|  | **Finding 9.1**  **Information about Basin Plan funding, processes and outcomes can be difficult to access** |
| --- | --- |
| Information about Murray–Darling Basin water management is fragmented and difficult to navigate. This can cause confusion about which agency to go to for information and reported information can differ across agencies. Communities can find it difficult to understand and engage with water policy and practice. Inconsistencies in information can undermine public confidence and trust in Basin institutions and instruments. | |

### Complex monitoring and reporting arrangements are reducing transparency

Effective reporting, monitoring and evaluation is critical to the successful implementation of the Basin Plan. There are two important aspects to reporting on the Basin Plan.

* Basin states, the MDBA, the IGWC and others report on implementation of and compliance with different elements of the Basin Plan. This is generally reported annually.
* The MDBA reports on the effectiveness of the Basin Plan and progress against its objectives. This includes annual reports on effectiveness, evaluations of the Basin Plan every five years, and the upcoming review of the Basin Plan in 2026.

It was expected that as implementation of the Plan progressed, governments and the community would want to focus less on the first type of reporting and more on the second. This would enable judgements on whether the significant public investment in the Basin Plan had been worthwhile and whether more needed to be done (or done differently). But very slow progress by Basin governments on key Basin Plan elements (chapters 2 and 4), and the related difficulty this leads to in terms of maintaining trust and confidence in the Plan, has encouraged a continued focus on maintaining accountability around implementation. For example, the Australian Dairy Industry Council called for reporting to focus more on outcomes:

The [Australian Dairy Industry Council] supports the intent of the Basin Plan to improve environmental outcomes across the Basin – that is the reason for the Basin Plan. Environmental outcomes should be the focus of measuring success of the Basin Plan, not simplistic measures of volumes recovered. This includes developing a systematic approach to quantifying outcomes, modelling to estimate what can be achieved, and the adoption of complementary measures to help us get there. (sub. 64, p. 7)

While reporting on implementation progress is important, the volume of implementation monitoring and reporting – by multiple agencies – may be obscuring important information and impeding accountability. For example, the 2020 evaluation by the MDBA found more than 100 outputs from monitoring and research programs, with important learnings and recommendations were ‘most often buried in numerous highly technical reports, which results in information being inaccessible to many audiences’ (MDBA 2020j, p. 172).

All this reporting may not be contributing meaningfully to the bigger picture. The MDBA found that – despite the large amount of information available – it did not have the information needed to undertake the Basin Plan evaluation in 2020.

A number of monitoring programs across the Basin were developed for purposes other than the Basin Plan (e.g., the Sustainable Rivers Audit) and have been modified in an attempt to meet current needs. While there is evidence that pre‑existing and new programs broadly align with Basin Plan objectives, a combination of issues – including fragmented results and findings, variability in monitoring methods, and disconnection across state boundaries – have reduced the value of information available to the Evaluation. These knowledge gaps have influenced the ability to fully evaluate against baseline conditions and to understand how conditions have changed over time. (MDBA 2020h, p. 131)

There is a need for Basin governments to explicitly shift focus to reporting that supports accountability for the *outcomes* of the Basin Plan and better supports adaptive management. The NSW Government observed:

The investment in a coordinated long‑term Basin‑scale [Monitoring, Evaluation and Reporting] program would facilitate the collection of comprehensive, consistent and relevant data on water availability, water quality, biodiversity, social, economic, cultural and ecological indicators and the impact of climate change, to support evidence‑based decision‑making and adaptive management strategies in future reviews and implementation. (sub. 43, p. 15)

In 2018, the Commission recommended the evaluation framework provide the basis to guide development of a monitoring strategy. This recommendation was accepted by governments, and the MDBA said its implementation is in progress (sub. 61, p. 45). The two key elements to ensure the new monitoring strategy is effective are to take a more strategic approach to monitoring and reporting, and to ensure the periodic evaluations of the Basin Plan are effective.

#### How to make the new monitoring strategy more effective

A more strategic approach to monitoring and reporting is needed. Ahead of the 2026 Review of the Basin Plan, the MDBA should conduct a stocktake of the Basin‑related monitoring information currently being collected (both by governments and other parties) and undertake an assessment of how this aligns with what is required to evaluate the Basin Plan. This would allow for important information gaps to be identified. It could also reveal areas of low‑value reporting, duplication and overlap in reporting efforts, or other areas where responsibility is unclear. The outcomes of this stocktake should inform the development of the new monitoring strategy.

The MDBA reports that it is working towards such a process.

There is an opportunity in the 2026 Basin Plan Review to consider the framework for Monitoring and Reporting (Basin Plan chapter 13). In its current form, it is designed to support the MDBA role of evaluating the effectiveness of the Basin Plan however there could be room to simplify and improve these arrangements by drawing a better distinction between the evaluation function that rests with the MDBA and the compliance function that rests with the Inspector‑General of Water Compliance. (sub. 61, p. 17)

That is not to say that existing monitoring of important processes and outcomes should be abandoned. Indeed, the Commission is recommending expanding oversight of intergovernmental funding agreements (recommendation 9.1), publication of material used for decisions (recommendation 6.3) and a monitoring framework for the northern Basin toolkit (recommendation 2.3). But there is a need to work towards a system of monitoring and reporting that contributes to the overall strategic direction and goal of the Basin Plan, not just its individual parts. As the NSW Government put it:

… continued efforts to establish a robust monitoring framework into the future that encompasses comprehensive and consistent data collection across the Basin is required. This includes monitoring water quality, water flows/groundwater levels, social, economic, cultural and ecological indicators, and climate trends to capture the complex dynamics of the hydrological system. (sub. 43, p. 14)

One avenue for this work is the Basin Condition Monitoring Program, which the MDBA is developing to operate alongside other long‑term monitoring programs. This program consists of 15 projects on cultural, environmental, social, hydrology and economics issues, and is scheduled to run through to December 2025 (MDBA 2022f).

This presents an opportunity to improve the approach to monitoring and reporting. The MDBA described its process as a ‘community‑centred bottom‑up’ approach to identify key issues and themes’ (MDBA 2022f, p. 4). At the same time, the MDBA has been consulting an inter‑jurisdictional working group to ‘ensure there is no overlap and the projects complement existing monitoring’ (MDBA 2022f, p. 5). The intention is for this monitoring program to integrate with and complement other monitoring and research work occurring across the Basin (MDBA 2022f, p. 6).

While the community is interested in ensuring integrity around implementation of the Basin Plan, participants are often overwhelmed and confused by current monitoring and reporting arrangements. The MDBA, in its role in evaluating the Basin Plan at the Basin scale and monitoring the condition of the Basin, should look for opportunities to ‘cut through’ this overcrowded space.

#### The need for effective evaluation

Evaluation is the systematic process of making a judgment about the merit or worth of a policy or program. It is a key tool for evidence‑based policy, and an important way that policies and programs can be improved over time. The Basin Plan represents good practice because regular review and evaluation were included from the start (box 9.6). But for evaluation to play its critical role, it needs to be high quality and useful. In particular, it is important that Basin Plan evaluations lead to lasting improvements in program or policy design (or better decisions about where to spend public funds).

In 2018, the Commission raised concerns about a real or perceived conflict of interest of the MDBA conducting the evaluation while also implementing the Basin Plan – the MDBA could be ‘marking its own homework’ (PC 2018, p. 257). To rectify this, the Commission recommended a Basin Plan Regulator take on the evaluation role.

Following the 2020 evaluation, participants continued to raise the potential conflict of interest as a concern. For example, the Murray Valley Private Diverters said:

If monitoring and evaluating the success of the Murray Darling Basin Plan … is to be managed or overseen by the MDBA, then conclusion is easily reached that this would be ‘monitoring one’s own homework’ and that systemic failures will never be rectified. (Murray Valley Private Diverters, sub. 95, p. 16)

| Box 9.6 – Basin Plan key evaluation questions |
| --- |
| Chapter 13 of the Basin Plan lists the key questions that the Murray–Darling Basin Authority must ask when undertaking an evaluation.   1. To what extent has the intended purpose of the Basin Plan … been achieved? 2. To what extent have the objectives, targets and outcomes set out in the Basin Plan been achieved? 3. How has the Basin Plan contributed to changes to the environmental, social and economic conditions in the Murray–Darling Basin? 4. What, if any, unanticipated outcomes have resulted from the implementation of the Basin Plan? 5. How could the effectiveness of the Basin Plan be improved? 6. To what extent were the actions required by the Basin Plan suited to meeting the objectives of the Basin Plan? 7. To what extent has the program for monitoring and evaluating the effectiveness of the Basin Plan contributed to adaptive management and improving the available scientific knowledge of the Murray–Darling Basin?   Source: Basin Plan, s.13.06. |
|  |

It has been clear for some time that the Basin Plan would not be delivered on time or in full, yet the 2020 evaluation did not recommend or lead to any material changes to the Basin Plan or implementation arrangements. As noted earlier, the MDBA highlighted that problems with data and information had led to knowledge gaps that affected its ability to conduct the evaluation (MDBA 2020h, p. 131). Participants to this inquiry also raised concerns about the MDBA’s 2020 evaluation and the response to it. Coleambally Irrigation Cooperative, for example, said:

The MDBA evaluation of the Basin Plan in 2020 produced data and reports but did not provide the analysis needed to deliver improved decision‑making. As noted earlier in this submission, our observation is the MDBA has not taken a leadership role in identifying solutions or changes needed to Basin Plan implementation. (sub. 21, p. 7)

The Basin Plan sets out the key questions for the evaluation (box 9.6) and they are a good basis for evaluation.

Even though it might start out with the right questions, the evaluation could in some way be hampered by a lack of clarity around the Basin Plans objectives and outcomes. While the Basin Plan sets out a range of detailed objectives and high‑level outcomes, they do not form a cohesive picture.

That said, the MDBA could take a leadership role in scoping out the most appropriate outcomes – indeed this could be informed by the evaluation itself. (As with the monitoring and reporting issues identified earlier.) Such a process is considered a cycle: starting with policy or program design; then setting objectives and collecting baseline data; then using evaluation findings to inform future policy and program design.

The MDBA is currently planning for the 2025 evaluation of the Basin Plan. It is important that this evaluation draws out learnings from Basin Plan implementation, identifies what is working well and what could be done better, and holds all responsible agencies to account for their actions (including expenditure of taxpayer funds).

The MDBA could consider partnering with the Australian Centre for Evaluation so that the 2025 evaluation becomes a model of best practice. The Australian Centre for Evaluation has set up a ‘community of practice’ across a number of departments and agencies, which the MDBA should join.

### The Basin Officials Committee is a ‘black box’

#### How the BOC operates is not well understood or documented

The BOC has an important role to play in Basin Plan implementation (section 9.1). However, the BOC’s activities and processes are not transparent, and there has been a lack of timely and clear information about the:

* outcomes of committee meetings, especially subcommittees
* notifications made by the BOC with respect to amendments to SDL adjustment mechanism projects (chapter 2)
* directions and delegations from Ministerial Council to the BOC
* community engagement activities undertaken by the BOC.

This lack of transparency makes it difficult to fully articulate and understand the BOC’s role, have confidence in what it is doing, monitor its performance or hold it to account. The National Irrigators Council noted that, while improvements have been made in recent years, this is not delivering the level of transparency required.

The Federal Minister has started to publish agendas ahead of [Ministerial Council] meetings, but it is often only a day or two before the meeting and is very limited. Both [Ministerial Council] and [BOC] should publish the full agendas and papers of their meetings well in advance of the meetings, and detailed minutes of discussions and outcomes in a timely way following the meetings. Every drop of productive water use is monitored, modelled, metered and reported on by multiple agencies. The community deserves the same level of transparency and accountability from decisions makers. (sub, 62, p. 23)

#### The BOC has previously committed to improving transparency, but other than the published communiqués, there is no publicly available evidence of additional transparency initiatives being progressed. Public information on the BOC does not provide communities with a clear understanding of how the BOC operates.

#### The transparency of the BOC should be improved

Transparency around the Basin Plan’s governance processes is critical for providing communities with confidence. While there may be aspects of the BOC’s operations that should remain confidential (such as advice to Ministerial Council or their respective ministers), there are several practical ways transparency could be improved. Wherever possible, the BOC should publish:

* meeting agendas, communiqués and other relevant information on meeting outcomes
* formal directions to BOC from Ministerial Council
* information on BOC’s stakeholder engagement activities, including its engagement with the BCC
* information on the Committee’s governance practices, including on subcommittees and establishing instruments or terms of reference.

#### An independent Chair for the BOC would strengthen governance arrangements

The BOC is chaired by a senior Australian Government official appointed by the Australian Water Minister.

In 2018, the Commission found that there was a strong case for an independent Chair of BOC (PC 2018, p. 28). The Claydon Review came to the same conclusion (Claydon 2019, p. 3). An independent Chair offers several advantages.

* It would remove the real or perceived conflicts of interest that can arise from having an Australian Government official in this role.
* By not being aligned with any Basin government, an independent Chair may be more effective at facilitating a culture of joint ownership and collaboration among Basin governments and building productive relationships with individual BOC members.
* By being independent of short‑term political pressures, an independent Chair could help to steer BOC towards decisions that take a Basin‑wide and longer‑term approach to managing the basin’s water resources.

For the same reasons, the Murray–Darling Basin Commission, which preceded the BOC, had an independent chair for 20 years before the Water Act was made.

| Box 9.7 – Participant support for improving BOC’s transparency |
| --- |
| Many stakeholders supported the Commission’s recommendation that the Basin Officials Committee improve the transparency of its activities, and that it should have an independent chair (Inland Rivers Network, sub. 109, p. 2; NSW Irrigators Council, sub. 110, p. 9; Lifeblood Alliance, sub. 119, p. 11. For example, the NSW Farmers' Association said:  Transparency on the decision‑making process is greatly needed to help improve the social licence of the MDBA and other state and federal agencies who are involved in delivering the Basin Plan. (sub. 123, p. 8)  The National Irrigators Council similarly noted that ‘transparency in decision making and authority is key to provide all stakeholders confidence’ (sub. 130, p. 10). The Australian Dairy Industry Council also supported improving transparency:  Given the number of organisations, both state and federal, involved in decision making on policy, operations and programs, improving transparency is imperative to ensure community confidence in decision making. (sub 117, p. 3)  And the Inspector‑General of Water Compliance in support, noted that the current arrangements limit its capacity to perform their functions effectively and the new proposed arrangements would enable a higher level of accountability (sub. 133, p. 7). |
|  |

Changes to chairing arrangements would require amendments to the Murray‑Darling Basin Agreement and the Water Act. These amendments should be pursued as part of the upcoming Water Act review or as part of any legislative amendments following the Basin Plan review.

|  | **Recommendation 9.2**  **Improving the transparency of the Basin Officials Committee** |
| --- | --- |
| The Basin Officials Committee (BOC) should be more transparent. The BOC should publish:   * meeting agendas, communiqués and information on meeting outcomes * BOC decisions and the reasons for those decisions * formal directions to the BOC from the Ministerial Council * information on the BOC’s strategic priorities, stakeholder engagement activities, governance practices and sub‑committees.   The *Water Act 2007* (Cth) should be amended to enable the appointment of an independent Chair to the BOC. | |

## Community engagement

### Effective engagement is critical to the success of the Basin Plan

Implementation of the Basin Plan hinges on effective community engagement on a range of matters including environmental watering activities, the development of water resource plans, and how to best manage the impacts on communities of a reduction in the consumptive pool of water.

When engagement is done well, it supports the community’s confidence and trust in the Basin Plan and ensures that the views and knowledge of Basin communities are genuinely considered in Basin water resource management. Good engagement can also facilitate accountability through the sharing of information on the performance of Basin government institutions, and the achievement (or otherwise) of Basin Plan outcomes.

Effective engagement with the community is another core principle of good water governance (chapter 1). We also considered principles of effective community engagement (box 9.8) and the International Association for Public Participation (IAP2) participation spectrum in assessing Basin Plan‑related engagement processes. The IAP2 participation spectrum (table 9.2) is a widely accepted means of selecting the level of participation that best defines the public’s role in an engagement program and is a valuable tool for shaping effective engagement processes in the Basin.

Table 9.2 – The IAP2 participation spectrum

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | ***Inform*** | ***Consult*** | ***Involve*** | ***Collaborate*** | ***Empower*** |
| **Participation goal:** | *To provide the public with information to help understand issues and opportunities* | *To obtain feedback* | *To work with the public to ensure that concerns are understood and considered* | *To partner with the public in each aspect of the decision* | *To place final decision‑making in the hands of the public* |
| **Participation promise:** | *We will keep you informed* | *We will keep you informed, listen to concerns and seek feedback* | *We will work with you to ensure your concerns and aspirations are reflected in the alternative options developed* | *We will look to you for advice and incorporate your advice to the maximum extent possible* | *We will implement what you decide* |

*Source: International Association for Public Participation (2019)*

Despite some evidence that engagement has improved in recent years (section 9.1), many participants expressed frustration and disillusionment with Basin governments’ engagement practices. For example, the National Farmers’ Federation noted that:

The community consultation and engagement efforts in the implementation of the Plan have fallen short of expectations. Despite extensive consultations, the lack of meaningful action and implementation of the recommendations has undermined the effectiveness of these efforts. (sub. 46, p. 15)

| Box 9.8 – Effective community engagement |
| --- |
| Some of the principles commonly used to describe effective community engagement in the Basin are:   * partnership and collaboration with those affected by a decision throughout the decision‑making process * participants being given the time, information and evidence to support meaningful engagement with the issues * decisions being communicated openly, transparently and in an accessible way * an environment where decision‑makers and those affected by decisions can engage in a meaningful and on‑going fashion.   Participants called for engagement practices that are consistent with these principles. For example:  Government needs to engage early, fully, transparently and authentically with local communities, valuing and respecting them as genuine partners with capabilities for co‑designing solutions. (Leeton Shire Council, sub. 72, p. 3)  Having the CEWH and state environmental water holders and other water related agencies making combined decisions with community on‑ground knowledge is a good model that needs to be replicated. (Inland Rivers Network, sub. 82, p. 5)  Sources: Moore (2016); OECD (2022); PC(PC 2018). |

Issues related to how Basin governments engage with First Nations people on Basin Plan matters is explored in chapter 5.

#### Participants do not always feel genuinely heard or understood

Very few participants said there should be more engagement by governments on implementation of the Basin Plan. However, there was a lot of support for more meaningful engagement (box 9.9).

The IAP2 participation spectrum (table 9.2) lists collaboration as involving community advice being incorporated as much as possible into the development of decisions. However, we heard that engagement is often a ‘one‑way conversation’ and participants do not feel that their participation is influencing key decisions (or even reaching ultimate decision‑makers). There is very little feedback provided by governments on the outcomes of engagement processes.

Effective engagement principles (box 9.8) point to the importance of decisions being communicated openly and transparently. This includes communicating the information and processes that led to a decision being made, as well as the decision itself. For communities to observe that engagement has been genuine and meaningful, Basin governments should communicate how community participation influenced the decision‑making process. This transparency can also incentivise meaningful engagement practices by Basin parties.

| Box 9.9 – Many participants were concerned about a lack of meaningful engagement |
| --- |
| Some participants said they felt that the concerns they raised were not heard.  We know that our concerns over these [dune] blowouts did not go above the Catchment Management Authority (CMA); they got lost in the government bureaucracy. We need to cut out that middle section and directly connect our cultural interests with the actual decision‑makers at DEECA. (Latji Latji Mumthelang First Peoples, sub. 78, p. 2)  The sentiment that engagement processes are often futile was particularly strong among Aboriginal and Torres Strait Islander people and groups. For example, on planning workshops for water resource use and water resource plans, the Environmental Defenders Office reported on MLDRIN’s assessment.  … there was not always enough time or provisions of appropriate information to enable Nations to participate fully and in an informed way. (sub. 91, p. 31)  Similarly, Dharriwaa Elders Group said:  … engagement with Dharriwaa Elders Group seems to be about managing us rather than truly listening to us. (sub. 86, p. 10)  Gwydir Valley Irrigators Association also noted a lack of meaningful engagement practices.  … at the MDBA River Reflections conference, they [DCCEEW] appeared aloof and without interest in answering the questions and concerns raised with them. (sub. 89, p. 16)  Lachlan Valley Water observed that some engagement processes feel like a box‑ticking exercise.  We are also concerned that the community engagement has not actually been about listening to communities throughout the Basin but about simply complying with a requirement to ‘consult’ communities rather than listen to them. (sub. 54, p. 8)  Likewise, South Australian Murray Irrigators observed that:  The consultation processes are multi‑jurisdictional and layered. Many community leaders are exhausted by this because of the frustration and lack of substantial achievements towards solving problems. (sub. 96, p. 9) |

#### Engagement across agencies is not well coordinated

There are at least 14 Australian government and Basin state agencies with functions that require them to engage with communities and key stakeholders on Basin Plan implementation and Basin water management.

However, the Commission heard that engagement by different government agencies is generally not well coordinated, and this creates a significant burden on those participating in Basin processes. Disjointed engagement can create barriers to participation (as there are time, travel and other costs involved with each process) and often people are required to repeat their views and stories to multiple agencies, leading to frustration and engagement fatigue (box 9.10).

While some government agencies, such as the Department of Planning and the Environment in New South Wales, have taken positive steps in publishing engagement plans in advance, it remains difficult for community members to identify the many disparate engagement processes going on across the Basin.

More generally, participants observed that the relatively narrow focus of engagement activities around a specific issue or agency responsibility, does not always align with how people experience issues in the Basin, namely, as holistic problems with which they have full lived experience.

| Box 9.10 – Participants pointed to consultation fatigue |
| --- |
| Lifeblood Alliance:  Unfortunately, little has changed in the intervening period [since 2018], with the same issues being raised again and again by the same people at consultation forums, and the Basin Plan continuing to be blamed for all manner of ills in the irrigation industry for which it is not responsible. (sub. 52, p. 11)  Griffith City Council:  The Community is suffering from ’consultation fatigue’. Further, many express frustration that environmental priorities have been considered as more important than the people who live and work in the Basin. (sub. 18, p. 2)  The Committee for Greater Shepparton:  … the ongoing consultation with communities that is often framed or limited to a local, state or even system level is inconsistent with the community’s ability to impact the outcomes and has progressively contributed to the ongoing sense of futility and fatigue. (sub. 80, p. 10)  Participants also noted that engagement opportunities are often advertised at late notice, clash with other agencies’ engagement processes, or are held in regions of the Basin that do not make sense. The National Farmers Federation, for example, said:  Recent examples of poor notice, apparent ‘limited access’ and misleading information do little to instil community confidence in process and support for their concerns. (sub. 46, p. 2).  And Citrus Australia pointed out that Basin governments do not sufficiently consider the seasonal nature of agricultural work when scheduling engagement sessions, particularly around harvest time (pers. comm, June 2023).  Additional concerns raised about consultation fatigue and coordination of engagement activities are discussed in appendix B. |
|  |

Many participants supported the Commission’s interim finding that engagement by government agencies is not well coordinated (For example, NSW Irrigators’ Council (sub. 110, p. 9) and NSW Farmers’ Association (sub. 123, p. 9). More coordination of engagement plans by government agencies with Basin Plan responsibilities could reduce the engagement burden on participants, save public resources and avoid some of the frustration that comes from repeatedly participating in processes without feeling genuinely heard. Poor coordination has the effect of undermining attainment of even the lower levels of engagement in the IAP2 participation spectrum (table 9.2) by limiting the effectiveness of obtaining meaningful feedback through consultations.

On a positive note, the MDBA has conducted nine rounds of ‘listening tours’ which involved a range of senior MDBA officials as well as representatives from DCCEEW, CEWH and state water agencies visiting Basin communities. This batched approach to engagement allows community members to engage with multiple different decision‑makers without expending additional time and effort attending separate events. Conversely, the Commission also heard that government engagements on environmental watering activities are generally conducted separately by the Victorian Environmental Water Holder, MDBA and CEWH.

There are trade‑offs to consider when coordinating engagement processes, and trying to combine processes that have distinctly different purposes is unlikely to be effective. However, batching together complementary processes can reduce overlap and duplication for participants and governments, and potentially allow for a more holistic consideration of key issues.

|  | **Finding 9.2**  **Engagement by government agencies on the Basin Plan is not well coordinated** |
| --- | --- |
| There are many Australian Government and Basin state agencies that engage with the community on the Murray–Darling Basin Plan. These engagement processes are generally not well coordinated, which can frustrate participants. More joined‑up engagement efforts could reduce costs for participants and governments and allow for a more holistic consideration of issues. | |

### Lessons for more effective engagement in the Basin

#### Local engagement mechanisms for decision‑making

One instance where the engagement approach appears to be working well – for participants and the agency alike – is the LEOs program used by the CEWH (section 9.1). The LEOs provide a local, direct, continuing and responsive mechanism for feeding community views into the development and implementation of environmental watering proposals. The Commission also heard that the LEOs are effective at building relationships and trust in local communities, something that can be difficult for government departments to achieve. For example, Sunrice supported the collaborative and integrated relationships built by LEOs:

We have two in the Murrumbidgee. They are great. They work really collaboratively with the NSW environmental water managers as well. (pers. comm, 8 June 2023)

The LEOs efforts have enabled greater community collaboration in line with the IAP2 participation spectrum (table 9.2) as government actively reaches out to the community for advice. Direct local relationships better facilitate the flow of community views to the CEWH as these relationships serve as a more accessible means of engagement over other traditional government access points.

The MDBA has also sought local engagement through its use of REOs. Unlike the LEO’s, the scope and purpose of the REO’s role is quite broad (reflecting the broad nature of the MDBA’s roles and responsibilities in the Basin). The Commission heard that this broad remit has created some ambiguity about the purpose and utility of the REOs, which may have limited their integration and engagement with local communities.

|  | **Finding 9.3**  **Well defined local outreach can be an effective engagement approach** |
| --- | --- |
| Local, place‑based engagement mechanisms can be an effective way of ensuring community views are sought, responded to, and considered by decision‑makers. A permanent local presence in communities can help foster community understanding of water policy processes and build relationships and trust. The Commonwealth Environmental Water Holder Local Engagement Officer model provides a good template for effective local engagement. | |

#### Strengthening community voices

Formal mechanisms for incorporating community views into decision‑making processes can help improve community engagement and support a more participatory approach to water management.

In the Basin Plan context, the BCC plays an important role in providing community views and advice to the MDBA (which are then provided to the BOC) – but the impact that the BCC advice has on the BOC’s activities is unclear. Along with stakeholder engagement more broadly, BOC does not directly report on its interactions with the BCC, and it is rare for the BCC to be mentioned in BOC communiqués.

Strengthening the BCC’s role should complement, not replace, community‑led approaches across Basin policymaking and implementation. It is not a substitute for effective engagement or participatory design – although it provides another mechanism for allowing communities to have their say when important decisions are made that affect them.

Many participants supported strengthening the community voice through a standing agenda item for the BCC at BOC meetings (box 9.11). However, some participants stated that their support was conditional upon greater transparency around how BCC members are appointed (Lifeblood Alliance, sub. 119, p. 11; Inland Rivers Network, sub. 109, p. 4; and National Parks Association of NSW, sub. 121, p. 4).

| Box 9.11 – Support for strengthening the voice of the Basin Community Committee |
| --- |
| There was broad support for providing the Basin Community Committee (BCC) with a standing item at Basin Officials Committee meetings (NSW Irrigators’ Council, sub 110, p. 10; Lifeblood Alliance, sub. 119, p. 11; Regional Australia Institute, sub 124, p. 5; National Irrigators’ Council, sub 130, p. 10.  The Inspector‑General of Water Compliance observed that the change is ‘necessary to address some of the barriers to effective participation by all relevant stakeholders in informing decisions that affect them (sub. 133, p. 7).  Others, such as the National Parks Association of NSW (sub. 121, p. 4) supported the change but argued that more transparency was needed around how the BCC is appointed and its terms of reference. The Inland Rivers Network noted that it:  … supports the strengthening of the community voice in Basin decision‑making as long as this includes the full variety of community opinion and that information is based on evidence. More transparency is needed about how the BCC is appointed and its Terms of Reference. A balance of representation across all community perspectives is important. (sub. 46, p. 4)  NSW Farmers’ Association said:  Collaborative partnerships and valuing local knowledge is critical to success for any program and these two factors are sorely lacking for the current decision‑making process. We strongly support the recommendation. (sub. 123, p. 9)  Murray Irrigation Limited also supported for the recommendation, and suggested that:  key decision‑making process should have an explicit community engagement strategy, and this should be agreed as part of normal planning for MDBA and DCCEEW projects and programs. These should be documented and agreed as part of BOC approval process and communication of strategic initiatives.(sub 118, p. 4) |
|  |

Providing the BCC with a standing agenda item at BOC meetings, as is done at Ministerial Council meetings, would help strengthen the feedback loop between communities and decision‑makers. The BCC could provide an ongoing community‑wide perspective to the BOC’s operations, better understand socio‑economic impacts and restore a sense of agency among Basin communities. The BOC should also publicly report on how or where the BCC advice has been considered and influenced the BOC’s advice or operations. There may also be other opportunities for strengthening the BOC‑BCC relationship – in the past, the BOC and the BCC have held joint workshops, which may also be another useful option for strengthening the community’s voice.

There may be times where the sensitive nature of the issues being discussed and deliberated at the BOC mean the BCC’s presence may not be appropriate. That said, a standing item does not prevent the BOC from having these discussions and could provide the BOC with an opportunity to incorporate the BCC’s advice before such discussions or decisions are made. As a broad principle, there is value in having a complete feedback loop between Basin communities and government officials during important water management decisions – instead of being consulted after important decisions have been made. More must be done to improve community input into Basin governance and decision‑making.

|  |  |
| --- | --- |
|  | Recommendation 9.3  Strengthening the community voice in Basin decision‑making |
| The Basin Community Committee should have a standing agenda item at Basin Officials Committee meetings to provide input and advice on matters from a community perspective. The Basin Officials Committee should publicly report on how this input and advice has been considered and has influenced decision‑making. | |

1. Public engagement

This appendix outlines the engagement process undertaken for this inquiry and lists the organisations and individuals who participated.

Following the receipt of the terms of reference on 2 May 2023, an advertisement was placed in The Australian and The Land, and a circular was sent to interested parties. A call for submissions was released on 17 May 2023 to assist people wanting to make a written submission to the inquiry.

An interim report was released on 30 October 2023. The Commission received 145 submissions, including 103 prior to the release of the interim report and 42 post the interim report (table A.1). We also received 25 brief comments. Submissions and brief comments are available online at https://www.pc.gov.au/inquiries/current/basin-plan-2023/submissions

The Commission met with representatives from Australian, state and territory government agencies, First Nations groups, water authorities, private irrigation corporations, local government, regional development groups, environmental and catchment management groups, irrigator and dryland farming groups, agricultural industry groups and corporations, and regional and local community groups (table A.2).

We also held 17 public forums over the period June to August 2023 (table A.3). The forums gave Basin communities an opportunity to share their views on the implementation of the Basin Plan over the past five years and provide ideas for improvements. Appendix B provides details on what the Commission heard at these forums and one‑on‑one meetings with community members and organisations across the Murray–Darling Basin.

In accordance with section 89 of the *Water Act 2007* (Cth), the Commission established a stakeholder working group for this inquiry. The working group is an important avenue for engagement. It provides a forum to exchange information and views on issues relevant to this inquiry (table A.4 lists the membership of the group).

After the release of our interim report, we also held a roundtable with some of the First Nations peoples we had met with during our earlier consultations (table A.5).

The Commission would like to thank everyone who participated in this inquiry.

Table A.1 – Submissions

| Participants | Submission no. |
| --- | --- |
| ACT Government | 85 |
| Anne Jensen | 39 |
| Aron Gingis | 141 |
| Australian Academy of Technological Sciences and Engineering | 71, 135 |
| Australian Competition and Consumer Commission | 26, 107 |
| Australian Conservation Foundation | 88 |
| Australian Dairy Industry Council | 64, 117 |
| Australian River Restoration Centre | 13, 142 |
| Australian Water Brokers Association | 139 |
| Balonne Shire Council | 70 |
| Barrie MacMillan | 45, 125 |
| Barry Croke | 12 |
| Ben Blackburn Racing | 3 |
| Bob Newman | 114 |
| Bourke Shire Council | 79 |
| Bureau of Meteorology | 17 |
| Campaspe Shire Council | 49, 115 |
| Central Irrigation Trust | 33, 122 |
| Central Murray Environmental Floodplains Group | 6, 57, 120 |
| Central NSW Joint Organisation | 31 |
| Cobram Estate Olives | 51 |
| Coleambally Irrigation Cooperative | 21 |
| Commissioner for the River Murray (SA) | 47 |
| Committee for Greater Shepparton | 80 |
| Commonwealth Environmental Water Holder | 69, 116 |
| Cotton Australia Ltd | 68 |
| CSIRO | 113 |
| Department for Environment and Water (South Australia) | 136 |
| Department of Climate Change, Energy, the Environment and Water (Australian Government) | 77, 127 |
| Department of Energy, Environment and Climate Action (Victoria) | 131 |
| Department of Regional Development, Manufacturing and Water (Queensland) | 112 |
| Dharriwaa Elders Group | 86 |
| Dr Melinda Hinkson | 59 |
| Dugald and Justine Bucknell | 66 |
| Environment Victoria | 99 |
| Environmental Defenders Office | 91 |
| Fleur Thompson | 14 |
| Friends of the Merbein Common | 8 |
| Fruit Growers Victoria | 44 |
| Goulburn Valley Environment Group | 28 |
| Griffith City Council | 18 |
| Gwydir Valley Irrigators Association | 89 |
| Healthy Rivers Lower Murray | 37, 106 |
| Inland Rivers Network | 82, 109 |
| Inspector‑General of Water Compliance | 75, 133 |
| Institute for Water Futures and Institute for Climate, Energy and Disaster Solutions, Australian National University | 35 |
| Jan Beer | 38, 108 |
| Jason Modica | 32 |
| Jeremy Cass | 20 |
| Jodie Hay | 63 |
| Kate Chipperfield | 56 |
| Ken Jury | 100, 145 |
| Lachlan Valley Water | 54 |
| Latji Latji Mumthelang First Peoples | 78 |
| Leeton Shire Council | 72 |
| Lifeblood Alliance | 52, 119 |
| Louise Burge | 98 |
| Lower Murray Water Strategic Advisory Committee | 9, 129 |
| Macquarie Marshes Environmental Landholders Association | 93 |
| Mervyn John Gordon | 19 |
| Moira Shire Council | 25 |
| Murray Irrigation Limited | 65, 118 |
| Murray Lower Darling Rivers Indigenous Nations | 92 |
| Murray Regional Strategy Group | 27 |
| Murray River Group of Councils | 22 |
| Murray Valley Private Diverters | 95 |
| Murray–Darling Basin Authority | 61, 126 |
| Murraylands and Riverland Landscape Board | 48, 132 |
| Murrumbidgee Irrigation | 73, 128 |
| Namoi Water | 94 |
| National Farmers’ Federation | 46, 134 |
| National Irrigators’ Council | 62, 130 |
| National Parks Association of NSW | 41, 121 |
| Nature Conservation Council of New South Wales | 50 |
| Newly formed Gingham Lower Gwydir landholders | 23 |
| Northern Victorian Irrigators | 7 |
| NRM Regions Australia | 36 |
| NSW Aboriginal Land Council | 101, 144 |
| NSW Farmers Association | 76, 123 |
| NSW Irrigators Council | 103, 110 |
| NSW Government | 43, 111 |
| NSW South‑West Water Users Association | 16 |
| Pastoralists Association of West Darling | 42 |
| Sarah Wheeler, Quentin Grafton, Jeff Connor and John Quiggin | 104 |
| Regional Australia Institute | 124 |
| Renmark Irrigation Trust | 24 |
| Ricegrowers’ Association of Australia | 60, 105 |
| River Lakes and Coorong Action Group | 15 |
| Riverina and Murray Joint Organisation | 58 |
| Robert Campbell | 29 |
| Robert Watson | 53 |
| Ron McWhae | 10 |
| Russell Crichton | 55 |
| Slattery and Johnson | 90 |
| SmartRivers | 102 |
| South Australian Murray Irrigators | 96 |
| Southern Riverina Irrigators | 97 |
| Speak Up | 2 |
| Stephen Henty | 1 |
| Summerfruit SA | 30 |
| Ted Hatty | 5 |
| Temba Orchards | 87 |
| Trangie Local Aboriginal Land Council | 40 |
| Tuesday Browell | 4 |
| Upper Murrumbidgee Catchment Network | 84, 140 |
| Upper Murrumbidgee Demonstration Reach | 83, 143 |
| Val McWhae | 11 |
| Victorian Automotive Chamber of Commerce | 67 |
| Victorian Farmers Federation | 34, 138 |
| Victorian Government | 74 |
| Watertrust Australia | 137 |
| Wentworth Group of Concerned Scientists | 81 |

Table A.2 – Consultations

| Participants |
| --- |
| Australian Almond Board |
| Australian Commercial Wine Producers Limited |
| Australian Competition & Consumer Commission |
| Australian Conservation Foundation |
| Balonne Shire Council |
| Barkandji Native Title Group |
| Barkindji Maraura Elders Environment Team Limited |
| Barwon‑Darling Water |
| Basin Community Committee |
| Bourke Shire Council |
| Bureau of Meteorology |
| Citrus Australia |
| Coleambally Irrigation Co‑Operative Limited |
| Committee for Aboriginal Water Interests |
| Commonwealth Environmental Water Holder |
| CRC TiME |
| Department for Environment and Water (SA) |
| Department of Climate Change, Energy, the Environment and Water (Australian Government) |
| Department of Energy, Environment and Climate Action (Victoria) |
| Department of Finance (Australian Government) |
| Department of Planning and Environment (NSW) – Water |
| Department of Planning and Environment (NSW) ‑ Water for the Environment |
| Department of Regional Development, Manufacturing and Water (QLD) |
| Dried Fruits Australia |
| Environmental Defenders Office |
| Environment, Planning and Sustainable Development Directorate (ACT) |
| First People of the Millewa Mallee Aboriginal Corporation |
| Goondiwindi Regional Council |
| Goulburn‑Murray Irrigation District Water Leadership Group |
| Goulburn‑Murray Water |
| Goulburn Valley Environmental Group |
| Greater Shepparton City Council |
| Griffith City Council |
| Gwydir Valley Irrigators Association |
| Hay Shire Council |
| Healthy Rivers Dubbo |
| Inspector‑General of Water Compliance |
| Kilter Rural Ltd |
| Lachlan Valley Water |
| Latji Latji Mumthelang First Peoples |
| Leeton Shire Council |
| Macquarie Food and Fibre |
| Macquarie Marshes Environmental Landholders |
| Mallee Catchment Management Authority |
| Mandandanji First Peoples |
| Menindee Food and Fibre |
| Menindee Local Aboriginal Land Council |
| Mildura Rural City Council |
| Moree Shire Council |
| Murray Darling Basin Authority |
| Murray Irrigation Limited |
| Murray Lower Darling Rivers Indigenous Nations |
| Murray Region Strategy Group |
| Murray River Group of Councils |
| Murray Valley Winegrowers Inc |
| Murrumbidgee Field Naturalists |
| Murrumbidgee Irrigation |
| Namoi Water |
| National Farmers Federation |
| National Irrigators Council |
| Nature Conservation Council of NSW |
| NSW Irrigators Council |
| NSW South Western Water Users |
| Pastoralists Association of West Darling |
| Renmark Irrigation Trust |
| Ricegrowers Association of Australia |
| River Lakes and Coorong Action Group |
| Riverina Winegrape Growers |
| South Australian Murray Irrigators |
| South‑West Indigenous Corporation |
| SunRice |
| Trangie Area Aboriginal Land Council |
| Victorian Environmental Water Holder |
| Victorian Farmers Federation |
| Wamba Wamba First Peoples |
| Yarkuwa Aboriginal Corporation |
| Yorta Yorta Nation Aboriginal Corporation |

Table A.3 – Public forums

| Forums | Dates, 2023 |
| --- | --- |
| Shepparton | 6 June |
| Echuca | 7 June |
| Deniliquin | 8 June |
| Griffith | 27 June |
| Mildura | 28 June |
| Hay | 28 June |
| Renmark | 29 June |
| Leeton | 29 June |
| Goolwa | 7 July |
| Menindee | 18 July |
| Dubbo | 18 July |
| Warren | 19 July |
| Bourke | 20 July |
| Moree | 31 July |
| Goondiwindi | 1 August |
| St George | 2 August |
| Dirranbandi | 3 August |

Table A.4 – Stakeholder working group

| Participants |
| --- |
| Australian Floodplain Association |
| Committee for Aboriginal Water Interests (observer) |
| Environmental Defenders Office of Australia |
| Lifeblood Alliance |
| Murray Darling Association |
| Murray Lower Darling Rivers Indigenous Nations |
| National Farmers Federation |
| National Irrigators Council |

Table A.5 – First Nations Roundtable

| **Participants** |
| --- |
| Barkandji Native Title Group |
| Dharriwaa Elders Group |
| First People of the Millewa Mallee Aboriginal Corporation |
| Latji Latji Mumthelang First Peoples |
| Mandandanji First Peoples |
| Southwest Indigenous Corporation |
| Yarkuwa Indigenous Knowledge Centre Aboriginal Corporation |
| Yorta Yorta Nation Aboriginal Corporation |

1. Public forums – what we heard

The Productivity Commission engaged with communities across the Murray–Darling Basin – visiting towns, holding public forums and one‑on‑one meetings. This appendix sets out how we engaged with communities across the Basin and ‘What we heard’ from people and organisations in these communities.

We want to thank everyone who participated in the public forums and one‑on‑one meetings. We recognise the importance of what we heard, and its value in informing this report.

* 1. Our approach

We undertook an eight-week round of public engagement across the Murray–Darling Basin, commencing 6 June 2023 and concluding on 3 August 2023.

We visited 17 towns across the Basin, holding a public forum in each location (table B.1).

Table B.1 – Public Forums

Towns visited across the Murray–Darling Basin

| Region | Towns | When |
| --- | --- | --- |
| Northern Victoria and the NSW Murray Valley | Shepparton – Echuca – Deniliquin | 6, 7 & 8 June |
| NSW Murrumbidgee Valley | Griffith – Hay – Leeton | 27, 28 & 29 June |
| Victorian Sunraysia and the South Australian Riverland | Mildura – Renmark | 27, 28 & 29 June |
| South Australia’s Lower Lakes | Goolwa | 7 July |
| NSW Menindee Lakes and the Lower Darling | Menindee | 18 & 19 July |
| NSW Macquarie and Barwon Darling Valleys | Dubbo – Warren – Bourke | 18, 19 & 20 July |
| NSW Gwydir Valley, NSW/Qld Macintyre Valley, Qld Lower Balonne Valley | Moree – Goondiwindi – St George – Dirranbandi | 31 July, 1, 2 & 3 August |

In total, 330 people attended the forums. The forum in Deniliquin had the most attendees (around 115 people).

In each town we also offered to meet separately with groups to facilitate one‑on‑one discussions. 54 groups took up this invitation, including First Nations, water authorities, private irrigation corporations, local governments, regional development groups, environmental groups, catchment management entities, and irrigation and dryland farming organisations.

We sought to meet with First Nations people on their country. We met with Elders, representatives and members of 11 First Nations of the Murray–Darling Basin (table B.2).

Table B.2 – First Nations we met with

| Who | When |
| --- | --- |
| Yorta Yorta Nation Aboriginal Corporation | 7 June |
| Yarkuwa Aboriginal Corporation | 8 June |
| Wamba Wamba First Peoples | 27 June |
| First People of the Millewa Mallee Aboriginal Corporation | 27 June |
| Barkindji Maraura Elders Environment Team Limited | 27 June |
| Latji Latji Mumthelang First Peoples | 28 June |
| Barkandji Native Title Group | 18 July |
| Trangie Area Aboriginal Land Council | 18 July |
| Menindee Local Aboriginal Land Council | 19 July |
| South‑West Indigenous Corporation | 2 August |
| Mandandanji First Peoples | 2 August |

The following sections set out what we heard at the Basin‑wide and regional level.

* 1. What we heard Basin‑wide

The Commission heard diverse views on water management topics. Some of the topics raised were within, and others beyond, the scope of this inquiry. From those within scope, there were a number of themes.

Generally, we observed greater interest and engagement in Basin Plan issues across the southern Basin towns we visited than those in the northern Basin. This was reflected in the attendance numbers in respective locations. Notwithstanding differences in town size, an average of 29 people attended the southern Basin forums, compared to an average of 5 in the northern Basin. The factors influencing a difference of this scale are hard to pinpoint, although at a general level, consultation fatigue and seasonal factors like harvesting time may be explanations. Less northern Basin interest in the Plan could also be because of a smaller scale of possible buybacks compared to the southern Basin.

We observed greater community acceptance (than in 2018) that the Basin needed a plan; such that the focus of interest had, for most part, shifted to questioning whether there were better ways to deliver the Plan. That said, when we spoke with First Nations people, some supported the importance of the Plan, others commented that ‘First Nations had never agreed to the Basin Plan’ and others said that it ‘does not take into account the views of First Nations’.

Interest in improving the Plan was often accompanied by concern and frustration that the broader benefits of environmental watering were not evident, along with a much stronger sense of wanting to see and understand the benefits delivered by the Basin Plan. People told us that going forward the Plan needed to have a greater focus on outcomes because ‘we seem to have lost sight of why we are doing this’.

That said, there were different views on specific elements of the Basin Plan across the Basin. For example, in some areas of the Basin the strong message was ‘no return to buybacks’; while in others it was ’restart buybacks immediately’. And on the 450GL recovery element, some communities said it was ‘pointless and detrimental’; while others said it was essential for restoring the health of the Basin.

People were critical of the lack of effort by state and Australian government agencies to engage with Basin communities. They spoke of engagement fatigue (box 9.10) but also frustration about ongoing uncertainty, a perceived lack of engagement in regions and little uptake of local solutions.

This was expressed in a number of ways. We often heard that Basin governments had ignored the Commission’s 2018 inquiry recommendations; and many questioned the point of putting in time and effort again. A variation of this was that Basin governments should ’stop talking to us from the capital cities about implementing the Basin Plan, come out and talk with us, because we want to engage you with our ideas’.

That said, many commented favourably about the Commonwealth Environmental Water Holder (CEWH) and its Local Engagement Officers and the way they work with Basin communities. Some communities said they had seen benefits in their region from the environmental watering activities undertaken by the CEWH in partnership with the state environmental watering, catchment management, water delivery, and irrigation infrastructure entities across New South Wales, Victoria and South Australia. They saw this as evidence of what is possible when governments and communities work in partnership.

Apart from environmental watering, First Nations people that we spoke with were less positive about the Basin Plan. Some described its impacts on them as ‘harmful’. Some also referred to the *Aboriginal Water Entitlements Program* (AWEP) – the $40 million commitment made in 2018 – which is yet to buy any water entitlements for Basin First Nations people.

First Nations people reiterated their aspirations for self‑determined decision making about water rights and river country management. One First Nations group, for example, said:

Government comes to us with great ideas but offer us no decision making, they need to let Indigenous people have a say. DCCEEW and others should come to us for ideas, not come and push their ideas on us. (Wamba Wamba First Peoples, pers. comm., 27 June 2023)

We heard frustration with governments’ approaches to engagement, including that submissions and views on water resource plans had not being considered. However, examples were given of partnerships and initiatives that are working well, including river rangers and partnerships to manage environmental water entitlements for cultural and ecological purposes.

Needing more time to deliver the Basin Plan was a re‑occurring theme across Basin communities. Some spoke about the need for more time to finish the Sustainable Diversion Limits (SDL) adjustment mechanism projects, and separately, to work through the concerns and issues held by communities who feel threatened by the potential impacts of lifting constraints. And some acknowledged that more time needed to be accompanied by clearer accountability for project delivery.

Often underlying the support for ‘more time’ was a fear of further buybacks if the SDL adjustment mechanism projects were not delivered; and concern that governments had not learned lessons about the impacts of previous buybacks on industries, communities and regional prosperity. Many expressed fears about the future of some smaller towns.

Many participants told us no more time should be allowed for other elements of Basin Plan implementation. This was expressed most clearly in the widespread view, in New South Wales and elsewhere, that the remaining NSW Water Resource Plans needed to be put in place as soon as possible.

Climate change, and the implications for water resource management, were front of mind for many and it was argued that these need to be at the centre of any discussion about the future of the Basin Plan.

Across all of the themes, we observed, in one way or another, an acceptance that fully implementing the Basin Plan and realising its benefits would not happen unless there was much stronger collaboration and a renewed partnership between all Basin governments. We regularly heard that all Basin governments need to take responsibility for their role in the Plan’s implementation, having repeatedly committed to implementing the Plan ‘on time and in full’.

* 1. Regional insights

### Northern Victoria and the NSW Murray Valley

In this region, we held public forums in Shepparton, Echuca and Deniliquin. There was a lot of interest from these communities – we had 170 people attend the three forums. And we met with a further 13 organisations.

These communities, and their surrounding areas, suffered a lot in the flood events that went through the southern Basin in 2023. With that as context, there was a consistent theme of community apprehension about the prospect of the Australian Government recommencing water buybacks.

The collective memory of earlier buyback programs still runs deep in these areas. Some said that their communities are still recovering from these earlier buybacks. Any return to buybacks was seen as a probable tipping point for their long term survival. Concerns were raised about towns with declining populations, falling school enrolments, declining community services and sports teams that could not be filled. These concerns were sometimes accompanied by a view that structural adjustment cannot work for small communities because ‘there is nothing to adjust to’. Though in contrast, others pointed to adjustment opportunities through attracting new investment to this region, particularly as part of renewable energy transition initiatives. But as we heard from one person, ‘while there is desire to pursue such opportunities, the pathway is not clear’.

From an irrigation farming perspective, the fears are again around poorly targeted buybacks creating a ‘swiss cheese’ effect in irrigation networks, resulting in stranded assets and higher fixed costs for remaining irrigators.

There was general frustration around the performance of all Basin governments, including around poor co‑ordination of consultation efforts, communities not being listened to, little or no effort to implement the Commission’s 2018 recommendations, and the continuing politicisation of the Plan. These elements and other perceived deficiencies (such as modelling accuracy) underscored an on‑going lack of community trust towards politicians and government water agencies. One participant at the Shepparton public forum, for example, spoke about the frustration of being ‘dragged back for consultation’.

That said, many wanted to see and understand better the benefits of environmental water. There were concerns about the lack of data and measurement of both environmental water use and its outcomes. People said they wanted to see environmental benefits achieved in their region from the water they had contributed up to now. There was disappointment with the continuing focus of the Australian Government on securing end of system environmental outcomes, ignoring the environmental needs of the landscapes that CEWH water passed through on its way to South Australia.

Some said that as much as they were farmers, they were also committed environmentalists. In their words, land in a healthy environmental condition underpins productive farming. They felt that governments, by not appreciating this connection, were foregoing an important opportunity to fashion environmental rehabilitation on private land to complement their efforts on public land.

We also heard that First Nations people in this region had no real voice in Basin water policy design and consultation on water management processes. And because they were not being included in efforts to stop damaging impacts to Country, their effort and energy was going into repeatedly producing messages and reports to show the harm happening to Country.

### NSW Murrumbidgee Valley

42 people in total attended the forums held in Griffith, Hay and Leeton. We also met with a further eight organisations.

The themes were similar to what we heard in Shepparton, Echuca, and Deniliquin:

* The southern Basin is bearing the brunt of Basin Plan implementation through water recovery – the northern Basin is getting off lightly.
* The needs of South Australia are being prioritised ahead of others.
* People would like to see evidence of environmental benefits from water recovery to date before recovering any more water. One participant at the Griffith meeting said ‘none of us know anything about the environmental outcomes of these projects. It’s all about just buying water back’. At Hay, it was expressed slightly differently: ‘Do we know how the water that has been bought back is being used and what’s been achieved with that water? Do people know how much the CEWH is using every year? If you can’t determine where you are now, with 15‑20 years of environmental water, how can you go and buy more?’.
* Basin governments are not listening to the voices of the regional people affected by the Basin Plan. One person at Griffith, for example, said, ‘Why am I coming here again, to say the same things we’ve been saying for so long but falling on deaf ears?’

The lack of transparency around water information, water management and water trading was a theme we heard not only in this valley but elsewhere as well. People were concerned about speculators distorting the water market. One take on this was ’we don’t know where water is going, who’s got it – it’s about making the whole thing as murky as you can’. A participant at Leeton commented that the ‘current system destroys productivity by encouraging people to bank water and then sell to desperate farmers’. Lack of access to real time water information was highlighted. We heard from one participant at Leeton that ‘there’s good historical information, which gives you a good idea of what’s gone wrong, but a lot of the information comes 12‑18 months later. Real‑time stuff is missing’.

Many people in these communities attributed a range of regional water and land management concerns to the Basin Plan which when examined more closely are in fact, related to state government functions outside the remit of the Plan. At the Griffith forum, for example, a number of speakers spoke about their frustration with matters relating to NSW water management decisions. One person asked that ‘we be given the water we’re entitled to, what’s on the piece of paper. We are not getting our allocations anymore. There was a flood and we only got our full allocation in January’. Another said ‘SA know they’re starting on 100%. Victoria already know what they’re likely to get. NSW do not provide that certainty each year for general security entitlements’.

When we asked what should be considered by Basin governments to progress the Plan’s implementation, common responses were around pausing the plan to take stock of what had been achieved to date – having a rethink. Many commented that the Basin Plan cannot be delivered in full under the current approach to implementation.

### Victorian Sunraysia and the South Australian Riverland

A total of 60 people attended the public forums in Mildura and Renmark. We also held 13 additional meetings with First Nations groups, local government, irrigator groups and water delivery managers.

First Nations people around Mildura were deeply concerned about the health of Country. Their ask of Basin governments was to take action to get water back on Country consistent with commitments made by the governments, in particular, the Australian Government’s AWEP Program.

With the geographic proximity of Mildura and Renmark, the issues raised were broadly similar though some local differences were observed. We were told that, by and large, the economic prosperity of Mildura and Renmark was underpinned by irrigated agriculture, though Mildura’s economic base is more diversified. That said, there were also views unique to each community.

Concern over the resumption of local water buybacks was heard in both communities, though the view in Renmark was less strident than Mildura. This was based in part on a belief that Mildura’s small horticultural irrigators would leave their farms for good this time, and the consequential impacts on both communities would be severe. In Mildura, this was accompanied by a concern about the impacts on the nation’s food production capability and the future cost of food for all Australians. In Renmark, the accompanying concern about buybacks focused on the town having already contributed more than its fair share in earlier buyback rounds, and that any further recovery from the Renmark district could be a tipping point for the future of irrigation farming.

Related to the shared concern about resumption of buybacks, we also heard concerns about the continuing corporatisation of agriculture and water holdings. Mention was made of the increasing foreign corporate ownership of Australia’s consumptive water resources and the negative side effects of this in terms of connecting with, and supporting the communities they operate within. One participant spoke about big corporates leaving as profit incentive disappears, leaving communities stranded with no economic activity.

Participants also mentioned what they considered to be poor performance by governments (federal, state and local) in co‑ordinating between themselves. These comments focused on the disconnect between agricultural land use planning and water management. We heard examples of poor practice in each region attributed to this disconnect. These focused mostly on highlighting the continuing influx of corporate investment to expand permanent plantings with little regard for the emerging water security risks to supply in the Sunraysia and Riverland districts.

On concerns unique to each town, we observed in Mildura a perspective that the Basin Plan was too top‑down, prescriptive and lacked nuance. One comment, for example, was that:

… the Basin Plan is a linear prescription; the problems it seeks to solve are too complex for it. It’s fixated on water when what we face is really an economic issue. The plan only measures water metrics, when really it should be measuring economic metrics and taking a bigger picture view of the problem. (Mildura Rural City Council, pers. comm., 28 June 2023)

There was also a strong view that communication and coordination has been poor. The Mildura Rural City Council expressed this sentiment as:

The good news stories don’t get spread, such as the saved wetlands and species. There is material for telling these stories but it’s not adequately disseminated. We hear what they’re doing, but never why we are doing this and these are going to be the benefits. (Mildura Rural City Council, pers. comm., 28 June 2023)

We heard clear disappointment with both the Australian and NSW governments. This related to a range of matters: unfinished water resource plans, slow rollout of metering, minimal contribution to the water recovery effort so far, and unfettered growth in high water demand agricultural development.

We also heard dissatisfaction with aspects of the CEWH’s performance, namely that they are not using their water for the benefit of Sunraysia’s riverine floodplains via overbank flow events; preferring instead to run their water within channel to the Lower Lakes, Murray Mouth and the Coorong. There was also dissatisfaction with CEWH trading policies, which meant the CEWH did not sell environmental water to farmers even in times of severe drought.

In Renmark, we were told the opportunities for improving water use efficiency in their irrigation systems had been exhausted through efforts to date. Therefore, it would be unfair for future buybacks to target the Riverland. To do so would unfairly punish South Australia for the shortcomings of NSW and Victorian efforts to improve water use efficiency in their own irrigation regions.

### South Australia’s Lower Lakes

We held a public forum in Goolwa attended by nine people, along with a meeting with the River Lakes and Coorong Action Group (RLCAG).

The narrative in South Australia’s Lower Lakes was more positive (than in upstream southern Basin communities) about the Basin Plan, its achievements to date and its prospects for further beneficial environmental health outcomes across the Lower Murray, Lower Lakes and Coorong regions.

There was a strong theme around the importance of building on the opportunity given by the recent sequence of flood events. One person commented that:

… the flood has given a once in a lifetime opportunity to start again, the river is cleaned out, completely flushed out. All the relevant players need to work together, get advice that doesn’t allow the river to fall into the parlous state it was in. Let’s re‑examine everything, tick the things we have right, and redo the things that we need to do better. We have a chance because we have a clean river. (Michael Scott, Alexandrina Council, pers. comm., 7 July 2023)

This narrative talked about ‘the river being flushed out by the floods and if everyone could work together, we could prevent the river falling back into the parlous state that it was in’.

The sense was that time should not be wasted getting the Plan fully operational.

The importance of not forgetting about water quality was highlighted. One participant commented on ’needing to ensure that the benefits of environmental water were not diminished by degraded water quality’.

While acknowledging the benefits observable in the lower parts of the Murray, it was commented that it is equally important that the Basin Plan delivers environmental benefits for all of the Basin’s river systems. And that this would only happen where governments and communities worked together in pursuit of a common easily understood goal.

One suggestion was to build greater cross border connection and understanding among basin communities – ’bringing different communities together and sharing differing views’.

There was some support for resuming buybacks. One person observed that:

… there is opposition to buy‑backs, this needs to shift because it’s the most efficient. The Federal Minister just has to do it, as long as you still invest in the communities to allow for transition. (RCLAG, pers. comm., 7 July 2023)

Also from a basin governance perspective, concern was expressed about recent changes to the Basin Community Committee which limit the connection of its members to the communities that they are selected to represent and lessen the transparency around how the Committee operates.

### NSW Menindee Lakes and the Lower Darling

There were 10 people at the Menindee public forum. We also had five additional meetings with local farming groups and First Nations organisations.

The people we met were strongly engaged with water management issues in their part of the Basin. We were reminded of their recent experiences with drought, flooding and fish kills. As a consequence, what they saw as poor implementation of the Basin Plan to date was front of mind and, as such, they welcomed the opportunity to provide their views on Basin Plan and Darling Baaka River water management issues.

We heard that without Water Resource Plans in place, there is no Basin Plan. Coupled to this was a view that NSW Water Sharing Plans are inadequate as planning instruments because their focus at valley level ignores system level objectives, such as maintaining river connectivity. There is a view that what has happened to the Darling Baaka over recent decades illustrates the consequences of this disconnect on river health, especially in dry conditions. Mention was also made of the looming consequences of earlier government decisions to not include climate change considerations into Water Resource Plans and Water Sharing Plans.

As in other communities, there was a conflation made between the Basin Plan and NSW water management processes that reflected a general frustration with agency performance in both spheres. This was very clear to us in the comments of some people about the performance of Australian and NSW government water agencies during the recent flood event that impacted the town. A related comment was ‘rules change, there was no talking between agencies, ego in outdoing each other and communities suffer’.

This sceptical view of the performance of governments and their water agencies was also heard in relation to the rollout of NSW floodplain harvesting licences, the management and operation of the regulated River Murray system as it impacted the Menindee Lakes storages, and the processes undertaken to develop and consult on SDL adjustment mechanism project proposals.

Driven by their experiences with fish kills in recent years, the Menindee community has real concerns about the on‑going decline in Darling Baaka River water quality, in particular the individual and shared impacts arising from this for their drinking, domestic and other basic water needs. Also strongly connected to this issue was the value that the community places on the contribution of tourism to the economic health of the town and its surrounds. In that context, they do not want to see this asset put at risk through continued poor management of in‑river water quality by the Australian and NSW governments. In part, this reflects their long-held view that the Lower Darling Baaka always comes off second best against the needs (and perceived economic value to the state of NSW) of the northern Darling Baaka and its tributaries.

And similar to other towns we visited, we heard that community engagement on all water matters affecting the town continues to be inadequate and/or inappropriate and that transparency around decision making in Basin water management processes is lacking. In the words of one participant, ‘there are no federal agencies coordinating with locals (in Menindee), there is a lack of clarity of the changes in rules. They just work to satisfy the ministers and politicians’.

From the First Nations people that we met with, we heard about the importance of having water in the Darling Baaka for cultural, social and economic use. One person commented that ‘when there is no water in the river and the lakes, mental health suffers’.

Concern was also expressed about the continuing lack of knowledge about the true extent of water extraction from the Darling Baaka upstream of Menindee, and the need for a greater presence from the NSW Natural Resource Access Regulator in far western NSW to monitor water extraction.

### NSW Macquarie and Barwon‑Darling Valleys

We travelled through central and north western NSW visiting Dubbo, Warren and Bourke. We held a public forum in each town attracting 24 people across the three sessions. We also held eight additional meetings with local government, environment groups, irrigator groups, and First Nations organisations.

There was considerably less interest (than in other areas we visited) in matters related to Basin water recovery. That said, concerns were raised about what was to become of the over recovery of water in the Macquarie‑Castlereagh system. The view in Warren was that this over recovery should be handed back to the valley, not shared with others.

We heard that the last two water years had been a boon for this part of NSW in terms of replenishing water stocks. As such, many of the views we heard focused on local or regional level water issues – some contemporary, others dating back to the 2017–19 drought.

We heard criticisms about decisions to release water for environmental purposes during the drought, too much environmental water being released causing subsequent damage to downstream riverine landscapes through higher than normal streamflow velocities, and environmental water causing a spike in carp numbers. We also heard concern that the NSW Government had not taken sufficient account of the lessons of the recent drought. In particular, we heard that Water Sharing Plans in this region still do not include operating rules for critical human water needs.

And, as in other basin regions, there was disquiet about the growing corporatisation of agriculture, its impacts on land and water prices, and its role in accelerating the decline of small rural towns in north western NSW.

Water resource plans were topical. We heard about a lack of clarity around how they connected to one another and their ‘reviewability’. The lack of closure on the NSW water resource plans was also mentioned. One person suggested the Inspector General of Water Compliance be empowered to make NSW finish its water resource plans.

The good quality of engagement efforts by the Murray Darling Basin Authority, the CEWH and the NSW Government also attracted comment. One participant said:

I am on the Macquarie environmental watering advisory group. It seems the state and commonwealth are working effectively on that … Isn’t perfect but it seems to work reasonably well. (Johnson, pers. comm., 7 June 2023)

On First Nations matters, we heard a consistent view across the region that delivery of the Australian Government’s AWEP Program needs to ‘get going’ and, in NSW, needed to be underpinned by a partnership between the State and Local Aboriginal Land Councils. We also heard that any water entitlements sourced under this program should not be held in a trust – ‘they need to be held by the 40 nations’. And one person said consideration should be given to ‘allocating half of all environmental water to cultural water’.

In the three towns, we heard about issues particular to each community.

In Dubbo, we heard about the adverse impacts of Burrendong Dam on First Nations cultural activity along the Macquarie River. There were concerns about the governance and operation of the Macquarie Cudgegong Environmental Water Advisory Group. We also heard support for complementary measures as an alternative to further water recovery. There was a desire for more timely conduct of annual SDL Accounting and the subsequent reporting of annual water take. Mention was also made about the observed poor performance by water agencies during water resource plan accreditation processes in undertaking consultation with First Nations.

In Warren, we heard that water recovered had benefited the Warren community through the improvement in the condition of the Macquarie Marshes; though this had to be considered in light of evidence of more prolonged drying periods. Concern was however, raised about the rollout of floodplain harvesting licences while apparent impacts of climate change were being observed.

In Bourke, the mood was pessimistic. There were three messages we heard consistently.

* Security of drinking water supply and its quality for the people of Bourke remains very uncertain.
* Water recovery over the past two decades has badly affected the town and any further recovery may be a tipping point for the viability of the town. This picture of decline was best summed up in one comment we heard:

… impact to our community was significant. We went from 4000 to 2600 people. We lost a school with 95 children. We lost the Chesterfield farm machinery outlet, the John Deere, Toyota and Suzuki dealerships, shops closed, and the NRMA has gone. (Bourke Shire Council, pers. comm., 20 July 2023)

* The town’s First Nations people have been devastated by loss of their cultural link to the Darling Baaka river through drought and upstream over extraction.

### NSW Gwydir Valley, NSW/Qld Macintyre Valley, Qld Lower Balonne Valley

At the end of July‑early August, we travelled from northern NSW into south west Queensland visiting the towns of Moree, Goondiwindi, St George and Dirranbandi. A return to drier conditions through these areas was noticeable. We held a public forum in each town attended in total by 15 people. We also held seven additional meetings with local government, irrigator groups and First Nations organisations.

As was the case with our visit to central and north western NSW, we heard a mix of views; some relating to Basin Plan implementation and others to local and regional water management issues.

While there was an acceptance of the Basin Plan and environmental watering undertaken by the CEWH, communities in this region remained concerned about the Plan’s flexibility and adaptability going forward.

There was a general tone of frustration about a perceived lack of accountability and transparency around environmental water decision making. This frustration related to feelings of not being consulted enough by decision makers, and a lack of recognition of the impacts of environmental water delivery on their land. Other participants commented about unrealistic goals being set through long‑term environmental watering plans. Others felt that ‘third‑party impacts caused by environmental water should be compensable’.

Concerns were raised about a range of water recovery related matters. There were criticisms of the Australian Government’s recent water tender process being ‘exclusionary, poorly communicated and lacking transparent engagement with impacted communities’. Others criticised the Australian Government’s renewed focus on buybacks at the expense of infrastructure‑based recovery. This view was accompanied by reference to the negative impacts of buybacks on ‘towns and communities, leading to job shortages and service reductions’.

One participant was sceptical about whether there was any scientific justification for the Australian Government attempting to recover a further 14GL of water licence in their catchment. They suggested consideration be given to requiring ‘scientific justification for additional water purchases, along with consideration of technological solutions’.

Other participants were keen to highlight the benefits seen in their region, including bird breeding events after environmental water releases. There was also support for environmental water processes to shift the focus from ‘volumes to outcomes’.

Across those we spoke with, there was also on‑going frustration across this region with the quality of consultation efforts by the Australian, NSW and Queensland governments. This was around a perceived lack of effort by governments in actioning the Commission’s 2018 recommendations on implementing the Basin Plan, water buybacks, environmental watering, over‑watering, water resource plans, disconnects within and across governments around water management and a general lack of collaboration and goodwill from government agencies.

We met with a number of First Nations groups across the region. There was a strong message that First Nations in this region want to collaborate with governments, fusing their traditional water knowledge into the current approaches to water management.

First Nations people said they wanted to be brought into the water loop, recognising each mob’s connection to their Country. Participants said they preferred a participatory approach involving all mobs rather than a representative body. Water licences issued to each mob were also considered preferable to a collective cultural water licence.

At a local level, some participants said that limited access to river country caused by fencing was impeding efforts to heal River and Country and was having a detrimental impact on peoples’ health and wellbeing. This was summed up in a comment about ‘river's declining, health impacts, fish scarcity, and a wish to restore the river as a community resource’.

* 1. Our concluding reflections

Drawing together the threads of our many conversations with people across the Basin, there are some clear messages, including:

* a strong desire by Basin communities (albeit expressed in differing ways and tones) for Basin governments to work collaboratively to finalise delivery of the Basin Plan
* a strong expectation that Basin governments will put in place better ways of working with local communities
* a growing interest in Basin Plan success being communicated through the lens of ‘environmental outcomes achieved’ rather than volumes of ‘annual environmental water used’
* a consistent call from First Nations people to be listened to, and involved in getting water onto their Country.

We thought carefully about each of these issues, reviewed the relevant evidence and sought to address them in our recommendations.

Abbreviations

|  |  |
| --- | --- |
| **ABARES** | Australian Bureau of Agricultural and Resource Economics and Sciences |
| **ACCC** | Australian Competition and Consumer Commission |
| **ACT** | Australian Capital Territory |
| **ADIC** | Australian Dairy Industry Council |
| **AEWP** | Annual Environmental Watering Priorities |
| **ANAO** | Australian National Audit Office |
| **ANZ Guidelines** | Australian and New Zealand Guidelines for Fresh and Marine Water Quality |
| **ATSE** | Australian Academy of Technological Sciences and Engineering |
| **BCC** | Basin Community Committee |
| **BDL** | Baseline Diversion Limit |
| **BOC** | Basin Officials Committee |
| **BOM** | Bureau of Meteorology |
| **BWEWS** | Basin-Wide Environmental Watering Strategy |
| **CAWI** | Committee for Aboriginal and Torres Strait Islander Water Interests |
| **CEWH** | Commonwealth Environmental Water Holder |
| **CICL** | Coleambally Irrigation Co-operative Limited |
| **CMS** | Constraints Management Strategy |
| **CMA** | Catchment Management Authority |
| **COAG** | Council of Australian Governments |
| **COFFIE** | Commonwealth On-Farm Further Irrigation Efficiency |
| **CSIRO** | Commonwealth Scientific and Industrial Research Organisation |
| **Cth** | Commonwealth |
| **DCCEEW** | Department of Climate Change, Energy, the Environment and Water |
| **DEG** | Dharriwaa Elders Group |
| **EDO** | Environmental Defenders Office |
| **EHG** | New South Wales Environment and Heritage Group |
| **ESLT** | Ecologically Sustainable Level of Take |
| **EWAG** | Environmental Watering Advisory Groups |
| **FLOW-MER** | Flow Monitoring, Evaluation and Research program |
| **GL** | Gigalitre |
| **GVEG** | Goulburn Valley Environment Group |
| **GVIA** | Gwydir Valley Irrigators Association |
| **IGA** | Intergovernmental Agreement |
| **IGWC** | Inspector-General of Water Compliance |
| **IRN** | Inland Rivers Network |
| **LALC** | Local Aboriginal Land Council |
| **LEO** | Local Engagement Officer (Commonwealth Environmental Water Holder) |
| **LTAAY** | Long-Term Average Annual Yield |
| **LTWP** | Long-Term Watering Plan |
| **LVA** | Latrobe Valley Authority |
| **LVW** | Lachlan Valley Water |
| **MDB Agreement** | Murray–Darling Basin Agreement |
| **MDBA** | Murray–Darling Basin Authority |
| **MDBEDP** | Murray–Darling Basin Economic Development Program |
| **MD WERP** | Murray–Darling Water and Environment Research Program |
| **ML** | Megalitres |
| **MLDRIN** | Murray Lower Darling Rivers Indigenous Nations |
| **NBAN** | Northern Basin Aboriginal Nations |
| **NBEWG** | Northern Basin Environmental Watering Group |
| **NBPG** | Northern Basin Project Group |
| **NCC NSW** | Nature Conservation Council of NSW |
| **NFF** | National Farmers' Federation |
| **NIC** | National Irrigators Council |
| **NRM** | Natural Resource Management |
| **NSW** | New South Wales |
| **NSW DPE** | New South Wales Department of Planning and Environment |
| **NSW DPI** | New South Wales Department of Primary Industries |
| **NSW DPIE** | New South Wales Department of Planning, Industry and Environment |
| **NSW NRC** | New South Wales Natural Resources Commission |
| **NSWIC** | New South Wales Irrigators' Council |
| **NWQMS** | National Water Quality Management Strategy |
| **OECD** | Organisation for Economic Co-operation and Development |
| **OFEP** | Off‑Farm Efficiency Program |
| **PC** | Productivity Commission |
| **PIIOP** | Private Irrigation Infrastructure Operators Program |
| **PPM** | Pre-requisite Policy Measures |
| **Qld DNRM** | Queensland Department of Natural Resources and Mines |
| **Qld DRDMW** | Queensland Department of Regional Development, Manufacturing and Water |
| **Qld DES** | Queensland Department of Environment and Science |
| **REO** | Regional Engagement Officer (Murray–Darling Basin Authority) |
| **RMWA** | River Murray Waters Agreement |
| **SA DEW** | South Australian Department for Environment and Water |
| **SCBEWC** | Southern Connected Basin Environmental Watering Committee |
| **SDL** | Sustainable Diversion Limit |
| **SDLAM** | Sustainable Diversion Limit Adjustment Mechanism |
| **SSCEC** | Senate Standing Committee on Environment and Communications |
| **SWWU** | New South Wales South-West Water Users Association |
| **TLM** | The Living Murray Program |
| **TLaWC** | Taungurung Land and Water Council |
| **Victorian DELWP** | Victorian Department of Environment, Land, Water and Planning |
| **VEWH** | Victorian Environmental Water Holder |
| **VMFRP** | Victorian Murray Floodplain Restoration Project |
| **WEP** | Water Efficiency Program |
| **WESA** | Water for the Environment Special Account |
| **WQM Plan** | Water Quality Management Plan |
| **WRP** | Water Resource Plan |

References

ABARES (Australian Bureau of Agricultural and Resource Economics and Sciences) 2020, *ABARES Insights: Analysis of water recovery in the Murray-Darling Basin*, Australian Bureau of Agricultural and Resource Economics and Sciences.

—— 2021, *Murray-Darling Basin water market catchment dataset 2021*.

ABC (Australian Broadcasting Corporation) 2021, ‘Murray Darling Basin Plan’s on-farm Water Efficiency Program axed by government’, 3 April.

ABC News 2023, ‘Victorian government puts hold on Murray-Darling Basin Plan projects’, 20 April.

ACCC (Australian Competition and Consumer Commission) 2021, *Murray-Darling Basin Water Markets Inquiry - Final Report*, Canberra.

—— 2023a, *Water charge rules*, https://www.accc.gov.au/by-industry/water/water-charge-rules (accessed 16 October 2023).

—— 2023b, *Water market rules*, https://www.accc.gov.au/by-industry/water/water-market-rules (accessed 16 October 2023).

ACT Government 2019, *ACT Water Strategy 2014–44 Striking the Balance Implementation Plan Two (2019-23)*.

—— 2023, *Australian Capital Territory - Matter 19 Annual report 2022-23*, Basin Plan Implementation Reports, November, Schedule 12 reports.

Aither 2023a, *Water Markets Report: 2022-23 Review and 2023-24 Outlook*.

—— 2023b, *Water Markets reports - 2022-23 Review and 2023-24 Outlook - presentation*.

ANAO (Australian National Audit Office) 2020, *Procurement of Strategic Water Entitlements*.

Andrews, D 2019, *Murray Floodplain Restoration Project Begins*, https://www.premier.vic.gov.au/murray-floodplain-restoration-project-begins/ (accessed 19 September 2023).

Assistant Minister for Social Services (Fifield) 2014, *National Water Commission (Abolition) Bill 2014 Second Reading Speech*, 25 September, Canberra, p. 7111.

Australian Government 2012a, *Basin Plan 2012*.

—— 2012b, *Basin Plan 2012 - Explanatory Statement*.

—— 2023, *Budget 2023-2024. Budget Measures Budget Paper No. 2*.

——, NSW Government and Victorian Government 2002, *Snowy Water Inquiry Outcomes Implementation Deed*.

—— 2021, *Select Committee on the Multi-Jurisdictional Management and Execution of the Murray-Darling Basin Plan*, Canberra.

Australian Governments and Coalition of Aboriginal and Torres Strait Islander Peak Organisations 2020, *National Agreement on Closing the Gap*.

BCC (Basin Community Committee) 2023, *Communique*, 13 July.

Birmingham, S (Senate Leader of the Opposition) 2014, *States Agree to Implement Murray-Darling Basin Water Reform*, Media Release, 27 February.

BOC (Basin Officials Committee) 2023a, *Basin Officials Committee update to the Murray-Darling Basin Ministerial Council: Progress Update on implementation of Joint Basin government response to the Productivity Commission inquiry report: Murray–Darling Basin Plan: Five-year assessment*, July.

—— 2023b, *Objectives and outcomes for river operations in the River Murray System*.

BOM (Bureau of Meteorology) 2020, *Trends and historical conditions in the Murray-Darling Basin*, A report for the Murray-Darling Basin Authority by the Bureau of Meteorology.

—— 2023, *Groundwater data now available in the Murray-Darlin Basin Water Information Portal*, https://media.bom.gov.au/releases/1168/groundwater-data-now-available-in-the-murray-darling-basin-water-information-portal/ (accessed 16 October 2023).

Buckley, M 2014, *Review of the Cost Shares for Joint Activities*, Final Report, MDBA, Canberra.

CEWH (Commonwealth Environmental Water Holder) 2021, *Partnership Agreement between CEWH and the SA Department for Environment and Water 2021-25*.

—— 2020, *Collaboration Deed between CEWH and Australian Landscape Trust 2020-25*.

—— 2023, *Assessing Vulnerability for use in Determining Basin-scale Environmental Watering Priorities*, Canberra.

CFFR (Council on Federal Financial Relations) 2020, *The Federation Funding Agreements Framework*.

Chiew, FHS, Zheng, H, Potter, NJ, Charles, SP, Thatcher, M, Ji, F, Syktus, J, Robertson, DE and Post, DA 2022, ‘Different hydroclimate modelling approaches can lead to a large range of streamflow projections under climate change: Implications for water resources management’, *Water*, vol. 14, no. 17, p. 2730.

Claydon, G 2019, *Review of the Murray-Darling Basin Joint Governance Arrangements*, Final Report.

COAG (Council of Australian Governments) 2004, *Intergovernmental Agreement on a National Water Initiative*, Canberra.

—— 2019, *Intergovernmental Agreement on Implementing Water Reform in the Murray Darling Basin*, Canberra.

CSIRO (Commonwealth Scientific and Industrial Research Organisation) 2020, *Science Solutions for the Murray-Darling Basin*, Canberra.

Cutting, M, Fenwick, B and Thorne, R 2022, *Commonwealth On-Farm Further Irrigation Efficiency (COFFIE) Program - Monitoring and Evaluation Report*, Murraylands and Riverland Landscape Board, Murray Bridge.

DAFF (Australian Government Department of Agriculture, Fisheries and Forestry) 2020, *National Partnership Agreement on Implementing Water Reform in the Murray-Darling Basin - Final Review*.

DAWE (Australian Government Department of Agriculture, Water and the Environment) 2020, *Guidelines for claiming payment under the Commonwealth Water Act*, Canberra.

DCCEEW (Australian Government Department of Climate Change, Energy, the Environment and Water) 2021a, *Australia: State of the Environment report*, Canberra.

—— 2021b, *Efficiency Measures - Agreed Criteria*.

—— 2022a, *Murray–Darling Basin Economic Development Program*, https://www.dcceew.gov.au/water/policy/programs/  
continuing/edpgrants#funded-round-3-projects (accessed 16 February 2023).

—— 2022b, *Northern Basin Environmental Watering Group*, https://www.dcceew.gov.au/water/cewo/nbew-group (accessed 16 October 2023).

—— 2022c, *Private Irrigation Infrastructure Operators Program in New South Wales*, https://www.dcceew.gov.au/water/policy/programs/completed/piiop-nsw (accessed 18 September 2023).

—— 2022d, *Supporting waterbirds at Narran Lakes (Dharriwaa)*, Canberra.

—— 2022e, *Water for Australia Plan - Budget October 2022-23*.

—— 2023a, *A National Climate Risk Assessment for Australia*.

—— 2023b, *Agreement of Murray-Darling Basin Ministers to deliver the Basin Plan in full*, 22 August.

—— 2023c, *Managing water for the environment*, https://www.dcceew.gov.au/water/cewo/about-commonwealth-environmental-water (accessed 19 September 2023).

—— 2023d, *Off-farm Efficiency Program*, https://www.dcceew.gov.au/water/policy/programs/open/off-farm-efficiency-program (accessed 23 August 2023).

—— 2023e, *Progress on Murray-Darling Basin water recovery*.

—— 2023f, *Strategic water purchasing – Bridging the Gap 2023*, https://www.dcceew.gov.au/water/policy/mdb/commonwealth-water-mdb/strategic-water-purchasing (accessed 23 August 2023).

—— 2023g, *Strategic Water Purchasing Framework - Bridging the Gap to the Sustainable Diversion Limits 49.2 gigalitres total from 7 catchments*.

—— 2023h, *Surface water purchasing – limited tender*, https://www.dcceew.gov.au/water/policy/mdb/commonwealth-water-mdb/limited-tender (accessed 24 August 2023).

—— 2023i, *Surface water recovery required under the Basin Plan including the Sustainable Diversion Limit Adjustment Mechanism*, 30 June.

—— 2023j, *Water Management Plan 2023-24*, https://www.dcceew.gov.au/water/cewo/publications/water-management-plan-2023-24 (accessed 13 November 2023).

—— 2023k, *What We Heard – consultation draft Aboriginal Water Entitlements Program*.

DPI (NSW) (New South Wales Department of Primary Industries) 2016, *Yarrawonga to Wakool Junction Reach Constraints Measure Business Case*, Business Case.

EIU (The Economist Intelligence Unit) 2019, *Resilience to climate change?*, https://www.eiu.com/public/topical\_report.aspx?campaignid=climatechange2019 (accessed 12 October 2023).

Frontier Economics 2020, *Water market architecture: Issues & options*.

GMW (Goulburn Murray Water) 2022, *Projects continue flow on*, https://www.g-mwater.com.au/news-updates/media-releases/country-news-columns/projects-continue-flow-on.html (accessed 16 October 2023).

Grafton, RQ and Wheeler, SA 2018, ‘Economics of water recovery in the Murray-Darling Basin, Australia’, *Annual Review of Resource Economics*, vol. 10, pp. 487–510.

Grafton, R, Fanaian, S, Sacco, G and Liberman, L 2021, ‘Bending towards water justice: pathways for truth, reconciliation, inclusion and transformative actions’, *International Journal of Water Resources Development*, vol. 38, no. 1, pp. 1–10.

Grant, T (Inspector-General of Water Compliance) 2023, *Cross-portfolio Murray-Darling Basin Plan Matters - Senate Estimates*, Environment and Communications Legislation Committee, 26 May, Australian Senate, Proof Committee Hansard.

Guest, C 2016, *Sharing the Water One hundred years of River Murray politics*, Murray-Darling Basin Authority.

Harris, P 2023, *Interim report - Review of the Inspector General for Water Compliance*, October.

Hartwig, LD, Jackson, S, Markham, F and Osborne, N 2021, ‘Water colonialism and Indigenous water justice in south-eastern Australia’, *International Journal of Water Resources Development*, vol. 38, no. 1, pp. 30–63.

Hausfather, Z 2019, *CMIP6: The Next Generation of Climate Models Explained—Carbon Brief*, Carbon Brief.

Howard, J 2007, *A National Plan for Water Security: Speech to the National Press Club*, Canberra.

IGWC (Australian Government Inspector-General of Water Compliance) 2021, *Inspector-General of Water Compliance - Compliance Priorities and Workplan*, August.

—— 2022a, *Annual Work Plan 2022-23*.

—— 2022b, *Audit of Accounting for Interstate Trade in the Northern Basin*, October, Australian Government, Canberra.

—— 2022c, *Audit of Goulburn-Murray Water disclosure obligations under the Basin Plan*, July, Australian Government, Canberra.

—— 2022d, *‘Steady as it flows’ An assessment of River Murray operations and environmental water management*.

—— 2022e, *Sustainable Diversion Limit compliance statement for 2020-2021*, August.

—— 2023a, *2020-21 Metering Report Card*, January.

—— 2023b, *2021-22 Metering Report Card*, July.

—— 2023c, *Annual Work Plan 2023-24*.

—— 2023d, *Audit of the management of overland flow harvesting in the Lower Balonne*, June.

—— 2023e, *Draft Regulatory Policy*, July.

—— 2023f, *Investigation - Trade price reporting*, October.

—— 2023g, *Regulatory policy*, October.

—— 2023h, *Sustainable Diversion Limit compliance statement for 2021-2022*, September.

—— and MDBA (Inspector-General of Water Compliance and Murray-Darling Basin Authority) 2022, *Memorandum of understanding MDBA and Inspector-General Water Compliance*, March.

Indec 2021a, *Constraints Measures Status Update October 2021 For Second WESA Review*, October, prepared for Department of Agriculture, Water and the Environment, p. 40.

—— 2021b, *Status Assessment: Sustainable Diversion Limit Adjustment Mechanism Program*, 29 April, prepared for Department of Agriculture, Water and the Environment.

International Association for Public Participation 2019, *IAP2 Published Resources*, https://iap2.org.au/resources/iap2-published-resources/ (accessed 3 December 2020).

IRORG (Independent River Operations Review Group) 2021, *Review of performance against objectives and outcomes - 2020-21*.

Joint Basin Governments 2019, *Response to the Productivity Commission Inquiry Report: Murray-Darling Basin Plan: Five Year Assessment*, Canberra.

Joint Council on Closing the Gap 2023, *Eleventh Meeting of the Joint Council on Closing the Gap Communique*.

Marsden Jacob Associates nd, *Urban Water in the Murray-Darling Basin*.

Matthews, K 2017a, *Independent Investigation into NSW Water Management and Compliance: Advice on Implementation*, New South Wales.

—— 2017b, *Independent Investigation into NSW Water Management and Compliance: Interim Report*, New South Wales.

McConville, A 2022, *Address to the National and Rural Press Club*, 22 November, Canberra.

MDB Ministerial Council (Murray-Darling Basin Ministerial Council) 2018, *Murray-Darling Basin Compliance Compact*, An Agreement between Commonwealth, New South Wales, Victoria, Queensland, South Australia, Australian Capital Territory, Canberra.

MDBA (Australian Government Murray Darling Basin Authority) 2022a, *River Murray System summary of river operations*, July.

—— 2013a, *Constraints Management Strategy: 2013 to 2024*.

—— 2013b, *Handbook for Practitioners – Water resource plan requirements*, 20/13.

—— 2016a, *Northern Basin Review*.

—— 2016b, *Phase 2 Assessment Guidelines for Supply and Constraint Measure Business Cases*.

—— 2017a, *2017 Basin Plan Evaluation*.

—— 2017b, *Phase 1 Assessment Guidelines for Constraint and Supply Proposals*.

—— 2017c, *Pre-2009 Water Recovery*, https://www.mdba.gov.au/  
publications-and-data/publications/pre-2009-water-recovery-table-2017 (accessed 17 October 2023).

—— 2017d, *Sustainable Diversion Limit Adjustment Mechanism*, Draft Determination Report 2017, Canberra.

—— 2017e, *The Murray-Darling Basin Water Compliance Review*, Canberra.

—— 2018a, *Basin Environmental Watering Priorities 2018-19*, June.

—— 2018b, *Water Resource Plan Assessment Framework*.

—— 2019a, *Climate change and the Murray-Darling Basin Plan*, MDBA Discussion Paper.

—— 2019b, *Murray-Darling Basin Compliance Compact Assurance Report 2019*, December, Canberra.

—— 2019c, *Review of the Basin-wide environmental watering strategy*, April.

—— 2019d, *Transition Period Water Take Report 2017-18: Report on Cap compliance and transitional SDL accounting*, July.

—— 2019e, *Water resource plans - quarterly report*, September.

—— 2019f, *Water resource plans - quarterly report*, December.

—— 2020a, *ACT Basin Plan annual report 2019-20 and statement of assurance*, October.

—— 2020b, *Annual Progress Report 2020: Sustainable Diversion Limit Adjustment Mechanism*, 26/20.

—— 2020c, *Basin Plan Evaluation 2020*, https://www.mdba.gov.au/basin-plan-evaluation-2020 (accessed 17 February 2023).

—— 2020d, *Basin-wide Environmental Watering Strategy, second edition*, Canberra.

—— 2020e, *MDBA Annual Report 2019-20*, Canberra.

—— 2020f, *Prerequisite policy measure documents*, https://www.mdba.gov.au/publications-and-data/publications/prerequisite-policy-measure-documents (accessed 17 October 2023).

—— 2020g, *Review of water quality targets in the Basin Plan*.

—— 2020h, *The 2020 Basin Plan Evaluation*, Canberra.

—— 2020i, *The 2020 Basin Plan Evaluation: Hydrological Analysis Evidence Report*, December, p. 59.

—— 2020j, *The 2020 Basin Plan Evaluation: Plan implementation evidence report*, December, Canberra.

—— 2020k, *Transition Period Water Take Report 2018-19: Report on Cap compliance and transitional SDL accounting*, December.

—— 2020l, *Water resource plans - December 2020 quarterly report*.

—— 2020m, *Water resource plans - June 2020 quarterly report*.

—— 2020n, *Water resource plans - March 2020 quarterly report*.

—— 2020o, *Water resource plans - September 2020 quarterly report*.

—— 2020p, *Why the Murray–Darling Basin matters*, https://www.mdba.gov.au/why-murray-darling-basin-matters (accessed 27 February 2023).

—— 2021a, *Annual Progress Report 2020-21*.

—— 2021b, *Annual Water Take Report 2019-20: Report on Basin wide water availability, use and Cap compliance*, November, Canberra.

—— 2021c, *Guidelines for amendments to water resource plans - Part 1*, January, Canberra.

—— 2021d, *Guidelines for amendments to water resource plans - part 2*, January, Canberra.

—— 2021e, *Review of the Environmental Watering Plan*, Canberra.

—— 2021f, *Sustainable Diversion Limit Adjustment Mechanism: 2021 Assurance report*, Canberra.

—— 2021g, *Water metering in the Basin is improving, but has a long way to go*, https://www.mdba.gov.au/news-and-events/newsroom/water-metering-basin-improving-has-long-way-go (accessed 7 September 2023).

—— 2021h, *Water resource plans - August 2021 quarterly report*, September.

—— 2021i, *Water resource plans - May 2021 quarterly report*, June.

—— 2021j, *Water resource plans - November 2021 quarterly report*, December.

—— 2022b, *2020-21 Sustainable Diversion Limit Accounts: Registers of Take*, May, Canberra.

—— 2022c, *Annual Water Take Report 2020-2021: Report on Basin wide water availability, use and Cap compliance*, September, Canberra.

—— 2022d, *Attachment D: Provision of material relevant to s71 reporting where Water Resource Plans have been withdrawn before 30 June 2022: NSW - MDBA Bilateral Agreement Action 2 report*, 30 June.

—— 2022e, *Basin annual environmental watering priorities 2022-2023*, Canberra.

—— 2022f, *Basin Condition Monitoring Program: Program plan*, August, Canberra.

—— 2022g, *Bilateral agreements with Basin state and territory governments*, https://www.mdba.gov.au/publications-and-data/publications/bilateral-agreements-basin-state-and-territory-governments (accessed 26 July 2023).

—— 2022h, *December 2022 Report Card*, Canberra.

—— 2022i, *First Nations participation in water for the environment 2021-22*, December, Canberra.

—— 2022j, *Framework for the 2025 Basin Plan Evaluation*, Canberra.

—— 2022k, *Murray-Darling Basin Ministerial Council Communique*, 12 October.

—— 2022l, *Rivers, the veins of our Country: Twelve case studies of First Nations involvement in managing water for the environment in the Murray-Darling Basin 2020-2021*, April.

—— 2022m, *Sustainable Diversion Limit Accounting and Reporting Framework*, August, Canberra.

—— 2022n, *Sustainable Diversion Limit Adjustment Mechanism: 2022 Assurance Report*, MDBA Publication 25/22, Canberra.

—— 2022o, *Sustainable diversion limit adjustment mechanism program – progress reporting*, https://www.mdba.gov.au/  
publications-and-data/publications/sustainable-diversion-limit-adjustment-mechanism-program (accessed 26 July 2023).

—— 2022p, *Water resource plans - August 2022 quarterly report*, September.

—— 2022q, *Water resource plans - February 2022 quarterly report*, March.

—— 2022r, *Water resource plans - May 2022 quarterly report*, June.

—— 2022s, *Water resource plans - November 2022 quarterly report*, December.

—— 2023a, *2023 mid-year Basin Plan report card*, 25 June.

—— 2023b, *Annual assurance reports – sustainable diversion limit adjustment mechanism*, July.

—— 2023c, *Authority response to Minister’s request for advice: Advice on Basin Plan Implementation*, 25 July.

—— 2023d, *Current diversion limits for the Basin*, https://www.mdba.gov.au/water-use/water-limits/current-diversion-limits-basin (accessed 18 September 2023).

—— 2023e, *First Nations environmental water guidance*, https://www.mdba.gov.au/water-use/water-first-nations/first-nations-environmental-water-guidance (accessed 18 October 2022).

—— 2023f, *How water is managed*, https://www.mdba.gov.au/  
water-management/river-murray-operations/how-water-managed (accessed 7 September 2023).

—— 2023g, *Lessons in water management across the Pacific*, Media release, 14 June.

—— 2023h, *Northern Basin Environmental Watering Group*, https://www.mdba.gov.au/about-us/governance-and-committees/environmental-watering-committees/northern-basin-environmental (accessed 17 October 2023).

—— 2023i, *Northern Basin Toolkit*, https://www.mdba.gov.au/water-management/northern-basin/northern-basin-toolkit (accessed 9 October 2023).

—— 2023j, *Our climate workplan*, https://www.mdba.gov.au/  
climate-and-river-health/climate/our-climate-workplan (accessed 9 October 2023).

—— 2023k, *Projects in the Northern Basin Toolkit*, https://www.mdba.gov.au/water-management/northern-basin/projects-northern-basin-toolkit (accessed 20 July 2023).

—— 2023l, *Roadmap to the 2026 Basin Plan Review*.

—— 2023m, *Sustainable Diversion Limit Adjustment Mechanism: 2023 Assurance report*, July.

—— 2023n, *Sustainable Diversion Limit Adjustment Mechanism - Program Status Dashboard*, 19 May.

—— 2023o, *Sustainable diversion limit adjustment projects*, https://www.mdba.gov.au/water-management/basin-plan/sustainable-diversion-limit-adjustment-mechanism/sustainable-0 (accessed 23 August 2023).

—— 2023p, *Sustainable diversion limit reporting 2021-22*, https://www.mdba.gov.au/publications-and-data/publications/  
sustainable-diversion-limit-reporting-2021-22 (accessed 6 December 2023).

—— 2023q, *Types of water modelling*, https://www.mdba.gov.au/  
water-management/water-resource-modelling/types-water-modelling (accessed 11 September 2023).

—— 2023r, *The Basin*, https://www.mdba.gov.au/basin (accessed 10 August 2023).

MDWERP (Murray-Darling Water and Environment Research Program) 2022, *Message from the Chair*, MD-WERP Newsletter, April, Edition 2.

Minister for Lands and Water NSW 2022, *No secret pact for water buybacks*, Media Release, 16 November.

MJA (Marsden Jacob Associates) 2021, *Water for the Environment Special Account—2nd independent review: Advice to the independent WESA review panel*.

MLDRIN (Murray and Lower Darling Rivers Indigenous Nations) 2007, *Echuca Declaration*, Melbourne.

—— and NBAN (Murray Lower Darling Rivers Indigenous Nations and Norther Basin Aboriginal Nations) 2021, *Research into how much water is held by First Nations and Traditional Owner Organisations in the Murray-Darling Basin in 2020: A First Nations Summary*.

Moggridge, BJ and Thompson, RM 2021, ‘Cultural value of water and western water management: an Australian Indigenous perspective’, *Australasian Journal of Water Resources*, vol. 25, no. 1, pp. 4–14.

Moore, T 2016, *Community engagement A key strategy for improving outcomes for Australian families*, Australian Institute of Family Studies.

Mouque, D 2012, *What are counterfactual impact evaluations teaching us about enterprise and innovation support?*, European Commission.

NBPC (Northern Basin Project Committee) 2022, *Northern Basin Toolkit: Updated status of implementation - August 2022*, Canberra.

—— 2023, *Northern Basin Toolkit Measures - August 2023 progress update from the Northern Basin Project Committee*.

NNTC (National Native Title Council) 2023, *Closing the Gap – Inland Waters Target Framework*, https://nntc.com.au/our-agenda/closing-the-gap/ (accessed 24 July 2023).

NSW Chief Scientist & Engineer 2023, *Independent review into the 2023 fish deaths in the Darling-Baaka River at Menindee*, Findings and Recommendations.

NSW DOI (New South Wales Department of Industry) 2018, *NSW Floodplain Harvesting Policy*.

NSW DPE (New South Wales Department of Planning and Environment) 2019, *How water for the environment is managed in NSW*, http://www.environment.nsw.gov.au/topics/  
water/water-for-the-environment/about-water-for-the-environment/what-is-it/how-is-it-managed (accessed 4 September 2023).

—— 2022a, *Draft Western Regional Water Strategy Attachment D: North-West Flow Plan discussion paper*, June, https://water.dpie.nsw.gov.au/\_\_data/assets/pdf\_file/0004/514309/north-west-flow-plan.pdf (accessed 20 September 2023).

—— 2022b, *Finalising Water Resource Plans - What happens now - Water in New South Wales*, https://www.industry.nsw.gov.au/water/plans-programs/water-resource-plans/what-happens-now (accessed 26 July 2023).

—— 2022c, *Monitoring, evaluation and reporting update*, https://www.environment.nsw.gov.au/topics/water/water-for-the-environment/planning-and-reporting/water-for-environment-outcomes-2021-22 (accessed 27 September 2023).

—— 2022d, *NSW annual report on water resource use for the 2020/21 water year*, Submission to the MDBA Water Take Report, February.

—— 2022e, *Open data framework*, https://water.dpie.nsw.gov.au/  
science-data-and-modelling/data/open-data-framework (accessed 16 October 2023).

—— 2022f, *Regional Water Strategy - Western*, Executive Summary, December.

—— 2022g, *Regional Water Strategy: Gwydir*, November.

—— 2023a, *Extreme Events Policy: Policy framework for the management of NSW water resources during extreme events*.

—— 2023b, *NSW annual report on water resource use for the 2021/22 water year*, Submission to the MDBA Water Take Report, May.

—— 2023c, *NSW Government response: Office of the NSW Chief Scientist and Engineer independent review into the 2023 fish deaths in the Darling-Baaka River at Menindee*, November.

—— 2023d, *Regional Water Strategy: Namoi*, June.

—— 2023e, *Status - Stages of a Water Resource Plan*, https://water.dpie.nsw.gov.au/plans-and-programs/water-resource-plans/status (accessed 12 December 2023).

—— 2023f, *Updates and engagement - Water resource plans*, https://www.industry.nsw.gov.au/water/plans-programs/water-resource-plans/updates-and-engagement (accessed 12 December 2023).

NSW DPIE (New South Wales Department of Planning, Industry and Environment) 2020a, *New climate analysis informs NSW’s regional water strategies*, https://water.dpie.nsw.gov.au/\_\_data/assets/pdf\_file/0004/500728/nsw-climate-model-report.pdf (accessed 9 October 2023).

—— 2020b, *NSW 2020 Five-yearly Matter 12 Report*, October.

—— 2021, *NSW annual report on water resource use for the 2019/20 water year*, Submission to the MDBA Water Take Report, April.

—— 2016, *Murrumbidgee River Constraints Measure*, Concept Proposal Business Case.

NSW NRC (New South Wales Natural Resources Commission) 2019, *Review of the Water Sharing Plan for the Barwon Darling Unregulated and Alluvial Water Sources 2012*, Final Report, NSW Government, Sydney.

OECD (Organisation for Economic Co-operation and Development) 2015, *OECD Principles on Water Governance*, https://www.oecd.org/governance/oecd-principles-on-water-governance.htm (accessed 21 September 2020).

—— 2022, *OECD Guidelines for Citizen Participation Processes*, OECD Public Governance Reviews.

Owens, K 2022, ‘Governing climate-related systemic risks in the Murray-Darling Basin in Australia’, *Utrecht Law Review*, vol. 18, no. 2, pp. 12–29.

PC (Productivity Commission) 2003, *Water Rights Arrangements in Australia and Overseas: Annex B New South Wales*, Commission Research Paper, Melbourne.

—— 2010, *Market Mechanisms for Recovering Water in the Murray-Darling Basin*, Research Report, Canberra.

—— 2017, *Transitioning Regional Economies*, Study Report, Canberra.

—— 2018, *Murray-Darling Basin Plan: Five-year Assessment*, Report no. 90, Canberra.

—— 2021a, *Assessment of the National Water Initiative implementation progress (2017-2020)*, National Water Reform 2020, Report no. 96, Canberra.

—— 2021b, *Knowledge Capacity and Capability Building*, National Water Reform 2020 Inquiry Report, Supporting Paper K.

—— 2021c, *National Water Reform 2020*, Canberra.

—— 2023, *Review of the National Agreement on Closing the Gap, Draft report*, Canberra.

Pearson, D 2022, *Compliance and enforcement across the Murray-Darling Basin*, Prepared for the Inspector-General of Water Compliance, June.

Plibersek, T and Hanson-Young, S (Minister for the Environment and Water and Greens Spokesperson for the Environment and Water) 2023, *Joint media release: Strengthening the Restoring Our Rivers Bill*, Media release, 27 November.

—— 2023a, *Decade of Liberal & National Sabotage puts Murray-Darling Basin Plan behind*, Media release, 25 July.

—— 2023b, *Independent review into Murray-Darling water compliance*, Media release, 14 September.

—— 2023c, *Positive response to government’s voluntary water tender process*, Media release, 31 October.

Pocock, D 2023, *New hope for the Murrumbidgee in water agreement*.

Prosser, IP, Chiew, FHS and Stafford Smith, M 2021, ‘Adapting water management to climate change in the Murray–Darling Basin, Australia’, *Water*, vol. 13, no. 18, p. 2504.

QLD DNRM (Queensland Department of Natural Resources and Mines) 2020, *Reporting for Basin Plan Schedule 12 Matter 12: Progress towards the water quality targets in Basin Plan Chapter 9*, October.

QLD DRDMW (Queensland Department of Regional Development, Manufacturing and Water) 2021, *Progress and performance report, rural water futures*.

—— 2022, *Basin Plan Annual report matter 19 Part A and Part B - Queensland 2020-21*.

—— 2023a, *Department of Regional Development, Manufacturing and Water (DRDMW) - Management response to audit recommendations*, Inspector-General of Water Compliance Audit management of overland flow harvesting in the Lower Balonne.

—— 2023b, *First Nations Water Strategy*, https://www.rdmw.qld.gov.au/water/consultations-initiatives/first-nations-water-strategy (accessed 22 September 2023).

Queensland DES (Queensland Department of Environment and Science) 2023, *$700,000 investment to enhance Queensland water modelling*, https://www.des.qld.gov.au/our-department/news-media/mediareleases/$700,000-investment-to-enhance-queensland-water-modelling (accessed 21 September 2023).

Queensland Government 2022, *Queensland Matter 19 compliance with Water Resource Plan Part A and Part B - 2021-22*.

—— 2023a, *Path to Treaty Act 2023*.

—— 2023b, *Water planning framework*, https://www.business.qld.gov.au/\_designs/content/guide-printing2?parent=201175&SQ\_DESIGN\_NAME=print\_layout (accessed 22 September 2023).

Quinlivan, D 2022, *Water market reform: final roadmap report*, September.

Rural and Regional Affairs and Transport References Committee 2013, *The management of the Murray-Darling Basin*, https://www.aph.gov.au/Parliamentary\_Business/  
Committees/Senate/Rural\_and\_Regional\_Affairs\_and\_Transport/Completed inquiries/2012-13/mdb/report/index (accessed 11 September 2023).

SA DEW (South Australian Department for Environment and Water) 2020, *South Australian Matter 12 Report 2020*, October.

—— 2021, *Yarning circles foster sharing of traditional Ngarrindjeri water knowledge*, https://www.environment.sa.gov.au/news-hub/  
news/articles/2021/11/yarning-circles (accessed 31 August 2023).

—— 2023a, *2023-24 water for the environment annual plan for the South Australian River Murray*.

—— 2023b, *Healthy Coorong, Healthy Basin - Scientific Trials and Investigations*, https://www.environment.sa.gov.au/topics/  
coorong/healthy-coorong-healthy-basin/scientific-trials-investigations (accessed 25 September 2023).

SA Government (South Australian Government) 2019, *Murray-Darling Basin Royal Commission*, 29 January, Bret Walker SC Commissioner, South Australia.

—— 2022, *South Australia Matter 19 compliance with Water Resource Plan River Murray Part A - 2021-22*, Basin Plan Implementation Reports, 12 December, Schedule 12 reports.

—— 2023a, *Aboriginal Partnerships Program*, https://www.landscape.sa.gov.au/mr/projects/community-projects/aboriginal-partnerships (accessed 25 September 2023).

—— 2023b, *Landscape boards committed to reconciliation and First Nations partnerships*, https://www.landscape.sa.gov.au/  
statement-of-commitment (accessed 25 September 2023).

—— 2023c, *SA First Nations Voice*, https://www.agd.sa.gov.au/first-nations-voice (accessed 25 September 2023).

Sauchyn, D, Belanger, J, Muhammad, RA, Soumik, B and Stewart, S 2022, *Understanding and accommodating uncertainty in Climate Change Data: a Climatewest primer*, ClimateWest, Canada.

Secretariat of the Convention on Biological Diversity 2004, *Akwé: Kon Voluntary Guidelines for the Conduct of Cultural, Environmental and Social Impact Assessment regarding Developments Proposed to Take Place on, or which are Likely to Impact on, Sacred Sites and on Lands and Waters Traditionally Occupied or Used by Indigenous and Local Communities*, CBD Guidelines Series, Montreal, Canada.

Sefton, R, Peterson, D, Woods, R, Kassebaum, A, McKenzie, D, Simpson, B and Ramsay, M 2020, *Final report: Independent assessment of social and economic conditions in the Murray-Darling Basin*, Panel for Independent Assessment of Social and Economic Conditions in the Murray-Darling Basin, Melbourne.

Senate Environment and Communications Legislation Committee 2023a, *Proof Committee Hansard, Water Amendment (Restoring Our Rivers) Bill 2023, Wednesday 1 November 2023*, November, Australian Government.

—— 2023b, *Water Amendment (Restoring Our Rivers) Bill 2023 [Provisions]*, Australian Government.

Siebert, B and Hollingworth, K 2022, ‘Most critical failure: Water compliance chief blasts NSW over Murray-Darling Basin Plan’, *ABC News*, 2 June.

The Australia Institute 2023, *Polling – Murray Darling: September 2023*, Canberra.

Thurgate, N, Mynott, J, Smith, L and Bond, N 2019, *Murray-Darling Basin Environmental Water Knowledge and Research Project*, Synthesis Report, p. 41.

UN (United Nations) 2007, *United Nations Declaration on the Rights of Indigenous Peoples*, Geneva, Switzerland.

Vertessy, R, Barma, D, Baumgartner, L, Mitrovic, S, Sheldon, F and Bond, N 2019, *Independent Assessment of the 2018-19 Fish Deaths in the Lower Darling*, 29 March.

VEWH (Victorian Environmental Water Holder) 2019a, *Managing water for the environment*, https://www.vewh.vic.gov.au/watering-program/managing-water-for-the-environment (accessed 4 September 2023).

—— 2019b, *Water for the environment is good for all of us*, https://www.vewh.vic.gov.au/water-for-the-environment/shared-community-benefits (accessed 5 July 2023).

—— 2022, *Reflections: Water for the Environment in Victoria 2021-22*, Melbourne.

Victorian DEECA (Victorian Department of Energy, Environment and Climate Action) 2023, *Water availability climate change guidelines*, https://www.water.vic.gov.au/our-programs/climate-change-and-victorias-water-sector/delivering-water-in-a-changing-climate/water-availability-climate-change-guidelines (accessed 9 October 2023).

Victorian DELWP (Victorian Department of Environment, Land, Water and Planning) 2016a, *Goulburn Constraints Measure Business Case*.

—— 2016b, *Hume to Yarrawonga Constraints Measure Business Case*.

—— 2020, *Water quality in the Victorian Murray Darling Basin*, October.

—— 2022a, *Basin Plan Annual report matter 19 Part A - Victoria 2020-21*.

—— 2022b, *Water is Life: Traditional Owner access to Water Roadmap*.

Victorian DEPI (Victorian Department of Environment and Primary Industries) 2014a, *Supply Measure Business Case: Gunbower National Park Environmental Works Project*.

—— 2014b, *Supply Measure Business Case: Guttrum and Benwell Forests Environmental Works Project*.

—— 2015a, *Supply Measure Business Case: Belsar-Yungera Floodplain Management Project*.

—— 2015b, *Supply Measure Business Case: Burra Creek Floodplain Management Project*.

—— 2015c, *Supply Measure Business Case: Hattah Lakes North Floodplain Management Project*.

—— 2015d, *Supply Measure Business Case: Lindsay Island Management Project*.

—— 2015e, *Supply Measure Business Case: Nyah Floodplain Management Project*.

—— 2015f, *Supply Measure Business Case: Vinifera Floodplain Management Project*.

—— 2015g, *Supply Measure Business Case: Wallpolla Island Management Project*.

Victorian Government 1989, *Water Act*.

—— 2022, *Victoria Matter 19 compliance with Water Resource Plan Part A and Part B 2021-22*, Basin Plan Implementation reports, 12 December, Schedule 12 reports.

Water for Rivers 2010, *Water for Rivers Response to the report - Market Mechanisms for Recovering Water in the Murray Darling Basin Productivity Commission Draft Research Report*, Submission DR 89.

Wensing, E, Taylor, K and Cannon, P 2023, *National First Nations Water Roundtable. Securing Water rights for First Nations’ self determination*, Australian National University, Canberra.

WESA Review (Water for the Environment Special Account Review Panel) 2020, *First Review of the Water for the Environment Special Account*, Report to Commonwealth Minister for Water Resources as required under Section 86AJ of the Water Act 2007, Canberra.

—— 2021, *Second Review of the Water for the Environment Special Account*, Report to Commonwealth Minister for Water Resources as required under Section 86AJ of the Water Act 2007, Canberra.

WGCS (Wentworth Group of Concerned Scientists) 2023, *Are Murray-Darling Basin rivers getting the water they need to stay healthy?*

Wheeler, S and Cheesman, J 2013, ‘Key findings from a survey of sellers to the restoring the balance programme’, *Economic Papers*, vol. 32, no. 3, pp. 340–352.

Wyborn, CA, Kerkhoff, LE van, Colloff, MJ, Alexandra, J and Olsson, R 2023, ‘The politics of adaptive governance: water reform, climate change, and First Nations’ justice in Australia’s Murray-Darling Basin’, *Ecology and Society*, vol. 28, iss. 1 art. 4.

Zhang, L, Zheng, H, Teng, J, Chiew, F and Post 2020, *Plausible Hydroclimate Futures for the Murray-Darling Basin. A report for the Murray–Darling Basin Authority*, CSIRO, Australia.

1. In long-term average annual yield terms (LTAAY). [↑](#footnote-ref-2)
2. The reduction in the northern Basin water recovery was on the condition that the Australian, Queensland, and New South Wales governments commit to implementing the northern Basin toolkit measures to ensure effective management of environmental water in the northern Basin. [↑](#footnote-ref-3)
3. The IGWC was established in response to the Commission’s 2018 recommendation to establish a Basin Plan Regulator (with the transfer of MDBA’s regulatory functions). [↑](#footnote-ref-4)
4. The notified Menindee Lakes project incorporates the lower Darling constraints‑easing project; it is counted in both figures. [↑](#footnote-ref-5)
5. Costs per ML/y of water recovery, in 2022 dollars. Commission estimates based on Wheeler et al (sub 104, p. 2). Cost estimates do not include the cost of any transitional assistance. [↑](#footnote-ref-6)
6. The other central pillars of the Agreement are: Building the Aboriginal and Torres Strait Islander community-controlled sector (priority reform 2) and Improving and sharing access to data and information to enable Aboriginal and Torres Strait Islander communities to make informed decisions (priority reform 4). [↑](#footnote-ref-7)
7. We use both ‘First Nations people’ and ‘Aboriginal and Torres Strait Islander people’ to refer to Aboriginal and/or Torres Strait Islander people. In some instances, we refer specifically to ‘Aboriginal people’. The term ‘Indigenous’ is sometimes used by participants and included in programs and policies (including the Basin Plan), so this term also appears in this report. [↑](#footnote-ref-8)
8. The Basin states are New South Wales, Victoria, Queensland, South Australia, and the Australian Capital Territory. [↑](#footnote-ref-9)
9. The reduction in the northern Basin water recovery was on the condition that the Australian, Queensland, and New South Wales Governments commit to implement the northern Basin toolkit measures to ensure effective management of environmental water in the northern Basin. [↑](#footnote-ref-10)
10. Submission to the Department of Climate Change, Energy, Environment and Water Delivering the Basin Plan Ideas Consultation Process (p. 3). [↑](#footnote-ref-11)
11. All water volumes are presented in long‑term average annual yield (LTAAY) terms, which provide a common unit for different types of water entitlements in the Basin. Different entitlements will make different contributions to water recovery targets, and individual entitlement types are converted into LTAAY through long‑term diversion limit equivalence factors, also known as ‘cap’ factors. [↑](#footnote-ref-12)
12. Being notified under section 7.12 of the Basin Plan means some constraints‑easing projects contribute to the supply measure water recovery offset, and are eligible for additional Australian Government funding under the 2013 *Intergovernmental Agreement on Implementing Water Reform in the Murray Darling Basin*. [↑](#footnote-ref-13)
13. *Intergovernmental Agreement on Implementing Water Reform in the Murray Darling Basin 2013*, s. 2.2. [↑](#footnote-ref-14)
14. Riverland Floodplain Integrated Infrastructure Program (SA), Eastern Mount Lofty Ranges Flows for the Future Project (SA), Nimmie Caira infrastructure modifications (NSW), South East Flows Restoration Project (SA) and Barmah‑Millewa Forest environmental water allocation (Vic). [↑](#footnote-ref-15)
15. The 2013 IGA (s. 3.1) states that the Australian Government will outline implementation of its commitment to bridge the gap through a water recovery strategy, and the role of water entitlement purchase will be ‘limited to the residual amount of water recovery required to bridge the gap by 2019’. [↑](#footnote-ref-16)
16. Basin Plan, s. 7.12(5). [↑](#footnote-ref-17)
17. Explanatory Memorandum, Water Legislation Amendment (Inspector-General of Water Compliance and Other Measures) Bill 2021, p. 3. [↑](#footnote-ref-18)
18. As discussed in chapter 4, slow progress on finalising water resource plans in NSW also means SDLs cannot yet be enforced in many parts of that state. [↑](#footnote-ref-19)
19. 2013 IGA, section 2.2. [↑](#footnote-ref-20)
20. Water Act, ss. 85B‑85D. [↑](#footnote-ref-21)
21. Basin Plan, s. 7.17(b). [↑](#footnote-ref-22)
22. CICL, sub. 21, pp. 4–5; MRGC, sub. 22, p. 6; Goulburn‑Murray Water, in Victorian Government, sub. 74, p. 9, VFF, sub. 138, pp. 1–2. [↑](#footnote-ref-23)
23. Basin Plan, schedule 5, s. 2(f). [↑](#footnote-ref-24)
24. Indec estimated the offset attributable to four southern Basin constraints-easing projects at 80 GL/y, although this estimate depended on progress of other measures, including the enhanced Environmental Water Delivery project (Indec 2021b). [↑](#footnote-ref-25)
25. *Water Act 1989* (Vic), s. 157; *Water NSW Act 2014* (NSW), s. 37. [↑](#footnote-ref-26)
26. For example, Beer, sub. 38, p. 14. [↑](#footnote-ref-27)
27. Indec (2021b, p. 1) used an estimate of 105.6–147.2 GL/y for the offset attributable to the Menindee project and all constraints projects except the South Australian River Murray. [↑](#footnote-ref-28)
28. The second WESA review in 2021 concluded that the lowest cost scenario of recovering 450 GL/y through efficiency measures, with a 75% premium on market prices, would cost $3.46 billion (WESA Review 2021, pp. 31–32). This implies that directly purchasing those entitlements – and ignoring the likely price impacts of a major water purchase program – would cost almost $2 billion and exceed the existing $1.575 billion available under the WESA. The Australian Government has indicated that more funding is allocated for water purchases, but the total amount is not available. [↑](#footnote-ref-29)
29. GVEG, sub. 28, p. 1; NSW Government, sub. 43, p. 12; Lifeblood Alliance, sub. 52, pp. 4–5; MDBA, sub. 61, p. 7; CEWH, sub. 69, p. 2; DCCEEW, sub. 77, pp. 16–17. [↑](#footnote-ref-30)
30. Basin Plan, schedule 5, s. 2(f). [↑](#footnote-ref-31)
31. NCC NSW, sub. 50, p. 4; Lifeblood Alliance, sub. 52, p. 4; Temba Orchards, sub. 87, p. 3; EDO sub. 91, attachment 1, p. 11; Environment Victoria, sub. 99. [↑](#footnote-ref-32)
32. River Lakes and Coorong Action Group, sub. 15, p. 2; Goulburn Valley Environment Group, sub. 28, pp. 1–2; Trangie Local Aboriginal Land Council, sub. 40, p. 1; Beasley, sub. 47, pp. 10–12; NCC NSW, sub. 50, pp. 2–3; Lifeblood Alliance, sub. 52, pp. 1–2; ATSE, sub. 71, p. 3; Wentworth Group of Concerned Scientists, sub. 81, p. 2; EDO, sub. 91, attachment 1, p. 9–11; Environment Victoria, sub. 99, pp. 12–16; NSW Aboriginal Land Council, sub. 101, p. 11. [↑](#footnote-ref-33)
33. LMW SAC, sub. 9, p. 1; CICL, sub. 21, p. 9; MRGC, sub. 22, pp. 10–11; Moira Shire Council, sub. 25, pp. 2–3; VFF, sub. 34, p. 4; NFF, sub. 46, pp. 8–9; NIC, sub. 62, pp. 10–11; ADIC, sub. 64, p. 2; Balonne Shire Council, sub. 70, pp. 2–3; Murrumbidgee Irrigation, sub. 73, p. 3; Victorian Government, sub. 74, pp. 3–4; Bourke Shire Council, sub. 79, p. 3; Committee for Greater Shepparton, sub. 80, p. 8; Southern Riverina Irrigators, sub. 97, p. 10. [↑](#footnote-ref-34)
34. GVIAP declined after 2018, in part due to 2019-20 drought and floods. [↑](#footnote-ref-35)
35. An administrative reduction to entitlement values would be expected to affect the ‘cap factors’ on the CEWH’s entitlements: the same water entitlement would contribute less towards the Bridging the Gap target in LTAAY terms. [↑](#footnote-ref-36)
36. Central Irrigation Trust, sub. 122, p. 2; NSW Farmers Association, sub. 123, pp. 4–5; National Irrigators Council, sub. 130, p. 11. [↑](#footnote-ref-37)
37. Planned environmental water is water provided through rules on consumptive water users or river operators that constrain the volume and timing of extractions or require releases from storages under certain conditions in order to ensure that water remains in the system to achieve environmental outcomes. Planned environmental water includes water committed by water resource plans (chapter 4) as well as state laws or plans. Held environmental water is water that has been recovered for the environment through the purchase of water entitlements and other mechanisms such as efficiency projects. Entitlements are managed by government environmental water holders (with the majority held by the Commonwealth Environmental Water Holder) and are used specifically to achieve positive environmental outcomes. [↑](#footnote-ref-38)
38. Chapter 8 of the Basin Plan, Part 2. [↑](#footnote-ref-39)
39. Chapter 7 of the Basin Plan, Part 2, Division 4. [↑](#footnote-ref-40)
40. Chapter 8 of the Basin Plan, Part 4. [↑](#footnote-ref-41)
41. This aligned with recommendation 11.1 of the Commission’s 2018 assessment of Basin Plan implementation. [↑](#footnote-ref-42)
42. Chapter 8 of the Basin Plan, Part 4, Division 3. [↑](#footnote-ref-43)
43. Changes to the BWEWS in 2019 were not considered sufficient to trigger a review of LTWPs (MDBA 2020d, p. 1). [↑](#footnote-ref-44)
44. Chapter 8 of the Basin Plan, Part 4, Division 3. [↑](#footnote-ref-45)
45. Chapter 8 of the Basin Plan, Part 4. [↑](#footnote-ref-46)
46. Chapter 8 of the Basin Plan, Part 4, Division 4. [↑](#footnote-ref-47)
47. Chapter 8 of the Basin Plan, Part 4, Division 5. [↑](#footnote-ref-48)
48. Including optimising social outcomes under Chapter 5 of the Basin Plan. [↑](#footnote-ref-49)
49. An SDL is defined for each SDL resource unit in the Basin. There are 109 units in total comprising surface and groundwater units (MDBA 2022m, p. 2). [↑](#footnote-ref-50)
50. As at 12 December 2023. [↑](#footnote-ref-51)
51. The NSW Government finalised regional water strategies for the Gwydir, Barwon-Darling and Namoi valleys in November 2022, December 2022 and June 2023 respectively (NSW DPE 2022f, 2022g, 2023d). These regional water strategies are not legislative documents. [↑](#footnote-ref-52)
52. The Water Act 2007 (Cth), ss. 68-69. [↑](#footnote-ref-53)
53. The Water Act 2007 (Cth), s. 73 sets out the six procedures over 13 sub-sections that must occur before the Minister can exercise step-in powers to request the MDBA to prepare a WRP. [↑](#footnote-ref-54)
54. Commitments include SDL accounting and protection of environmental water. [↑](#footnote-ref-55)
55. Under section 10.17 and 10.18 of the Basin Plan, WRPs must be prepared having regard to whether it is necessary to include rules which ensures the operation of the WRP does not compromise the meeting of environmental watering requirements of priority environmental assets and ecosystem functions. Planned environmental water (water in the system after extraction) is influenced by these rules and is different to held environmental water entitlements which have specific volumes attached to them (chapter 3). [↑](#footnote-ref-56)
56. Basin Plan s. 10.12(1)(e). [↑](#footnote-ref-57)
57. Basin Plan ss. 10.23(1)(b) and (3)(b)ii. [↑](#footnote-ref-58)
58. Basin Plan s. 10.27. [↑](#footnote-ref-59)
59. Basin Plan s. 10.35. [↑](#footnote-ref-60)
60. The Basin Plan s. 6.08(6). [↑](#footnote-ref-61)
61. Submissions to the Senate Standing Committee on Environment and Communications inquiry into the Water Amendment (Restoring Our Rivers) Bill 2023 (SSCEC 2023) (IGWC, SSCEC 2023, sub. 32, p. 4; Shing, SSCEC 2023, sub. 68, p. 3; Close, SSCEC 2023, sub. 70, p. 4-5). [↑](#footnote-ref-62)
62. Requirements for WRPs are set out in chapter 10 of the Basin Plan. [↑](#footnote-ref-63)
63. Independent Investigation into NSW Water Management and Compliance (Matthews 2017b, 2017a) and The Murray–Darling Basin Water Compliance Review (MDBA 2017e). [↑](#footnote-ref-64)
64. Basin Plan 10.17-10.21. [↑](#footnote-ref-65)
65. Basin Plan 10.22 and part 9, 10.41. [↑](#footnote-ref-66)
66. ACT Government, sub. 85., p. 4; CICL, sub. 21, p. 6; MLDRIN, sub. 92, p. 14-15; Victorian Government, sub. 74., response to information request, p. 3. [↑](#footnote-ref-67)
67. DEECA, sub. 131, p. 1; DRDMW, sub. 112, p. 8; MIL, sub. 118, p. 1; NIC, sub. 130, p. 10; NSWIC, sub. 110, p. 5. [↑](#footnote-ref-68)
68. IRN, sub. 109, p. 2; LBA, sub. 119, p. 6; NPA NSW, sub. 121, p. 3; NSW FA, sub. 123, p. 6. [↑](#footnote-ref-69)
69. Water Act 2007 (Cth) s. 66. [↑](#footnote-ref-70)
70. Water Regulations 2008 (Cth) 2.11A. [↑](#footnote-ref-71)
71. DRDMW, sub. 112, p. 15; NIC, sub. 130, p. 10; NSWIC, sub. 110, p. 5. [↑](#footnote-ref-72)
72. IRN, sub. 109, pp. 4-5; LBA, sub. 119, p. 6; NPA NSW, sub. 121, p. 3. [↑](#footnote-ref-73)
73. Basin state governments have primary responsibility for regulating water take for individual water licence holders while the MDBA and the IGWC use Basin states water take data to assess compliance against the SDL resource units for each WRP area. [↑](#footnote-ref-74)
74. The MDBA also publishes on its website the narratives that Basin states provide accompanying their SDL water accounting data (MDBA 2023p). [↑](#footnote-ref-75)
75. Permitted take is underpinned by a number of ‘planning assumptions’ such as historical climate conditions, expected utilisation of entitlement classes, trading patterns and the impact of water sharing rules for a particular WRP Area (for example, carryover, trading, floodplain harvesting and water access rules). [↑](#footnote-ref-76)
76. For the NSW WRPs that are not yet in place, reporting on SDL water accounting and make good actions where exceedances occur are supported by bilateral agreements signed between Basin States and the MDBA (MDBA 2022d) and required under s. 71 of the *Water Act 2007* (Cth) (NSW DPE 2022d, 2023b; NSW DPIE 2021). Information on NSW water extraction is included in the annual water take report. However, the IGWC cannot undertake enforcement or compliance actions until a WRP is accredited. [↑](#footnote-ref-77)
77. Non-compliance occurs when the cumulative balance over a three year period exceeds 20 per cent of the long-term annual diversion limit for the SDL and Basin States do not provide a reasonable excuse (IGWC 2023h, pp. 18–19, 2023e, p. 8). [↑](#footnote-ref-78)
78. Basin Plan 10.45(1). [↑](#footnote-ref-79)
79. The Pearson Report made six recommendations in total to ‘facilitate more collaboration, consistency and reconcilability’ in compliance and enforcement activities across the Basin (Pearson 2022, pp. 12–13). [↑](#footnote-ref-80)
80. See also Accounting for Interstate Trade in the Northern Basin (IGWC 2022b) and Goulburn-Murray Water disclosure obligations under the Basin Plan (IGWC 2022c). [↑](#footnote-ref-81)
81. Basin Plan Schedule 12, Matter 19. [↑](#footnote-ref-82)
82. Basin Plan Schedule 12, Matter 18. [↑](#footnote-ref-83)
83. ACT Government (2023); QLD DRDMW (2022); SA Government (2022); Victorian Government (2022). [↑](#footnote-ref-84)
84. Key Evaluation Question (KEQ) (b) to what extent have the objectives, targets and outcomes set out in the Basin Plan been achieved? KEQ(d) what, if any, unanticipated outcomes have resulted from the implementation of the Basin Plan? KEQ(e) how could the effectiveness of the Basin Plan be improved? KEQ(f) to what extent were the actions required by the Basin Plan suited to meeting the objectives of the Basin Plan? [↑](#footnote-ref-85)
85. pg i. [↑](#footnote-ref-86)
86. The views outlined do not represent those of all Basin First Nations nor were they unanimous across First Nations groups represented at the Roundtable. [↑](#footnote-ref-87)
87. Part 14 Chapter 10 [↑](#footnote-ref-88)
88. ss. 10.52(2)(a) [↑](#footnote-ref-89)
89. ss. 10.52(2)(b) [↑](#footnote-ref-90)
90. ss. 10.54 [↑](#footnote-ref-91)
91. ss. 10.53(1)(a) [↑](#footnote-ref-92)
92. ss.  4.03(g) [↑](#footnote-ref-93)
93. ss.  5.02(a) [↑](#footnote-ref-94)
94. ss.  5.04(1) [↑](#footnote-ref-95)
95. ss.  8.15(4)(e) [↑](#footnote-ref-96)
96. ss.  8.29(3)(g) and 8.35 (iii-iv) [↑](#footnote-ref-97)
97. ss.  10.52 [↑](#footnote-ref-98)
98. ss. 10.52 (3) [↑](#footnote-ref-99)
99. Part 14 of the Basin Plan 2012 [↑](#footnote-ref-100)
100. https://www.mdba.gov.au/water-management/basin-plan/water-resource-plans/list-state-water-resource-plans [↑](#footnote-ref-101)
101. The views outlined do not represent all Basin First Nations and they were not unanimous across First Nations groups. [↑](#footnote-ref-102)
102. Since 2018 responsibility for the program has been transferred between three Australian Government agencies and now sits with DCCEEW. [↑](#footnote-ref-103)
103. River Lakes Coorong Action Group, sub. 15, p. 4; Anne Jensen, sub. 39, p. 3; Environmental Defenders Office, sub. 91, p. 29; NSW Aboriginal Land Council, sub. 101, p. 10. [↑](#footnote-ref-104)
104. *Water Act 2007* (Cth), s.  21(4). [↑](#footnote-ref-105)
105. Sections 4.03, 8.53, 8.56, 8.62, 10.49, 11.03, 13.04. [↑](#footnote-ref-106)
106. Chapter 1, Part 3. [↑](#footnote-ref-107)
107. The Basin Plan was amended in 2018 following the Northern Basin Review and in 2021 to establish the role of the Inspector-General of Water Compliance. Further amendments were made in late 2023 to extend the timeframe for full implementation of the Basin Plan (chapter 1). [↑](#footnote-ref-108)
108. The MDBA was allocated $103.7 million in the 2023-24 budget for the 2026 review of the Basin Plan, with updated science to enable the Basin to adapt to the impacts of climate change (Australian Government 2023). [↑](#footnote-ref-109)
109. The Environmental Watering Plan is chapter 8 of the Basin Plan. [↑](#footnote-ref-110)
110. s. 8.04 [↑](#footnote-ref-111)
111. s. 4.03 [↑](#footnote-ref-112)
112. By knowledge generation we mean activities that build understanding of the current state of the world, what is expected to happen and what may happen if things change. These activities include discovering new information, and also collating information in new ways to enhance understanding. Knowledge can include results of scientific research, First Nations’ knowledges, community insights and experience, monitoring data and the findings of reviews and evaluations (including reviews of socio-economic conditions). [↑](#footnote-ref-113)
113. Basin Plan, s. 5.02 and 5.04 [↑](#footnote-ref-114)
114. Basin Plan, ss. 9.04 to 9.07 and ss. 9.16 to 9.19 [↑](#footnote-ref-115)
115. Basin Plan, s. 9.09(3) [↑](#footnote-ref-116)
116. Basin Plan, s. 9.14(6) [↑](#footnote-ref-117)
117. Basin Plan, s. 9.09(5) [↑](#footnote-ref-118)
118. Basin Plan, Schedule 12, Matter 12 [↑](#footnote-ref-119)
119. (NSW DPIE 2020b; SA DEW 2020; Victorian DELWP 2020) [↑](#footnote-ref-120)
120. Some of the water quality targets for fresh water-dependent ecosystems in Schedule 11 of the Basin Plan refer to the ANZ Guidelines. The Basin Plan also allows WQM plans to specify alternative water quality targets if, among other things, the targets are determined in accordance with procedures set out in the ANZ Guidelines. See sections 9.16 and 10.32 and Schedule 11 of the Basin Plan. [↑](#footnote-ref-121)
121. Water Act, s. 86A [↑](#footnote-ref-122)
122. Basin Plan, chapter 11. ‘Conveyance water is water in the River Murray System required to deliver water to meet critical human water needs as far downstream as Wellington in South Australia’: Water Act s. 86A(4). [↑](#footnote-ref-123)
123. Basin Plan, Schedule 12, item 13 [↑](#footnote-ref-124)
124. Basin Plan, chapter 10, part 13 [↑](#footnote-ref-125)
125. Specifically, the areas covered by the surface water resource plans for NSW Murray and Lower Darling, Barwon-Darling watercourse. [↑](#footnote-ref-126)
126. Fleur Thompson, sub. 14, p. 1; Pastoralists’ Association of West Darling, sub. 42, pp. 2, 8; NSW South-West Water Users Association, sub. 16, p. 3; NSW Aboriginal Land Council, sub. 101, p. 9. [↑](#footnote-ref-127)
127. The MDB Agreement requires that each year the Basin Officials Committee approve the *Objectives and outcomes for river operations in the River Murray System* anddocument where the general objectives and outcomes relate to: Water storage, delivery and accounting; River Murray Operations assets; People and communities; Environment; Communications and information management (MDBA 2022a, p. vii). [↑](#footnote-ref-128)
128. The Independent River Operations Review Group also suggested changes to governance arrangements to meet these challenges (IRORG 2021, pp. 28–30). [↑](#footnote-ref-129)
129. *New South Wales – Queensland Border Rivers Intergovernmental Agreement 2008* and *Paroo River Intergovernmental Agreement 2003* [↑](#footnote-ref-130)
130. NSW Government, sub. 111, p. 11; Queensland Department of Regional Development, Manufacturing and Water, sub. 112, p. 9-10; Murray Darling Basin Authority, sub. 126, pp. 7–8; Department of Climate Change, Energy, the Environment and Water, sub. 127, p. 19. [↑](#footnote-ref-131)
131. Other reports have considered related options, such as establishing a Basin-scale group that is both ‘cross jurisdiction and cross agency’ to scope and implement emergency responses (Vertessy et al. 2019, p. 68). [↑](#footnote-ref-132)
132. Healthy Rivers Lower Murray, sub. 106, p. 4; Inland Rivers Network, sub. 109, pp. 5–6; Lifeblood Alliance, sub. 119, p. 11; Murraylands and Riverland Landscape Board, sub. 132, p. 5. [↑](#footnote-ref-133)
133. For example, NSW Irrigators Council, sub. 110, p. 8; NSW Farmers’ Association, sub. 123, p. 8. [↑](#footnote-ref-134)
134. Basin Plan, s. 5.07. [↑](#footnote-ref-135)
135. As discussed below, some of these rules will be modified and moved out of the Basin Plan and into the Water Act by the Restoring Our Rivers Act. [↑](#footnote-ref-136)
136. Water Act, s. 22(1), item 12 and Schedule 3. [↑](#footnote-ref-137)
137. National Water Initiative Agreement 2004, par. 23 (v). [↑](#footnote-ref-138)
138. National Water Initiative Agreement 2004, par. 58 (i) - (v). [↑](#footnote-ref-139)
139. The Commission’s terms of reference state that we should avoid unnecessarily duplicating recently completed or ongoing reviews, including the water reform roadmap. [↑](#footnote-ref-140)
140. Schedule D allows water users in some states to trade water across state boundaries and between valleys. A review of this schedule is underway and is seeking to identify ‘opportunities to improve efficiency and access to intervalley trade opportunities’ and is expected to ‘address relevant roadmap recommendations’ (DCCEEW, sub. 77 p. 22). [↑](#footnote-ref-141)
141. Submission to Senate Standing Committee on Environment and Communications inquiry into the Water Amendment (Restoring Our Rivers) Bill 2023 (pp. 12–13). [↑](#footnote-ref-142)
142. ACCC, sub. 107; IGWC, sub. 133; Inland Rivers Network, sub. 109; NSW Irrigators, sub. 110; Lifeblood Alliance, sub. 119; National Parks NSW, sub. 121; National Irrigators Council, sub. 130 (in principle). [↑](#footnote-ref-143)
143. Basin Plan, ss. 12.16 and 12.18. [↑](#footnote-ref-144)
144. Basin Plan, s. 12.19. [↑](#footnote-ref-145)
145. Basin Plan, s. 12.20. [↑](#footnote-ref-146)
146. Basin Plan, s. 12.20(3). [↑](#footnote-ref-147)
147. An instrument of the Water Act (part 2, division 1). [↑](#footnote-ref-148)
148. Water Act s. 201A. [↑](#footnote-ref-149)
149. Water Act s. 201. [↑](#footnote-ref-150)
150. Basin Plan s. 7.12. [↑](#footnote-ref-151)
151. Water Act s. 202. [↑](#footnote-ref-152)
152. Water Act s. 215C. [↑](#footnote-ref-153)
153. See also Slattery and Johson, sub. 90, pp. 22‑23 and Renmark Irrigation Trust, sub. 24, p. 5. [↑](#footnote-ref-154)
154. Agreement of Murray-Darling Basin Ministers to Deliver the Basin Plan in Full (CFFR 22 August 2023). [↑](#footnote-ref-155)
155. Implementing Water Reform in the Murray‑Darling Basin 2021‑22 - 2023‑24 (CFFR 1 March 2022). [↑](#footnote-ref-156)
156. IGWC, sub. 75, p. 23; Slattery and Johnson, sub. 90 p. 23; Inland Rivers Network, sub.109 p. 2; Lifeblood Alliance, sub.119 p. 11; National Parks Association, sub. 121 p. 4; NSW Farmers’ Association, sub. 123 p. 8; the National Irrigators’ Council, sub. 130 p. 10. [↑](#footnote-ref-157)