# 17	Implementation

## 1	Implementation in outline

In this draft report, the Commission has laid out a blueprint for a coherent response to the significant problems that bedevil the provision of disability support services. But while many people need help urgently, implementation cannot occur overnight. The Commission’s proposals concern arrangements for the long run:

- They involve two major new national programs on a scale much larger than the sum of all the current state-based disability and accident arrangements, so careful and detailed preparatory work will be needed.

- Different pathways and contingencies are possible and need to be planned for.

- No matter how careful the planning, the introduction of the NDIS, a wholly new and very complex scheme, will inevitably encounter some early difficulties. These would be more manageable and less likely to be serious if the scheme started on a relatively small scale.

Moreover, implementation will confront the difficulties of a major reform being undertaken within a system that has multiple jurisdictions with established systems, overlapping responsibilities and a long-standing shortfall in funding. For such reasons, existing state and territory disability services will have to remain as they are for a while and, even after the introduction of the new arrangements, coexist for some time. During this period, the Australian Government should supplement funding under the National Disability Agreement to reduce some of the worst rationing of support services. This would also help to alleviate pressures on the state schemes during the transition to the NIIS and the NDIS.

This chapter is about the various phases in the implementation of the NIIS and NDIS. The proposed timetable is discussed below and summarised in tables 17.1 and 17.2.

## 2	Implementation of the NIIS

Chapter 16 has laid out a detailed implementation plan for the NIIS, noting several reasons why its overall implementation could be rapid. This would be helped by the strong knowledge base that already exists. Some jurisdictions have already made a successful transition from fault-based to no-fault motor vehicle accident schemes (the Lifetime Care and Support scheme in New South Wales, for example), and a number of others have undertaken detailed work on the possible implementation of a no-fault system. The Heads of Treasuries Insurance Issues Working Group had earlier looked at possible national arrangements for the sharing of information through a central database, benchmarking, and consistent actuarial valuations. Senior state insurance executives meet regularly, and working groups such as the Heads of Compulsory Third Party Authorities and Heads of Workers’ Compensation Authorities are well versed in many of the issues.

To facilitate implementation, the Commission proposes that a full-time high level taskforce comprising representatives from all jurisdictions should be established. The initial priority should be the creation of no-fault motor vehicle and medical accident insurance schemes in all jurisdictions by October 2013, with other forms of catastrophic injury to be covered by 2015 (table 17.1).

Table 1	Implementation of the NIIS

| Date | Milestone |
| --- | --- |
| Second half of 2011, or early 2012 | COAG would: - agree to the establishment of the NIIS, whereby states would implement no-fault accident insurance schemes for long-term care of new cases of catastrophic injury - agree to have these arrangements in place in all jurisdictions for motor vehicle and medical accidents by October 2013 - establish a full-time high level taskforce to help implement this the taskforce would report back regularly to Heads of Treasuries meetings and COAG on milestones reached |
| Oct 2013 | NIIS to cover catastrophic injuries from motor vehicle and medical accidents in all jurisdictions on a no-fault basis |
| 2015 | people suffering catastrophic injuries from other causes should be covered by at least 2015 |
| 2020 | independent review of the NIIS |

This would require a memorandum of understanding between jurisdictions, or other provisions that provide a framework for cooperation and joint activities. (Some existing cooperative agreements between the states in relation to disability services are noted in box 17.1.)

The key stakeholders in the NIIS will be the state and territory governments. But the Australian Government would play a facilitation role, and perhaps contribute to the premium pool in those jurisdictions where the injury risks are higher (chapter 16). More broadly, it could encourage the states and territories to establish an NIIS as a quid pro quo of the very large additional revenue contributions it would make to the NDIS.

Do not delete this return as it gives space between the box and what precedes it.

Box 1 Existing cooperative agreements between the states

Memorandum of Understanding (MOU) between Victoria and NSW The aim of the MOU is to assist ADHC and the Victorian Department of Human Services to engage in a collaborative approach to the delivery of specialist disability services in cross-border regions of NSW and Victoria: - To establish arrangements for the better coordination of service delivery of cross-border specialist disability services - To enable eligible individuals living in cross-border community to access specialist disability services funded by the State other than their State of residence, where it is considered appropriate to do so - To establish an ongoing forum in which cross-border issues can be discussed and resolved - To facilitate a better understanding of each department’s policies and services as it affects day to day regional business. The Tri-State Agreement The Western Australia, South Australia and the Northern Territory Governments in 2004 formed the Tri-State Disability Services Group to develop a framework agreement to ensure a coordinated approach to providing disability services to the Ngaanyatjarra, Pitjantjatjara and Yankunytjatjara lands covering 350 000km2 across the three jurisdictions. The framework agreement has guided the operations of the three jurisdictions in delivering services to the people of the region over the past five years. The Interstate Portability Protocol In 2000, the Disability Services Ministers endorsed a national policy framework regarding the interstate transfer of people with a disability. This framework or Protocol establishes a mechanism to assist people with a disability transferring between jurisdictions to negotiate programs and services to achieve a comparable level of support. Work is currently underway to improve the implementation of the Protocol across jurisdictions.

Source: NSW Government (sub. 536, pp. 49–50).

When established, the NDIA (itself a federated institution) would act as a facilitator, to ensure clear linkages between the various state and territory government schemes. It would:

- host regular meetings of the CEOs of the accident scheme agencies

- act as a forum to address issues such as greater consistency in eligibility, definitions and assessment; the appropriate benchmark standard of care; reporting standards; and benchmarking of performance

- be the central repository for data and its analysis

- assist in undertaking cooperative trials across jurisdictions, combined research studies, and diffusions of any lessons from innovations undertaken by a given jurisdiction.

## 3	Implementation of the NDIS

### Early negotiation between all governments

The Australian Government and the state and territory governments should negotiate early on the NDIA and the NDIS.

The initial objective should be to get agreement to allow detailed work to begin immediately on creation of the NDIS, irrespective of how the pathway to a new system unfolds. Examples of such detailed work are given below.

For other matters, such as the structural aspects of the NDIA and the NDIS, early work may need to wait until sufficient jurisdictions have given in-principle support and the broad shape of the scheme has been settled. The Australian Government should be responsible for drafting legislation to establish and underpin the NDIS, but in consultation with state and territory governments.

### A taskforce should oversee preparatory work

To oversee an early start on essential preparations, all governments, through the Council of Australian Governments (COAG), should establish a high level taskforce comprising senior officials from all jurisdictions. In view of the commercial, corporate model of governance proposed for the scheme (chapter 7), the taskforce should be headed by a person with insurance or disability experience who has driven change successfully in a large organisation, appointed with the agreement of all jurisdictions. The taskforce should operate on a full-time basis, and report back regularly to Heads of Treasuries meetings and to COAG on agreed milestones in the planning for the commencement of the NDIS.

A key task will be to develop the details and drafts of the proposed intergovernmental agreements and the associated revenue arrangements, including setting out the financing obligations of the Australian Government and the reciprocal introduction of tax reform by state and territory governments. This will involve close liaison between Heads of Treasuries and the taskforce.

Governments should seek to achieve in-principle agreement on these matters at an early meeting of COAG in 2012, and final agreement in early 2013. This should allow the scheme to commence at the beginning of 2014.

There are many ‘nuts and bolts’ issues that will need to be resolved early in order to successfully implement the NDIS. Work could commence immediately on many of these, in many cases through parties contracted to the taskforce. Examples include the following:

- Data and the systems that underpin it will be critical. These will act like navigation systems, providing continual feedback and informing small ongoing adjustments that will help keep the NDIS on track. Without this feature, the scheme would not be able to effectively monitor outcomes nor keep costs under control. For example, under a constrained budget it would mean the re-emergence of rationing and under a flexible budget it would risk the financial sustainability of the scheme. In either case, it would imply less than ideal outcomes for people with a disability and their families. To avoid this, there is a need for high quality, real-time data to be produced and incorporated into day-to-day decision-making. Work should begin on:

- processes for achieving agreement on data standards and content, assessment standards and protocols and standards for services, electronic patient records and so on

- devising the administrative and IT arrangements to allow communication and reporting between the NDIA and the many assessors, suppliers, and others that will have a role to play (and for whom regular communication and reporting will be important for the smooth running of the NDIS). One possibility would be to start with fairly standard and relatively flexible commercial software packages that are already used in some jurisdictions, but simpler approaches may also work just as well for some parties providing services in the NDIS, as effective communication need not require common or highly sophisticated IT systems. (These matters are discussed in chapter 10.)

- Development would start on the assessment toolbox so that a reasonable measure would be available at the commencement of the scheme. The Australian Government would fund its development and it would be tested in pilot form in some states for selected groups of existing clients.

- The detailed elements of how self-directed funding would work and what rules should apply would need to be agreed to.

- The fine details on the role of non-government intermediaries (DSOs) would need to be determined, arrangements put in place to encourage their formation, and people with disabilities would need to be made aware of their potential role in the new scheme.

- Work would be needed with interested support and advocacy groups to plan how to build confidence so that people with disabilities will exercise choice in the new arrangements. People with disabilities and their carers will be looking for information and guidance about the assessment procedures, case management, self-directed funding and complaints mechanisms. Existing disability organisations and advocacy groups should play a key role in disseminating this information.

- Arrangements would also be set in train to encourage capacity building for service providers, who would face a considerably altered client base and client expectations and would require encouragement and guidance to develop appropriate skills and to support their workforce (including training for staff in new service offerings and in dealing with consumers with much greater autonomy to make their own decisions).

- Quality monitoring of service providers would be required to protect the interests of clients. The taskforce would oversee the development of the precise procedures and arrangements for implementing the arrangements spelt out in chapter 8, including standards, reporting requirements and other quality controls (chapter 8).

- Planning should also commence:

- for a regional presence for the scheme. Medicare or Centrelink offices would be appropriate in remote areas such as Weipa or the Tiwi Islands.

- on workforce development, in view of expected large increase in demand

- to build an evidence base for possible early intervention programs

- to develop an Indigenous strategy

- to develop information dissemination strategies (for example, web design) and to prepare for a future research role.

The costs of setting up the NDIS, while significant, would be reduced by using the NSW LTCS scheme, TAC, ACC or MAIB schemes as sources for well-tested procedures, guidelines and operating systems. And while there are many details to be sorted out, there are many people within the current state and territory disability services sectors with experience and expertise in the provision of disability support. There are also long-standing working groups of state officials who are well versed in many of the issues confronting the sector, and who are already seeking to make beneficial changes.

The taskforce should also start work on the structural elements of the NDIS, once its agreed form is clear. As noted in chapter 7, Commonwealth legislation would be needed to establish the NDIS and the NDIA, and to set in train processes for the creation of the appointment panel for the board, appointment of the board, appointment of the advisory council, the appropriation of funds (and the formula relating to these) and funds management. Such legislation can be sequenced as needed, starting with an early establishment Act, which can be followed later by a financing Act, and the main Act for the scheme.

#### Targeted consultation will be needed

This preparatory work would draw on the skills and knowledge of practitioners in the field, and would seek to build upon the best features of the current state schemes. The taskforce would need to consult with key groups to reach a position on many of the matters listed above. For example, discussions would need to be held with:

- disability professionals and insurance experts, about terminology, data definitions, assessment standards and protocols

- people with disabilities, about how the proposed scheme should work and how it would interact with them

- service providers, about administrative procedures, the proposed arrangements for self-directed funding and quality control measures.

However, these consultations should be about implementation, and it is important that they be well-targeted and not prolonged. Their primary purpose would be to obtain particular information and to test the practicality and appropriateness of the proposed building blocks of the scheme.

The important thing is to start early on areas where progress would lead to more effective building blocks for better future provision of disability support services, almost irrespective of the final shape of the scheme, and not wait for the structural and legal aspects of the scheme to be agreed upon. The latter approach would lead to completely unnecessary delays in implementing better support programs for people with disabilities.

The Commission sees its proposed timetable (table 17.2) as realistic and achievable. Other large public policy changes have also been introduced to tight timeframes in the past. The Job Network — a sweeping change in employment services across Australia — took two years to implement. The Higher Education Contribution Scheme was also introduced over a very short period, as was Medibank (box 17.2).

Do not delete this return as it gives space between the box and what precedes it.

Box 2 Implementing Medibank

Medibank started on schedule, on 1 July 1975. In nine months, the Health Insurance Commission had increased its staff from 22 to 3500, opened 81 offices, installed 31 minicomputers, 633 terminals and 10 medium-sized computers linked by land-lines to the central computer, and registered and issued health insurance cards to 90% of the Australian population. Its information technology was, for its day, state of the art, but the enormous burden of processing around 150 000 claims a day caused severe problems for some months. It was December before the processing delays had been overcome …

Source: Scotton (2000, pp. 9–11).

### Implement the NDIS slowly and build it up over time

Even with successful completion of the preparatory work discussed above, the proposed NDIS would be too large and complex to implement fully at a single start date. It would need to be rolled out in a carefully staged way. Consequently, many people who would be entitled to support services under the guiding legislation would not be able to receive them until the scheme was fully operational, which will take several years (five years, in the Commission’s view). The drafting of the legislation should include a timetable for the transition to a full scheme. But once fully operational, the scheme would provide support services to all who are entitled, as specified in the legislation.

As noted in chapter 3, the Commission is recommending that the NDIS provide three tiers of support (and therefore, three somewhat different populations of customers):

- tier 1: promoting opportunities for people with disabilities, and creating community awareness of the issues that affect people with disabilities; and minimising the impact of disability

- tier 2: information, referral and web-based services

- tier 3: the provision of funded individualised supports.

When the NDIA first begins operation, it would need to be able to begin delivering tier 1 and tier 2 services, at least initially at a basic level. Delivery of these services should improve quickly, as the NDIA refines its processes and learns more. The feasible number able to be brought into the scheme each year will depend in part on the success of the implementation taskforce in settling some of the preparatory matters discussed above.

For the all-important tier 3 services, the Commission proposes that the scheme would begin with a group of clients that is sufficiently large, but not unmanageably so. While all people with disabilities entitled to support from the NDIS have high needs, there are too many for the scheme to incorporate all of them in the proposed first year of operation (2014). The scheme needs to begin slowly to allow the NDIA to test its procedures, learn about what elements of the scheme work best and determine what adjustments need to be made. The administrative arrangements will need to be bedded down, links with external assessors and support providers made functional, regional offices opened and staffed, and so on. The capacity of the available workforce of experienced assessors and case managers to handle a sizeable intake load, and the effectiveness of internal processes to equilibrate their decisions, would also be an important constraint.

Gradual implementation would allow the NDIA to refine the scheme’s processes with a client base that is not overwhelming; build robust and well-functioning assessment, funding and case management processes; fine tune administrative arrangements; and allow for a measured recruitment process that would encourage good staffing selection (rather than a rush to select a large number of people in a short time period).

Moreover, given the inevitable uncertainties about the exact costing of the scheme before its commencement (chapter 14), the early phase would be used to provide a much more precise estimate of the longer-run size of the Australian Government’s premium contributions to the NDIS premium fund. It is difficult to predict such matters as how many people with disabilities will apply to the NDIA for services and support, what their assessments will reveal in the way of reasonable and necessary support, what mix of needs they will have, how much informal care they can reasonably be expected to rely upon themselves, and so on.

The phased introduction of the scheme would reduce the risks of costly, abrupt changes to the services market, as funding shifts from block to individualised funding. It would give service providers time to adapt their administrative systems, and to train and recruit new staff. Moreover, the transition period would allow people employed in state government disability departments to make a decision about whether to stay in the state government services field, shift into the NDIA or choose other roles. The NDIA and service providers could be expected to employ many of these people.

#### Which people to start with?

Our proposal would be to select a particular region that contained a modest number of likely clients (say, around 10 000) and implement the scheme there in 2014 (stage 1). This would be the ‘test bed’ for the scheme, where early problems could be identified and ironed out, the efficacy of the toolbox tested and refined, and more precise estimates of likely scheme costs arrived at.

In the second year, the scheme would expand Australia-wide, and should be fully operational by 2018. In the intervening years, more people with disabilities would be brought into the scheme. Groups that might be considered for the early rollout stages might include:

- people with newly-acquired disability who would meet the criteria for support under the scheme; this would allow the NDIA to learn about helping clients from the onset of disability, allow for the optimal use of early intervention measures, and might limit the scheme’s exposure to cost escalations, were these clients to be brought in at a later date

- children aged under five years who have substantial core activity limitations, as early investments have the potential to have high long-run payoffs

- select groups for whom involvement in pilot early intervention programs looks promising; this would inform future therapies and approaches to disability

- people who are now cared for by ageing carers, thus benefiting both the person with a disability and the aged carer

- people who have been inappropriately placed in nursing homes, thereby also freeing up nursing home resources for elderly people.

The practicality of particular levels of intakes each year should be a matter for the NDIA to manage this as it sees fit. As it built up its internal capacity and refined its procedures to reflect what it had learned while supporting stage 1 clients, it would be well-placed to decide such matters. For example, it might choose to take on much larger numbers of clients in the second and subsequent years, as its systems, procedures and workforce were more established and the NDIA had become a more experienced agency.

Table 2	Implementation of the NDIS

| Date | Milestone |
| --- | --- |
| Second half of 2011, or early 2012 | COAG would: - agree to an MOU that sets out in-principle agreement that the NDIS should commence in stages from Jan 2014 - create a high level taskforce from all jurisdictions, to be headed by a person with insurance or disability experience who has driven change successfully in a large organisation (appointed with the agreement of all jurisdictions) the taskforce would: - work full time on planning the details of the scheme - develop a draft intergovernmental agreement for final signing in 12 months - report back regularly to Heads of Treasuries meetings and COAG on milestones reached in the planning for the commencement of NDIS by Jan 2014 |
| Feb 2013 COAG meeting | final consideration and agreement by COAG to the intergovernmental agreement, including an agreement on funding arrangements announcement of the NDIS Board taskforce executive to act as interim staff |
| March to May 2013 | Commonwealth to introduce legislation to create NDIS and NDIA, with an initial appropriation - state legislation and further Commonwealth legislation to follow board to commence formally - board to appoint a CEO - staff to be recruited |
| July 2013 | appoint NDIA case managers - intensive training over 2 months test information systems between those who want to be service providers and the NDIS |
| Sep to Dec 2013 | establish local and regional offices for NDIA intensive training of allied health professionals as NDIS assessors commencement of public information campaign; outreach by local case managers to local disability organisations, people with disabilities, existing and potential service providers, local community service groups and local media information sessions across Australia for people with disabilities, their families and carers, service providers and the general community - what the NDIS will do for people - the assessment process - people’s rights and responsibilities disability organisations also to undertake group information sessions call for interest and pre-registration of stage 1 clients (Continued next page) |

Table 2	(continued)

| Date | Milestone |
| --- | --- |
| Jan 2014 | NDIS commences with a full-scale rollout in a region with around 10 000 clients. That would allow fine-tuning of the scheme, while providing high quality services to many thousands of people. |
| 2015 | in Jan 2015, rollout would extend nationally to cover all of Australia - progressively it would be expanded to cover all relevant people with a disability, commencing with all new cases of significant disability and some of the groups most disadvantaged by the current arrangements. |
| 2017 | NDIA evaluation of effectiveness of self-directed funding |
| 2018 | all current and new clients to be receiving NDIS services |
| 2020 | independent review of NDIA and NDIS |

However, many people have been waiting a long time for better services, so the process for recruitment into the scheme must not be open-ended. The Commission proposes that the NDIA’s legislation should give the NDIA some flexibility, but should specify that all those who met the criteria for entitlement must be receiving services by 2018.

## 4	Interaction between the two schemes

There are likely to be some economies of scope between NDIS and NIIS (for example, some local case managers, assessors and support providers may undertake the same function for clients in both schemes). In such cases, it would be important to streamline compliance burdens, for example, in relation to reporting and performance monitoring, to avoid a ‘doubling-up’ of such requirements.

In time, there may be some logic in bringing the NIIS into the NDIS. However, as discussed in chapter 16, this is not clearcut, as there are some differences between the two schemes, and the gains from a merger might not be worth incurring the costs. The Commission consider it much more important that governments address the undoubted problems of the present arrangements through the NDIS and NIIS, rather than wait many more years in an attempt to achieve a consensus on a single all-encompassing scheme.

The Commission recommends that, in 2020, governments should institute an independent and public inquiry into the appropriateness of a merger. After this period of operation, sufficient experience and information would be available then to better establish the costs and benefits of this.

In the second half of 2011 or early 2012, the Australian Government and the state and territory governments should, under the auspices of COAG, agree to a memorandum of understanding that sets out an in-principle agreement:

DRAFT RECOMMENDATION 17.1

- that the NDIS should commence in stages from January 2014, be rolled out nationally in 2015 and be fully operational by 2018

- to follow the reform timetable for the NIIS specified in draft recommendation 16.5.

The Australian Government and the state and territory governments, under the auspices of COAG, should create:

DRAFT RECOMMENDATION 17.2

- a full-time high level taskforce from all jurisdictions to commence work on the detailed implementation of the NDIS

–	to be headed by a person with insurance or disability experience who has driven change successfully in a large organisation, appointed with the agreement of all jurisdictions

–	with a draft intergovernmental agreement to be prepared for final consideration and agreement by COAG in February 2013

- a full-time high level taskforce from all jurisdictions to commence work on the implementation of the NIIS by the states and territories.

In the period leading up until the full introduction of the NDIS, the Australian Government should supplement funding under the National Disability Agreement to reduce some of the worst rationing of support services.

draft recommendation 17.3

In 2020, there should be an independent public inquiry into the operation of the NDIS and its effectiveness in meeting the needs of people with disabilities. The review should also encompass the review of the NIIS as set out in draft recommendation 16.5.

DRAFT RECOMMENDATION 17.4