WESTERN AUSTRALIA – Progress against Subacute Care Implementation Plan

National Partnership Agreement on Hospital and Health Workforce Reform – Schedule C

July 2011 – June 2012

Summary of Progress

WA can report a third successful year of progress against the WA Subacute Care Implementation Plan. Projects commenced over the period 2009-2011 continued, with further consolidation and expansion. A number of these projects formed the basis for further expansion with Schedule E NPA2 funding. Outstanding projects planned to begin in 2010-2011 were implemented, while projects scheduled to begin in 2011-2012 also commenced. Important milestones completed in 2011-2012 were the establishment of the 10 bed Geriatric Evaluation and Management Unit at Fremantle Hospital in the South Metropolitan Health Region, a 14 bed Evaluation and Management Unit at Sir Charles Gairdner Hospital in the North Metropolitan Health Region and the dedicated 10 bed stroke rehabilitation unit at Bentley Hospital in the South Metropolitan Health Region. In addition, the WA Statewide Subacute Care Training and Development Centre (TRACS WA) was established. This marks an important milestone in the implementation of the WA Subacute Care Plan 2009-2013. Department of Health recruitment processes delayed the employment of personnel over the period 2010-2011. However, with key positions in place in the last quarter much progress has been noted. The Centre is the first of it’s kind in WA and has been established to improve the quality of services provided to Western Australians in the areas of rehabilitation, geriatric evaluation and management, and psycho-geriatric care by supporting staff who work in these areas. TRACS WA is making training accessible through: - videoconferencing - self-paced learning packages - e-learning - communities of practice meetings - funding and support of skills exchange programs - workshops and seminars. TRACS WA is located in Thorburn House on the Shenton Park Campus of Royal Perth Hospital. The Centre is led by two Co-Chairs; Associate Professor, Christopher Beer who is a highly experienced and respected consultant geriatrician based at Royal Perth Hospital and the University of WA, and Gail Milner, Operational Director, Innovation and Health System Reform, Department of Health. The Centre is also supported by an Expert Reference Group of respected specialist clinicians and academics currently practicing in the subacute domains. Financial savings from delayed start dates have been re-invested in the development of the geriatric workforce through the funding of additional trainee positions; two in the metropolitan area and one position in the South-West. Re-investment of savings has also allowed the further expansion of services that perform well and/or have enabled the diversification of existing services. Examples are the North Metropolitan Area Health Service Parkinson’s Disease Outreach Program at both Osborne Park Hospital and Swan Kalamunda Hospital where a full multi-disciplinary allied health team with medical governance supports patients on an outpatient basis in the eastern metropolitan region. Day Therapy Unit services have also benefited from expansion through reinvestment of savings. Timely implementation and consolidation of services funded through the WA Subacute Care Plan has served to strengthen the credibility of the reform process for subacute care services. The gradual expansion of subacute services across the state in the third year of the operation of the WA Subacute Care Plan has provided a strong platform for service expansion in Schedule E. Notable achievements also continue in the area of data collection processes with further improvement in the quality of subacute care data. With funding allocated to the employment of staff dedicated to the improvement of subacute care data collection, there has been a greater awareness and understanding of the importance of accurate data collection across the WA Department of Health. This has also benefited the process of data recording and collection for Schedule E reporting.

| Key deliverables |  | Progress and timing | Allocation of NPA funding | Comments |
| --- | --- | --- | --- | --- |
| REHABILITATION |  |  |  |  |
| DAY THERAPY SERVICES - Increase in service delivery levels at metropolitan Day Therapy sites: - Increase in service delivery levels at regional sites: |  | Service delivery at full capacity according to agreed funding level for 2011-2012 Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $4,643,738 total - Recurrent funding - $1,479,864 in 2011-12 - $2,558,414 total - Recurrent funding - $783,613 in 2011-12 | 2011-2012 project deliverables completed. Metropolitan services occurring at Armadale, Bentley, Fremantle – Moss Street, Joondalup, Osborne Park Hospital, Mercy Day Therapy, Sir Charles Gairdner, Swan Districts and Rockingham. Regional services occurring at Geraldton, Northam, Albany and Bunbury. |
| REHABILITATION IN THE HOME (RITH) - Increase in service delivery levels in metropolitan area COMMUNITY REHABILITATION (WA COUNTRY HEALTH SERVICES) - Commencement of home-based service delivery in regional locations |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $3,495,408 total - Recurrent funding - $999,675 in 2011-12 - $655,430 total - Recurrent funding - $217,858 in 2011-12 | 2011-2012 project deliverables completed: Expansion of existing rehabilitation in the home (RITH) services in the North Metropolitan Region linked to Osborne Park and Joondalup Hospital sites and in the South Metropolitan Region linked to the Armadale, Bentley, Peel and Rockingham Hospital sites. 2011-2012 project deliverables completed: Home-based rehabilitation services commenced at Geraldton, Albany. *Note: It was originally planned to have commence community rehabilitation at Bunbury. The funding has been converted to Day Therapy services at outlying sites in the South West. This is reflected in the reduction in funding for Community Rehabilitation). |
| COMMUNITY PHYSIOTHERAPY SERVICES - Increase in existing community based physiotherapy services in the North and South Metropolitan Regions - Increase in community based physiotherapy services at Northam |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites Full service at Northam hospital 2011-2012 | - $3,045,647 total - Recurrent funding - $887,134 in 2011-12 - $208,000 total - Recurrent funding - $62,240 in 2011-12 | 2011-2012 project deliverables completed. Diversification of community physiotherapy programs commenced, eg cardio-pulmonary, stroke rehabilitation. . |
| AMPUTEE SPECIALIST REHABILITATION SERVICES - Specialist medical rehabilitation services for amputee patients with the integration of an allied health multi-disciplinary team to service North and South Metro Regions |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $710,627 total - Recurrent funding - $156,526 in 2011-12 | 2011-2012 project deliverables completed: The multidisciplinary outreach service is provided by the Statewide Rehabilitation Centre (Shenton Park) and delivered at outpatient clinics at Fremantle and Sir Charles Gairdner Hospitals. |
| DEDICATED PARKINSON DISEASE AMBULATORY CARE OUTREACH REHABILITATION SERVICES – SOUTH METROPOLITAN REGION - Regional ‘hub and spoke’ model with a multi-disciplinary rehab focus for people with Parkinson’s disease at Day Therapy Units. |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $3,741,305 total - Recurrent funding - $1,278,000 in 2011-12 | 2011-2012 project deliverables completed Allied health and clinical experts from a central Day Therapy Unit (Moss Street Centre for clinical expertise and training) consult at satellite units on a rotating basis; Armadale, Bentley, Rockingham/Peel. Establishment of Centre of Excellence in Parkinson’s Disease in South Metro. |
| DEDICATED PARKINSON DISEASE AMBULATORY CARE OUTREACH REHABILITATION SERVICES – NORTH METROPOLITAN REGION - Regional “hub and spoke” model with a multi-disciplinary rehab focus for people with Parkinson’s disease at Day Therapy Units. |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $441,624 total - Recurrent funding - $217,000 in 2011-2012 - $280,000 total - $80,400 in 2011-12 | Expansion of 2011-2012 project deliverables for Parkinson’s Disease Rehabilitation programs A full multi-disciplinary team including medical specialist input established at Swan Districts Hospital to service north-eastern metropolitan catchment area. Service operates with the Day Therapy Unit program. Linked to Osborne Park Hospital centre for clinical expertise and training in capacity as North Metropolitan Centre of Excellence in Parkinson’s Disease. Outreach nursing service for central north metropolitan region to complement existing Osborne Park Hospital Centre of Excellence for Parkinson’s Disease. |
| SECONDARY STROKE UNIT IN NORTH METROPOLITAN REGION - Integrated secondary stroke rehabilitation service – Osborne Park Hospital |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $3,834,097 total - Recurrent funding $1,388,585 in 2011- 2012 | 2011-2012 project deliverables completed: North Metropolitan Area Health Secondary Stroke unit at Osborne Park Hospital with Early Supported Discharge and Outpatient service. The dedicated inpatient unit is 10 beds. This service acts to take pressure off acute hospital services at the Sir Charles Gairdner Hospital tertiary site. |
| SECONDARY STROKE SERVICES IN SOUTH METROPOLITAN AREA HEALTH SERVICE - BENTLEY HOSPITAL - Integrated secondary stroke rehabilitation service – Bentley Hospital |  | Service Commencement 2011-12 | - $2,521,000 total - Recurrent funding $1,165,000 in 2011-2012 | 2011-2012 project deliverables completed: Inpatient and outpatient services dedicated to stroke rehabilitation at South Metropolitan secondary hospital site, meeting objectives of rehabilitation care provision ‘closer to home’ and taking pressure off acute hospital services at the Royal Perth Hospital tertiary site. |
| NEUROSCIENCE SPECIALIST -SOUTH METROPOLITAN AREA HEALTH SERVICE - BENTLEY HOSPITAL |  | Service commencement October 2012 | - $127,250 total - Recurrent funding $31,250 2011-2012 | This position is intended to provide the specialised medical consultation for the stroke unit at Bentley Hospital as well as provide expertise and clinician availability for Parkinson’s Disease programs. Delays in recruitment and a “false start” have hampered the full operation of the service. Recruitment to the position has now been resolved with the intention to commence full operation in January 2012-2013. |
| MID-WEST REHABILITATION INPATIENT - Geraldton |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $327,215 total - Recurrent funding - $109,000 in 2011-12 | 2011-2012 project deliverables completed: Additional Allied health resources to service inpatient rehabilitation needs at Geraldton Hospital. |
| GREAT SOUTHERN INPATIENT REHABILITATION - Albany |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $327,215 total - Recurrent funding - $109,000 in 2011-12 | 2011-2012 project deliverables completed: Additional allied health resources to service inpatient rehabilitation needs at Albany Hospital |
| SOUTH WEST INTEGRATED REHABILITATION SERVICE - Inpatient rehabilitation and restorative service servicing South-West region of WA |  | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $4,456,000 total - Recurrent funding $1,792,150 2011-2012 | 2011-2012 project deliverables completed. Dedicated 10-bed inpatient unit at Bunbury Regional Hospital, integrated with the Day Therapy Unit and linked to regional sites. A Geriatrician provides consultancy and liaison services throughout the South West Health region. |
| OUTSTANDING PROJECTS 2011-2012 - REHABILITATION |  |  |  |  |
| INTEGRATED REHABILITATION SERVICE - KALGOORLIE | Recruitment phase |  | - $586,000 total - Recurrent funding - $63,000 2011-2012 - Additionally, $33,000 was expended in 2011-2012 for site visits to Kalgoorlie Regional Hospital by a metropolitan based rehabilitation physician. | Service model in a rural and remote region determined. Initial visiting service by metropolitan based rehabilitation physician suspended until recruitment of Rehabilitation Coordinator completed. Position advertised. Anticipated commencement will occur November 2012. Following this, the service will recommence with visiting rehabilitation physician visits. It is proposed to establish a dedicated Inpatient and Day Therapy Unit service based on a multi-disciplinary approach to rehabilitation. A specialist rehabilitation visiting service will be purchased from a metropolitan tertiary teaching hospital to provide assistance for medical governance of the program. |

| GERIATRIC EVALUATION AND MANAGEMENT |  |  |  |
| --- | --- | --- | --- |
| GERIATRIC EVALUATION AND MANAGEMENT SERVICE – SOUTH-WEST REGION OF WA | Full service commencement 2011-2012 | - $989,000 total - Recurrent funding - $337,704 in 2011-12 | 2011-2012 project deliverables completed. Geriatric consultation and liaison across the South-West region. |
| GEM SERVICES AT DAY THERAPY SITES IN THE METROPOLITAN REGION | Full service commencement 2011-2012 | - Nil allocation, within existing Department of Geriatric Medicine resources | 2011-2012 project deliverables completed Best practice initiative/ State-wide Reform Program underway to promote consistent assessment practices, equity of access to a uniform suite of services across WA continues with engagement of all Day Therapy Units and geriatricians in metropolitan and regional areas. Data collection processes improved with mapping to national Tier 2 Non-admitted data collection framework. |
| VISITING GERIATRICIAN CONSULTATION AND LIAISON SERVICE TO ALL RURAL AND REMOTE REGIONS | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $1,365,267 total - Recurrent funding - $338,121 in 2011-12 | 2011-2012 project deliverables completed Visiting Geriatrician Service support across WA Country Health Services to provide a specialist geriatric consultation and liaison service. Sites visited include Bunbury, Collie, Busselton, Harvey, Bridgetown, Narrogin, Albany, Kalgoorlie, Esperance, Northam, Merredin, Moora, Geraldton, Port Hedland, Broome, Kununurra. |
| CLINICAL SUPPORT SERVICE FOR VISITING GERIATRICIAN SERVICE TO RURAL AND REMOTE REGIONS | Service delivery at full capacity according to agreed funding level for 2011-2012 at specified sites | - $1,061,563 total - Recurrent funding - $353,775 in 2011-12 | 2011-2012 project deliverables completed Clinical support in WA Country Health Services region that provides support for the Visiting Geriatrician Service and implementation of care recommendations post consultant geriatrician visit. Sites are as listed in preceding paragraph for Visiting Geriatrician services. |
| NORTH METROPOLITAN AREA HEALTH SERVICE – DEDICATED GEM UNIT | Commencement August 2011 | - $1,365,000 total - Recurrent funding for allied health - $525,000 2011-12 - Additional funding $100,000 for GEM registrar position | A 14-bed Unit at Sir Charles Gairdner Hospital commenced in August 2011, providing the only dedicated GEM Unit for the North Metropolitan region. It is a “fast-track” rehabilitation ward located on a tertiary hospital campus. |
| SOUTH METROPOLITAN AREA HEALTH SERVICE – DEDICATED GEM UNIT | Commencement September 2011 | - $897,000 total - Recurrent funding for allied health - $413,000 2011-12 | A 10-bed GEM Unit commenced at Fremantle Hospital in September 2011, providing a dedicated GEM Unit for the South Metropolitan region. It is a “fast-track” rehabilitation ward located on a tertiary hospital campus and is similar in model to the North Metropolitan region GEM unit. |
| REINVESTMENT STRATEGY – GERIATRIC WORKFORCE DEVELOPMENT | Commencement January 2012 | - $1,286,110 in total - recurrent funding $325,000 | Savings accumulated across the three year operation of the WA Subacute Care Plan provided the opportunity for re-investment in the geriatric workforce for three positions: - Advanced trainee registrar in geriatrics Bentley Hospital - Advanced trainee registrar in geriatrics – Bunbury Regional Hospital - Basic trainee registrar in geriatrics – Armadale Hospital - Fractured Neck of Femur discharge nurse at Osborne Park Hospital - Occupational Therapist - RPH GEM Unit |

| PSYCHO-GERIATRIC CARE |  |  |  |
| --- | --- | --- | --- |
| CO-LOCATION OF DEDICATED IN-PATIENT PARKINSON DISEASE REHABILITATION SERVICES WITH PSYCHOGERIATRIC CARE SERVICES – SOUTH METROPOLITAN REGION | As reported in the 2009-2010 Annual Report, this project was redefined and reconfigured to become the Parkinson’s Disease outreach rehabilitation service for the South Metropolitan Area Health Service region. | N/A | N/A |
| VISITING PSYCHO-GERIATRICIAN CONSULTATION AND LIAISON SERVICE - RURAL AND REMOTE REGIONS | Full service commencement 2011-2012 | - $837,821 total - Recurrent funding - $269,520 in 2011-12 | 2011-2012 project deliverables completed Visiting Psycho-geriatricians conduct clinics at Albany, Bunbury, Broome, Geraldton, Kalgoorlie, Esperance, Kununurra, Port Hedland, Carnarvon, Northam, Narrogin, Merredin. |
| SENIOR OLDER ADULT MENTAL HEALTH SUPPORT SERVICE – RURAL AND REMOTE REGIONS | Full service commencement 2011 -2012 | - $1,451,110 total - Recurrent funding - $422,800 in 2011-12 | Older adult mental health professionals in rural and remote regions provide support for the Visiting Psycho-geriatrician Service and for local specialist mental health services, by implementing the care plans and recommendations established by the medical consultants. Sites are as listed in the preceding paragraph for Visiting Psycho-geriatrician service. |
| PALLIATIVE CARE |  |  |  |
| PALLIATIVE CARE TRAINING REGISTRARS POSITIONS - Two community-based palliative care medical registrar training positions to service the North and South Metropolitan Regions | Full service commencement in 2011-2012 | - $893,368 total - Recurrent funding - $222,669 in 2011-12 | 2011-2012 project deliverables completed |
| PALLIATIVE CARE TRAINING FOR RESIDENTIAL AGED CARE - Evidence Based Training Package | Full service commencement in 2011-2012 | - $567,000 total - Recurrent funding - $221,749 in 2011-12 | 2011-2012 project deliverables completed Waitlisted bookings for RACF participation in the program occurred in 2011-2012. |
| WORKFORCE TRAINING AND DEVELOPMENT |  |  |  |
| - Clinical Training and Workforce Development Unit | Establishment of a Training and Development Unit completed. | - $2,162,098 total - Recurrent funding - $534,203 in 2011-12 | - Recruitment completed with Co-Chairs, Coordinator, Clinical Leads and Development Facilitators in place. Achievements in 2011-2012: - Partnering with WA Health workers and agencies to support community initiated innovative learning activities - Partnering with agencies already delivering training and resources relevant to subacute care to improve accessibility to the material - Creation of a Community of Practice in Subacute Care to partner workers across the domains and across rural and metro sites to share information, resources and expertise - Development of a governance structure that includes partners from multiple disciplines (health and teaching and learning experts) and agencies (within and external to health) to guide and support the centre’s operations and creation of formal documentation. - A skills development/exchange program between metropolitan and rural sites. An example is the Kimberly OAMH and Aged Care Team site visit to Royal Perth Hospital and linked community based services. |
| DATA COLLECTION AND REPORTING |  |  |  |
| SUBACUTE CARE REPORTING AND IMPROVEMENTS IN DATA COLLECTION | Across life of COAG NPA funding | - $825,000 total - Recurrent funding - $224,000 in 2011-12 | WA has participated in national meetings to achieve national consistency in subacute care measurement. Improvement in statewide collection of subacute care activity with dedicated funding for additional positions located within Data Integrity Branch. Improvements in data collection have contributed to a revision in baseline methodology for 2007-2008 and revised activity for 2009-2010, 2010-2011 and 2011- 2012. Development and implementation of data collection reporting frameworks to support the Subacute Care NPA that will be self-supporting and sustainable beyond the life of the NPA funding. |